## 00. SUMMARY
Summary of RFI for ELECO
[12 empty] | Date : | 2025-11-10
01. Total Summary for RFI
| SubCon | Unit | Discipline | Code | Type | Accumulative RFI Status
[6 empty] | Issued | Accepted | Ongoing | Rejected | Cancelled | Remark
| ELECO | C300 | Trial Mix | TRM | RFI | 0 | 0 | 0 | 0 | 0 | * Cancelled due not ready to inspection.
|  |  | Material Receiving | MRI | RFI | 3 | 0 | 3 | 0 | 0
|  |  | General Test | GLT | RFI | 1 | 0 | 1 | 0 | 0
|  |  | Survey Work | SVW | RFI | 0 | 0 | 0 | 0 | 0
|  |  | Brickwork | BRI | RFI | 10 | 10 | 0 | 0 | 0
|  |  | Plaster | PLA | RFI | 11 | 10 | 0 | 0 | 1
|  |  | Ceiling | CEI | RFI | 0 | 0 | 0 | 0 | 0
|  |  | Tile | TIL | RFI | 1 | 1 | 0 | 0 | 0
|  |  | Water Proofing | WTP | RFI | 2 | 0 | 2 | 0 | 0
|  |  | Roofing | RFG | RFI | 3 | 0 | 3 | 0 | 0
|  |  | Window and Door | WDD | RFI | 4 | 4 | 0 | 0 | 0
|  |  | Fitting | FIT | RFI | 1 | 0 | 0 | 0 | 0
|  |  | Floor | FLR | RFI | 7 | 4 | 1 | 0 | 2
|  |  | Painting | PAI | RFI | 7 | 5 | 2 | 0 | 0
| Total |  |  |  |  | 43 | 29 | 10 | 0 | 3 |  |  |  | Beginning Date | 2024-01-01
[14 empty] | ending date | 2025-12-31
02. Pending Items
| Item |  | ELECO
CIVIL WORK
RFI
| Ongoing |  | 10
| Pending Sign |  | 0
| Pending Attachment |  | 0
| Reschedule |  | 0
| On schedule |  | 0
| Total: |  | 10

## 01.RFI_TRM
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2025-11-10
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY

## 02.RFI_MRI
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2025-11-10
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Building | RFI-ELE-ARC-F-C300-MRI-0001 | External | Eleco | Civil Work | N/A | Architecture | Material Receiving | Material Receiving for Anti Dust Epoxy System Jotafloor for Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-06-19 | 2025-06-20 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 2 | Building | RFI-ELE-ARC-F-C300-MRI-0002 | External | Eleco | Civil Work | N/A | Architecture | Material Receiving | Material Receiving for Powerfloor Raised Floor for Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-06-26 | 2025-06-27 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 3 | Building | RFI-ELE-ARC-F-C300-MRI-0003 | External | Eleco | Civil Work | N/A | Architecture | Material Receiving | Material Receiving for panice device push bar for fire rated door Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-10-30 | 2025-10-31 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
-
-
-
-
-
-
-
-
-
-
-

## 03.RFI_GLT
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2025-11-10
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Building | RFI-ELE-ARC-F-C300-GLT-0001 | External | Eleco | Civil Work | N/A | Architecture | General Inspection | Final Inspection and Handover IER Room to HQC E&I at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-07-31 | 2025-08-01 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing

## 04.RFI_SVW
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2025-11-10
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY

## 05.RFI_BRI
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2025-11-10
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-ARC-F-C300-BRI-0001 | External | Eleco | Civil Work | N/A | Architecture | Brickwork | Inspection of bricklaying at GroundFloor Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-03-10 | 2025-03-11 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 2 | Civil | RFI-ELE-ARC-F-C300-BRI-0002 | External | Eleco | Civil Work | N/A | Architecture | Brickwork | Inspection of bricklaying at GroundFloor Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-03-17 | 2025-03-18 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 3 | Civil | RFI-ELE-ARC-F-C300-BRI-0003 | External | Eleco | Civil Work | N/A | Architecture | Brickwork | Inspection of bricklaying at GroundFloor Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-03-22 | 2025-03-24 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 4 | Civil | RFI-ELE-ARC-F-C300-BRI-0004 | External | Eleco | Civil Work | N/A | Architecture | Brickwork | Inspection of bricklaying, lintel and stiffener at GroundFloor Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-04-05 | 2025-04-07 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 5 | Civil | RFI-ELE-ARC-F-C300-BRI-0005 | External | Eleco | Civil Work | N/A | Architecture | Brickwork | Inspection of bricklaying, lintel and stiffener at 1st floor Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-04-10 | 2025-04-11 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 6 | Civil | RFI-ELE-ARC-F-C300-BRI-0006 | External | Eleco | Civil Work | N/A | Architecture | Brickwork | Inspection of bricklaying, lintel and stiffener at Ground Floor and 1st floor Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-04-14 | 2025-04-15 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 7 | Civil | RFI-ELE-ARC-F-C300-BRI-0007 | External | Eleco | Civil Work | N/A | Architecture | Brickwork | Inspection of bricklaying, lintel and stiffener at Ground Floor and 1st floor Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-04-21 | 2025-04-22 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 8 | Civil | RFI-ELE-ARC-F-C300-BRI-0008 | External | Eleco | Civil Work | N/A | Architecture | Brickwork | Inspection of bricklaying, lintel and stiffener at Ground Floor and 1st floor Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-04-28 | 2025-04-29 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 9 | Civil | RFI-ELE-ARC-F-C300-BRI-0009 | External | Eleco | Civil Work | N/A | Architecture | Brickwork | Inspection of door lintel, window awning concreting for switchgear room at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-05-05 | 2025-05-06 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 10 | Civil | RFI-ELE-ARC-F-C300-BRI-0010 | External | Eleco | Civil Work | N/A | Architecture | Brickwork | Inspection of bricklaying, lintel and stiffener at GF Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-11-10 | 2025-11-11 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
-

## 06.RFI_PLA
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2025-11-10
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-ARC-F-C300-PLA-0001 | External | Eleco | Civil Work | N/A | Architecture | Plaster | Inspection of mock up plastering for brickwall at GroundFloor Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-03-17 | 2025-03-18 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Cancelled
| 2 | Civil | RFI-ELE-ARC-F-C300-PLA-0002 | External | Eleco | Civil Work | N/A | Architecture | Plaster | Inspection of mock up plastering for brickwall at GroundFloor Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-03-22 | 2025-03-24 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 3 | Civil | RFI-ELE-ARC-F-C300-PLA-0003 | External | Eleco | Civil Work | N/A | Architecture | Plaster | Inspection of plastering / skim for brickwall at GroundFloor Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-03-24 | 2025-03-25 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 4 | Civil | RFI-ELE-ARC-F-C300-PLA-0004 | External | Eleco | Civil Work | N/A | Architecture | Plaster | Inspection of plastering / skim for brickwall at GroundFloor Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-04-05 | 2025-04-07 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 5 | Civil | RFI-ELE-ARC-F-C300-PLA-0005 | External | Eleco | Civil Work | N/A | Architecture | Plaster | Inspection of plastering / skim for brickwall at 1 st Floor Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-04-10 | 2025-04-11 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 6 | Civil | RFI-ELE-ARC-F-C300-PLA-0006 | External | Eleco | Civil Work | N/A | Architecture | Plaster | Inspection of plastering / skim for brickwall at Ground floor and 1 st Floor Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-04-14 | 2025-04-15 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 7 | Civil | RFI-ELE-ARC-F-C300-PLA-0007 | External | Eleco | Civil Work | N/A | Architecture | Plaster | Inspection of plastering / skim for brickwall at Ground floor and 1 st Floor Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-04-21 | 2025-04-22 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 8 | Civil | RFI-ELE-ARC-F-C300-PLA-0008 | External | Eleco | Civil Work | N/A | Architecture | Plaster | Inspection of plastering / skim for brickwall at Ground floor and 1 st Floor Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-04-28 | 2025-04-29 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 9 | Civil | RFI-ELE-ARC-F-C300-PLA-0009 | External | Eleco | Civil Work | N/A | Architecture | Plaster | Inspection of plastering / skim for brickwall at Ground floor and 1 st Floor Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-05-19 | 2025-05-20 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 10 | Civil | RFI-ELE-ARC-F-C300-PLA-0010 | External | Eleco | Civil Work | N/A | Architecture | Plaster | Inspection of plastering / skim for brickwall at Ground floor and 1 st Floor Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-06-04 | 2025-06-05 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 11 | Civil | RFI-ELE-ARC-F-C300-PLA-0011 | External | Eleco | Civil Work | N/A | Architecture | Plaster | Inspection of plastering / skim for brickwall at Ground floor Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-11-10 | 2025-11-11 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
-
-
-

## 07.RFI_CEI
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2025-11-10
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY

## 08.RFI_TIL
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2025-11-10
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Building | RFI-ELE-ARC-F-C300-TIL-0001 | External | Eleco | Civil Work | N/A | Architecture | Tiling | Inspection for Acid Resistance Tiling Battery Room at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-06-19 | 2025-06-20 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted

## 09.RFI_WTP
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2025-11-10
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-ARC-F-C300-WTP-0001 | External | Eleco | Civil Work | N/A | Architecture | Waterproofing | Inspection of waterproofing for RC Roof Slab at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-04-29 | 2025-04-30 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 2 | Civil | RFI-ELE-ARC-F-C300-WTP-0002 | External | Eleco | Civil Work | N/A | Architecture | Waterproofing | Inspection of waterponding test for Roof Slab at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-05-05 | 2025-05-06 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing

## 10.RFI_RFG
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2025-11-10
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-ARC-F-C300-RFG-0001 | External | Eleco | Civil Work | N/A | Architecture | Roofing | Inspection of insulation installation for flat roof Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-05-13 | 2025-05-14 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 2 | Civil | RFI-ELE-ARC-F-C300-RFG-0002 | External | Eleco | Civil Work | N/A | Architecture | Roofing | Inspection of 50 mm cement screeding with 1:3 mortar for RC flat roof Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-05-20 | 2025-05-21 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 2 | Civil | RFI-ELE-ARC-F-C300-RFG-0003 | External | Eleco | Civil Work | N/A | Architecture | Roofing | Inspection of waterproofing layer for RC Flat Roof Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-10-30 | 2025-10-31 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing

## 11.RFI_WDD
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2025-11-10
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-ARC-F-C300-WDD-0001 | External | Eleco | Civil Work | N/A | Architecture | Installation | Inspection of fire rated door frame fit up and installation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-04-16 | 2025-04-17 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 2 | Civil | RFI-ELE-ARC-F-C300-WDD-0002 | External | Eleco | Civil Work | N/A | Architecture | Installation | Inspection of fire rated door frame fit up and installation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-04-21 | 2025-04-22 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 3 | Civil | RFI-ELE-ARC-F-C300-WDD-0003 | External | Eleco | Civil Work | N/A | Architecture | Installation | Inspection of fire rated door fit up and installation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-05-12 | 2025-05-13 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 4 | Civil | RFI-ELE-ARC-F-C300-WDD-0004 | External | Eleco | Civil Work | N/A | Architecture | Installation | Inspection of panic device push bar for fire rated door at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-10-30 | 2025-10-31 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted

## 12.RFI_FIT
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2025-11-10
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Building | RFI-ELE-ARC-F-C300-FIT-0001 | External | Eleco | Civil Work | N/A | Architecture | Fitting | Inspection of installation and fitting for anti climb fencing at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-06-19 | 2025-06-20 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted

## 13.RFI_FLR
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2025-11-10
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-ARC-F-C300-FLR-0001 | External | Eleco | Civil Work | N/A | Architecture | Flooring | Inspection of mock up anti dust epoxy resin flooring at Switch Room Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-05-06 | 2025-05-07 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Cancelled
| 2 | Civil | RFI-ELE-ARC-F-C300-FLR-0002 | External | Eleco | Civil Work | N/A | Architecture | Flooring | Inspection of anti dust epoxy resin flooring at Switch Room Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-06-04 | 2025-06-05 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Cancelled
| 3 | Civil | RFI-ELE-ARC-F-C300-FLR-0003 | External | Eleco | Civil Work | N/A | Architecture | Flooring | Inspection of surface preparation, cement render and anti dust epoxy resin at IER Room Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-06-12 | 2025-06-13 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 4 | Civil | RFI-ELE-ARC-F-C300-FLR-0004 | External | Eleco | Civil Work | N/A | Architecture | Flooring | Inspection of surface preparation, cement render and anti dust epoxy resin at Switch Room Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-06-16 | 2025-06-17 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 5 | Civil | RFI-ELE-ARC-F-C300-FLR-0005 | External | Eleco | Civil Work | N/A | Architecture | Flooring | Inspection of surface preparation, cement render and anti dust epoxy resin at UPS Room Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-06-19 | 2025-06-20 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 6 | Civil | RFI-ELE-ARC-F-C300-FLR-0006 | External | Eleco | Civil Work | N/A | Architecture | Flooring | Inspection of surface preparation, cement render and Carborundum epoxy resin at HVAC Room Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-07-28 | 2025-07-29 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 7 | Civil | RFI-ELE-ARC-F-C300-FLR-0007 | External | Eleco | Civil Work | N/A | Architecture | Flooring | Inspection of installation for Raised Floor at IER Room | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-07-28 | 2025-07-29 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing

## 14.RFI_PAI
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2025-11-10
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-ARC-F-C300-PAI-0001 | External | Eleco | Civil Work | N/A | Architecture | Painting | Inspection of painting (primer) for external wall Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-05-03 | 2025-05-05 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 2 | Civil | RFI-ELE-ARC-F-C300-PAI-0002 | External | Eleco | Civil Work | N/A | Architecture | Painting | Inspection of painting (primer) for internal wall Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-05-19 | 2025-05-20 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 3 | Civil | RFI-ELE-ARC-F-C300-PAI-0003 | External | Eleco | Civil Work | N/A | Architecture | Painting | Inspection of painting (primer) for external wall Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-05-19 | 2025-05-20 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 4 | Civil | RFI-ELE-ARC-F-C300-PAI-0004 | External | Eleco | Civil Work | N/A | Architecture | Painting | Inspection of painting (primer) for internal wall Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-06-04 | 2025-06-05 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 5 | Civil | RFI-ELE-ARC-F-C300-PAI-0005 | External | Eleco | Civil Work | N/A | Architecture | Painting | Inspection of painting (top coat) for fascia Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-06-16 | 2025-06-17 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 6 | Civil | RFI-ELE-ARC-F-C300-PAI-0006 | External | Eleco | Civil Work | N/A | Architecture | Painting | Inspection of painting (top coat) for external Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-07-02 | 2025-07-03 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 7 | Civil | RFI-ELE-ARC-F-C300-PAI-0007 | External | Eleco | Civil Work | N/A | Architecture | Painting | Inspection of painting (top coat) for Internal Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-07-09 | 2025-07-10 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted