## 00. SUMMARY
Summary of RFI for ELECO
[12 empty] | Date : | 2026-01-14
01. Total Summary for RFI
| SubCon | Unit | Discipline | Code | Type | Accumulative RFI Status
[6 empty] | Issued | Accepted | Ongoing | Rejected | Cancelled | Remark
| ELECO | C300 | Trial Mix | TRM | RFI | 0 | 0 | 0 | 0 | 0 | * Cancelled due not ready to inspection.
|  |  | Material Receiving | MRI | RFI | 2 | 0 | 2 | 0 | 0
|  |  | General Test | GLT | RFI | 0 | 0 | 0 | 0 | 0
|  |  | Survey Work | SVW | RFI | 0 | 0 | 0 | 0 | 0
|  |  | Brickwork | BRI | RFI | 6 | 5 | 1 | 0 | 0
|  |  | Plaster | PLA | RFI | 4 | 2 | 2 | 0 | 0
|  |  | Ceiling | CEI | RFI | 0 | 0 | 0 | 0 | 0
|  |  | Tile | TIL | RFI | 0 | 0 | 0 | 0 | 0
|  |  | Water Proofing | WTP | RFI | 0 | 0 | 0 | 0 | 0
|  |  | Roofing | RFG | RFI | 0 | 0 | 0 | 0 | 0
|  |  | Window and Door | WDD | RFI | 2 | 1 | 1 | 0 | 0
|  |  | Fitting | FIT | RFI | 0 | 0 | 0 | 0 | 0
|  |  | Floor | FLR | RFI | 0 | 0 | 0 | 0 | 0
|  |  | Painting | PAI | RFI | 3 | 2 | 1 | 0 | 0
|  |  | Final Inspection | FNL | RFI | 3 | 2 | 1 | 0 | 0
| Total |  |  |  |  | 14 | 8 | 6 | 0 | 0 |  |  |  | Beginning Date | 2024-01-01
[14 empty] | ending date | 2025-12-31
02. Pending Items
| Item |  | ELECO
CIVIL WORK
RFI
| Ongoing |  | 6
| Pending Sign |  | 0
| Pending Attachment |  | 0
| Reschedule |  | 0
| On schedule |  | 0
| Total: |  | 6

## 01.RFI_TRM
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-14
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY

## 02.RFI_MRI
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-14
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-ARC-F-D300-MRI-0001 | External | Eleco | Civil Work | N/A | Architecture | Material Receiving | Material Receiving inspection for aluminium window frame at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-07-29 | 2025-07-30 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Ongoing
| 2 | Civil | RFI-ELE-ARC-F-D300-MRI-0002 | External | Eleco | Civil Work | N/A | Architecture | Material Receiving | Material Receiving inspection for procelain tiles from MML | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-12-19 | 2025-12-20 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Ongoing
-
-
-
-
-
-
-
-
-
-
-

## 03.RFI_GLT
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-14
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY

## 04.RFI_SVW
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-14
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY

## 05.RFI_BRI
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-14
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-ARC-F-D300-BRI-0001 | External | Eleco | Civil Work | N/A | Architecture | Brickwork | Inspection of bricklaying at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-05-05 | 2025-05-06 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 2 | Civil | RFI-ELE-ARC-F-D300-BRI-0002 | External | Eleco | Civil Work | N/A | Architecture | Brickwork | Inspection of bricklaying at Workshop and Maintenance Building | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-05-10 | 2025-05-12 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 3 | Civil | RFI-ELE-ARC-F-D300-BRI-0003 | External | Eleco | Civil Work | N/A | Architecture | Brickwork | Inspection of bricklaying at Workshop and Maintenance Building | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-05-19 | 2025-05-20 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 4 | Civil | RFI-ELE-ARC-F-D300-BRI-0004 | External | Eleco | Civil Work | N/A | Architecture | Brickwork | Inspection of bricklaying, lintel and Stiffener at Workshop and Maintenance Building | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-05-29 | 2025-05-30 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 5 | Civil | RFI-ELE-ARC-F-D300-BRI-0005 | External | Eleco | Civil Work | N/A | Architecture | Brickwork | Inspection of bricklaying, lintel and Stiffener at Workshop and Maintenance Building | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-06-04 | 2025-06-05 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Ongoing
| 6 | Civil | RFI-ELE-ARC-F-D300-BRI-0006 | External | Eleco | Civil Work | N/A | Architecture | Brickwork | Inspection of bricklaying, lintel and Stiffener at Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-08-21 | 2025-08-22 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
-

## 06.RFI_PLA
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-14
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-ARC-F-D300-PLA-0001 | External | Eleco | Civil Work | N/A | Architecture | Brickwork | Inspection of Plastering at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-05-09 | 2025-05-10 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 2 | Civil | RFI-ELE-ARC-F-D300-PLA-0002 | External | Eleco | Civil Work | N/A | Architecture | Brickwork | Inspection of Plastering at Meeting Room WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-07-29 | 2025-07-30 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Ongoing
| 3 | Civil | RFI-ELE-ARC-F-D300-PLA-0003 | External | Eleco | Civil Work | N/A | Architecture | Brickwork | Inspection of Plastering at Workshop and Maintenance Building | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-09-04 | 2025-09-05 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Ongoing
| 4 | Civil | RFI-ELE-ARC-F-D300-PLA-0004 | External | Eleco | Civil Work | N/A | Architecture | Brickwork | Inspection of Plastering at Chemical and Catalyst Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-11-10 | 2025-11-11 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 5 | Civil | RFI-ELE-ARC-F-D300-PLA-0005 | External | Eleco | Civil Work | N/A | Architecture | Brickwork | Inspection of Plastering at 1st Floor Workshop and Maintenance Building | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2026-01-06 | 2026-01-07 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Ongoing
-
-
-
-
-
-

## 07.RFI_CEI
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-14
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY

## 08.RFI_TIL
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-14
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY

## 09.RFI_WTP
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-14
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY

## 10.RFI_RFG
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-14
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY

## 11.RFI_WDD
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-14
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-ARC-F-D300-WDD-0001 | External | Eleco | Civil Work | N/A | Architecture | Installation | Inspection of Window Frame Installation for Ground Floor WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-07-29 | 2025-07-30 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Ongoing
| 2 | Civil | RFI-ELE-ARC-F-D300-WDD-0002 | External | Eleco | Civil Work | N/A | Architecture | Installation | Inspection of Louvers Installation at Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-12-16 | 2025-12-17 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 3 | Civil | RFI-ELE-ARC-F-D300-WDD-0003 | External | Eleco | Civil Work | N/A | Architecture | Installation | Inspection of roller shutter Installation at Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2026-01-06 | 2026-01-07 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted

## 12.RFI_FIT
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-14
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY

## 13.RFI_FLR
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-14
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-ARC-F-D300-FLR-0001 | External | Eleco | Civil Work | N/A | Architecture | Flooring | Inspection of Anti Dust Epoxy Coating for Switchroom Floor at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2026-01-06 | 2026-01-07 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Ongoing
| 2 | Civil | RFI-ELE-ARC-F-D300-FLR-0002 | External | Eleco | Civil Work | N/A | Architecture | Flooring | Inspection of Anti Dust Epoxy Coating for Calibration Room at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2026-01-14 | 2026-01-15 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Ongoing
| 3 | Civil | RFI-ELE-ARC-F-D300-FLR-0003 | External | Eleco | Civil Work | N/A | Architecture | Flooring | Inspection of Anti - Slip Chemical Resistance Coating for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2026-01-14 | 2026-01-15 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Ongoing
| 4 | Civil | RFI-ELE-ARC-F-D300-FLR-0004 | External | Eleco | Civil Work | N/A | Architecture | Flooring | Inspection of Anti - Slip Chemical Resistance Coating for Scheduled Waste Storage Building | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2026-01-14 | 2026-01-15 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Ongoing

## 14.RFI_PAI
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-14
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-ARC-F-D300-PAI-0001 | External | Eleco | Civil Work | N/A | Architecture | Painting | Inspection of Painting for Workshop and Maintenance Building (External) | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-12-16 | 2025-12-17 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Ongoing
| 2 | Civil | RFI-ELE-ARC-F-D300-PAI-0002 | External | Eleco | Civil Work | N/A | Architecture | Painting | Inspection of Painting for Chemical and Catalyst Storage Shelter (External) | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-12-16 | 2025-12-17 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 3 | Civil | RFI-ELE-ARC-F-D300-PAI-0003 | External | Eleco | Civil Work | N/A | Architecture | Painting | Inspection of Painting for Schedule Waste Storage (External) | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-12-16 | 2025-12-17 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 4 | Civil | RFI-ELE-ARC-F-D300-PAI-0004 | External | Eleco | Civil Work | N/A | Architecture | Painting | Inspection of Painting for Workshop and Maintenance Building (Internal) | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2026-01-06 | 2026-01-07 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Ongoing
| 5 | Civil | RFI-ELE-ARC-F-D300-PAI-0005 | External | Eleco | Civil Work | N/A | Architecture | Painting | Inspection of Chemical Resistance Coating for Chemical and Catalyst Storage Shelter (Internal Wall) | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2026-01-14 | 2026-01-15 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Ongoing
| 6 | Civil | RFI-ELE-ARC-F-D300-PAI-0006 | External | Eleco | Civil Work | N/A | Architecture | Painting | Inspection of Chemical Resistance Coating for Scheduled Waste Storage Building (Internal Wall) | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2026-01-14 | 2026-01-15 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Ongoing

## 15.RFI_FNL
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-14
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-ARC-F-D300-FNL-0001 | External | Eleco | Civil Work | N/A | Architecture | Final Inspection | Final Inspection for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-12-22 | 2025-12-23 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Ongoing
| 2 | Civil | RFI-ELE-ARC-F-D300-FNL-0002 | External | Eleco | Civil Work | N/A | Architecture | Final Inspection | Final Inspection for Scheduled Waste Storage Building | BASIL-01-EXE-HQC-000-QAC-ITP-0022 | B | 2025-12-22 | 2025-12-23 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Ongoing