## 00. SUMMARY
Summary of RFI for ELECO
[12 empty] | Date : | 2026-01-27
01. Total Summary for RFI
| SubCon | Unit | Discipline | Code | Type | Accumulative RFI Status
[6 empty] | Issued | Accepted | Ongoing | Rejected | Cancelled | Remark
| ELECO | D300 | Trial Mix | TRM | RFI | 15 | 14 | 1 | 0 | 0 | * Cancelled due not ready to inspection.
|  |  | Material Receiving | MRI | RFI | 51 | 49 | 2 | 0 | 0
|  |  | General Test | GLT | RFI | 29 | 29 | 0 | 0 | 0
|  |  | Survey Work | SVW | RFI | 13 | 13 | 0 | 0 | 0
|  |  | Excavation | EXC | RFI | 14 | 13 | 0 | 0 | 1
|  |  | Pre-Concrete | PRC | RFI | 194 | 175 | 15 | 0 | 4
|  |  | Concrete | CON | RFI | 194 | 176 | 15 | 0 | 3
|  |  | Post-Concrete | PSC | RFI | 194 | 176 | 15 | 0 | 3
|  |  | As-Built | ASB | RFI | 167 | 152 | 11 | 0 | 4
|  |  | Cube Test | CUB | RFI | 480 | 480 | 0 | 0 | 0
|  |  | Backfilling | BFL | RFI | 24 | 24 | 0 | 0 | 0
|  |  | Field Density Test | FDT | RFI | 20 | 17 | 0 | 0 | 3
| Total |  |  |  |  | 1395 | 1318 | 59 | 0 | 18 |  |  |  | Beginning Date | 2024-01-01
[14 empty] | ending date | 2025-12-31
02. Pending Items
| Item |  | ELECO
CIVIL WORK
RFI
| Ongoing |  | 59
| Pending Sign |  | 0
| Pending Attachment |  | 0
| Reschedule |  | 0
| On schedule |  | 0
| Total: |  | 59

## 01.RFI_TRM
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-27
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-CVL-W-G-TRM-0001 | External | ELECO | Civil Work | N/A | Trial Mix | Trial Mix | Concrete trial mix for normal mix design for concrete grade 20MPa, 30MPa, and 37MPa | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | A | 2024-04-20 | 2024-04-22 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted | -
| 2 | Civil | RFI-ELE-CVL-W-G-TRM-0002 | External | ELECO | Civil Work | N/A | Cube Test | Cube Test | Cube test 7days for Concrete Trial Mix Grade 30MPa | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | A | 2024-04-27 | 2024-04-29 | 14:00 | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted | -
| 3 | Civil | RFI-ELE-CVL-W-G-TRM-0003 | External | ELECO | Civil Work | N/A | Cube Test | Cube Test | Cube test 7days for Concrete Trial Mix Grade 37MPa | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | A | 2024-04-27 | 2024-04-29 | 14:00 | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted | -
| 4 | Civil | RFI-ELE-CVL-W-G-TRM-0004 | External | ELECO | Civil Work | N/A | Cube Test | Cube Test | Cube test 28days for Concrete Trial Mix Grade 30MPa | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-05-17 | 2024-05-20 | 14:00 | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted | -
| 5 | Civil | RFI-ELE-CVL-W-G-TRM-0005 | External | ELECO | Civil Work | N/A | Cube Test | Cube Test | Cube test 28days for Concrete Trial Mix Grade 37MPa | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-05-17 | 2024-05-20 | 14:00 | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted | -
| 6 | Civil | RFI-ELE-CVL-W-G-TRM-0006 | External | ELECO | Civil Work | N/A | Trial Mix | Trial Mix | Concrete trial mix for pump mix design for concrete grade 37MPa | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-07 | 2024-09-09 | 9:00 | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted | -
| 7 | Civil | RFI-ELE-CVL-W-G-TRM-0007 | External | ELECO | Civil Work | N/A | Trial Mix | Trial Mix | Concrete trial mix for pump mix design for concrete grade 30MPa | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-11 | 2024-09-12 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted | -
| 8 | Civil | RFI-ELE-CVL-W-G-TRM-0008 | External | ELECO | Civil Work | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G37 pump mix for Trial Mix at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-14 | 2024-09-18 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted | -
| 9 | Civil | RFI-ELE-CVL-W-G-TRM-0009 | External | ELECO | Civil Work | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G30 pump mix for Trial Mix at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-17 | 2024-09-19 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted | -
| 10 | Civil | RFI-ELE-CVL-W-G-TRM-0010 | External | ELECO | Civil Work | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G37 pump mix for Trial Mix at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-05 | 2024-10-07 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 11 | Civil | RFI-ELE-CVL-W-G-TRM-0011 | External | ELECO | Civil Work | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G30 pump mix for Trial Mix at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-09 | 2024-10-10 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 12 | Civil | RFI-ELE-CVL-W-G-TRM-0012 | External | ELECO | Civil Work | N/A | Trial Mix | Trial Mix | Concrete trial mix for pump mix design for concrete grade 30MPa, 37 Mpa, Normal Mix and Pump Mix at LCS MARKETING SDN BHD (DAMANSARA PLANT) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-22 | 1900-01-23 02:24 | 9.00 AM | I/R | W | N/A | W | Hanis | LCS Plant (Damansara) | Accepted | -
| 13 | Civil | RFI-ELE-CVL-W-G-TRM-0013 | External | ELECO | Civil Work | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G30N,G37N,G30P,G37P for Trial Mix at LCS Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-31 | 2024-11-01 | 9.00 AM | I/R | W | N/A | W | Hanis | LCS Plant (Damansara) | Accepted | -
| 14 | Civil | RFI-ELE-CVL-W-G-TRM-0014 | External | ELECO | Civil Work | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G30N,G37N,G30P,G37P for Trial Mix at LCS Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-19 | 2024-11-21 | 9.00 AM | I/R | W | N/A | W | Hanis | LCS Plant (Damansara) | Accepted | -
| 15 | Civil | RFI-ELE-CVL-W-G-TRM-0015 | External | ELECO | Civil Work | N/A | Cube Test | Cube Test | Concrete trial mix for pump mix design for concrete grade G35A for normal and pump mix at LCS Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-06 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS Plant (Damansara) | Ongoing | -

## 02.RFI_MRI
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-27
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-CVL-W-G-MRI-0001 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Inspection of material receiving for rebar at Yick Hoe Steel Industries Sdn. Bhd. | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-05-31 | 2024-06-04 | 10.00 AM | H | W | N/A | W | Hanis | Ulu Tiram | Accepted | -
| 2 | Civil | RFI-ELE-CVL-F-D300-MRI-0002 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Inspection of material receiving for pile plug at D300. | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-06-10 | 2024-06-11 | 10.00 AM | H | W | N/A | W | Hanis | D300 | Accepted | -
| 3 | Civil | RFI-ELE-CVL-F-D300-MRI-0003 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Inspection for material receiving for rebar at D300. | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-24 | 2024-08-26 | 10.00 AM | H | W | N/A | W | Hanis | D300 | Accepted
| 4 | Civil | RFI-ELE-CVL-F-G-MRI-0004 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Inspection for material receiving for embedded plate for earthing. | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-30 | 2024-09-02 | 10.0 AM | H | W | N/A | W | Hanis | Site Office CN Eleco | Accepted | -
| 5 | Civil | RFI-ELE-CVL-F-G-MRI-0005 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Inspection for material receiving for broken pile rectification work | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-26 | 2024-09-26 | 10.00 AM | H | W | N/A | W | Hanis | Site Office CN Eleco | Accepted | -
| 6 | Civil | RFI-ELE-CVL-F-D300-MRI-0006 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Inspection for material receiving for hardcore material | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-28 | 2024-09-30 | 10.00 AM | H | W | N/A | W | Hanis | D300 | Accepted | -
| 7 | Civil | RFI-ELE-CVL-F-D300-MRI-0007 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Inspection for material receiving for rebar at D300. | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-02 | 2024-10-03 | 10.00 AM | H | W | N/A | W | Hanis | D300 | Accepted | -
| 8 | Civil | RFI-ELE-CVL-F-D300-MRI-0008 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Inspection for material receiving for hardcore material | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-08 | 2024-10-08 | 10.00 AM | H | W | N/A | W | Hanis | D300 | Accepted | -
| 9 | Civil | RFI-ELE-CVL-F-D300-MRI-0009 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Inspection for material receiving for rebar at D300. | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-18 | 2024-10-18 | 10.00 AM | H | W | N/A | W | Hanis | D300 | Accepted | -
| 10 | Civil | RFI-ELE-CVL-W-G-MRI-0010 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Inspection for material receiving for SS316L Drain Pipe w/o sleeves for T-16234 at ELECO Yard | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-29 | 2024-10-30 | 10.00 AM | H | W | N/A | W | Hanis | D300 | Accepted | -
| 11 | Civil | RFI-ELE-CVL-W-G-MRI-0011 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Inspection for material receiving for hardcore material | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-01 | 2024-11-01 | 11.30 AM | H | W | N/A | W | Hanis | D300 | Accepted | -
| 12 | Civil | RFI-ELE-CVL-F-D300-MRI-0012 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Inspection for material receiving for SS316L Pipe c/w 3LPE for TK-16234 at D300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-05 | 2024-11-05 | 11.00 AM | H | W | N/A | W | Hanis | D300 | Accepted | -
| 13 | Civil | RFI-ELE-CVL-F-D300-MRI-0013 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Inspection for material receiving for rebar for Man Refiner at D300. | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-13 | 2024-11-14 | 11.00 AM | H | W | N/A | W | Hanis | D300 | Accepted | -
| 14 | Civil | RFI-ELE-CVL-F-G-MRI-0014 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Inspection for material receiving for anti termite material | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-15 | 2024-11-16 | 11.00 AM | H | W | N/A | W | Hanis | Site Office CN Eleco | Accepted | -
| 15 | Civil | RFI-ELE-CVL-F-G-MRI-0015 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Inspection for material receiving for rebar at D300. | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-18 | 2024-11-18 | 11.00 AM | H | W | N/A | W | Hanis | D300 | Accepted
| 16 | Civil | RFI-ELE-CVL-F-G-MRI-0016 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Inspection for material receiving for anchor bolt D300 Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-21 | 2024-11-22 | 09.00 AM | H | W | N/A | W | Hanis | D300 | Accepted
| 17 | Civil | RFI-ELE-CVL-F-G-MRI-0017 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Inspection for material receiving for rebar at D300. | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-23 | 2024-11-23 | 11.00 AM | H | W | N/A | W | Hanis | D300 | Accepted
| 18 | Civil | RFI-ELE-CVL-F-G-MRI-0018 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Inspection for material receiving for rebar at D300. | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-26 | 2024-11-26 | 11.00 AM | H | W | N/A | W | Hanis | D300 | Accepted
| 19 | Civil | RFI-ELE-CVL-F-G-MRI-0019 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Inspection for material receiving for anchor bolt MAN Refiner PC16 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-27 | 2024-11-27 | 3.30 PM | H | W | N/A | W | Hanis | D300 | Accepted
| 20 | Civil | RFI-ELE-CVL-F-G-MRI-0020 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Inspection for material receiving for anchor bolt | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-04 | 2024-12-04 | 3.30 PM | H | W | N/A | W | Hanis | D300 | Accepted
| 21 | Civil | RFI-ELE-CVL-F-G-MRI-0021 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Inspection for material receiving for HDPE Geomembrane Lining | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-06 | 2024-12-06 | 3.30 PM | H | W | N/A | W | Hanis | D300 | Accepted
| 22 | Civil | RFI-ELE-CVL-F-G-MRI-0022 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Inspection for material receiving for ABS, UPVC Pipe, Corrugated Pipes and accessories | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-17 | 2024-12-17 | 5.30 PM | H | W | N/A | W | Hanis | D300 | Accepted
| 23 | Civil | RFI-ELE-CVL-F-G-MRI-0023 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Inspection for material receiving for Anchor Bolt with varies size for D300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-17 | 2024-12-17 | 5.30 PM | H | W | N/A | W | Hanis | D300 | Accepted
| 24 | Civil | RFI-ELE-CVL-F-G-MRI-0024 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for Polyethylene fillerboard for Foundation Joint. | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-20 | 2024-12-21 | 9:00 | H | W | N/A | W | Hanis | D300 | Accepted
| 25 | Civil | RFI-ELE-CVL-F-G-MRI-0025 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for BRC A10 200mm x 200mm | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-24 | 2024-12-25 | 9:00 | H | W | N/A | W | Hanis | D300 | Accepted
| 26 | Civil | RFI-ELE-CVL-F-G-MRI-0026 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for PVC waterstop 200 mm width | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-28 | 2024-12-30 | 9:00 | H | W | N/A | W | Hanis | D300 | Accepted
| 27 | Civil | RFI-ELE-CVL-F-G-MRI-0027 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for Polyethylene Sheet (Damp proof membrane) 1000 gauge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-28 | 2024-12-30 | 9:00 | H | W | N/A | W | Hanis | D300 | Accepted
| 28 | Civil | RFI-ELE-CVL-F-G-MRI-0028 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for Anchor bolt various size | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-30 | 2024-12-31 | 9:00 | H | W | N/A | W | Hanis | D300 | Accepted
| 29 | Civil | RFI-ELE-CVL-F-G-MRI-0029 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for Stainless Steel SS316L with 3LPE HDPE for TK -18203 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-06 | 2025-01-06 | 9:00 | H | W | N/A | W | Hanis | D300 | Accepted
| 30 | Civil | RFI-ELE-CVL-F-G-MRI-0030 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for Angle guard/bar with fishtail for Substation Cable floor opening | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-13 | 2025-01-13 | 16:00 | H | W | N/A | W | Hanis | D300 | Accepted
| 31 | Civil | RFI-ELE-CVL-F-G-MRI-0031 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for RWDP socket 60" for Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-20 | 2025-02-21 | 16:00 | H | W | N/A | W | Hanis | D300 | Ongoing
| 32 | Civil | RFI-ELE-CVL-F-G-MRI-0032 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for anhor bolts varies size for D300 and C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-21 | 2025-02-22 | 16:00 | H | W | N/A | W | Hanis | D300 | Ongoing
| 33 | Civil | RFI-ELE-CVL-F-G-MRI-0033 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for Autoclaved Aerated Concrete (AAC) from Henner with accessories for Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-05 | 2025-03-06 | 16:00 | H | W | N/A | W | Hanis | D300 | Accepted
| 34 | Civil | RFI-ELE-CVL-F-G-MRI-0034 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for SikaTop Seal 107 waterproofing slurry for roof slab repair | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-19 | 2025-03-19 | 16:00 | H | W | N/A | W | Hanis | D300 | Accepted
| 35 | Civil | RFI-ELE-CVL-F-G-MRI-0035 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for Hilti RE 500 V4 Chemical Anchor | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-19 | 2025-03-20 | 16:00 | H | W | N/A | W | Hanis | D300 | Accepted
| 36 | Civil | RFI-ELE-CVL-F-G-MRI-0036 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for 40 mm gravel for cable cellar at Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-10 | 2025-04-10 | 16:00 | H | W | N/A | W | Hanis | D300 | Accepted
| 37 | Civil | RFI-ELE-CVL-F-G-MRI-0037 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for fire rated door frame at Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-16 | 2025-04-17 | 16:00 | H | W | N/A | W | Hanis | D300 | Accepted
| 38 | Civil | RFI-ELE-CVL-F-G-MRI-0038 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for carborundum/ silicon carbide powder at Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-18 | 2025-04-19 | 16:00 | H | W | N/A | W | Hanis | D300 | Accepted
| 39 | Civil | RFI-ELE-CVL-F-G-MRI-0039 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for ladder rung for Manhole | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-28 | 2025-04-29 | 16:00 | H | W | N/A | W | Hanis | D300 | Accepted
| 40 | Civil | RFI-ELE-CVL-F-G-MRI-0040 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for waterproofing material (Pentens T-007, Pentens T-100, and fibreglass mesh) for Roof Slab Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-28 | 2025-04-29 | 16:00 | H | W | N/A | W | Hanis | D300 | Accepted
| 41 | Civil | RFI-ELE-CVL-F-G-MRI-0041 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for insert plate type IP-1 and IP-2 for WMB Roof Truss | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-02 | 2025-05-03 | 16:00 | H | W | N/A | W | Hanis | D300 | Accepted
| 42 | Civil | RFI-ELE-CVL-F-G-MRI-0042 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for Jotun Paint for Substation C2015 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-03 | 2025-05-05 | 16:00 | H | W | N/A | W | Hanis | D300 | Accepted
| 43 | Civil | RFI-ELE-CVL-F-G-MRI-0043 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for Anti Dust Epoxy Resin Nitoflor Lithurin (M) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-05 | 2025-05-06 | 16:00 | H | W | N/A | W | Hanis | D300 | Accepted
| 44 | Civil | RFI-ELE-CVL-F-G-MRI-0044 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for Raised floor Powerfloor for IER Room Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-05 | 2025-05-06 | 16:00 | H | W | N/A | W | Hanis | D300 | Accepted
| 45 | Civil | RFI-ELE-CVL-F-G-MRI-0045 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for AAC Blocks and adhesives from Alam Con | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-10 | 2025-05-12 | 16:00 | H | W | N/A | W | Hanis | D300 | Accepted
| 46 | Civil | RFI-ELE-CVL-F-G-MRI-0046 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for Sunfoil SB250FR (Aluminium bubble foil) for Roofing Insulation Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-13 | 2025-05-14 | 16:00 | H | W | N/A | W | Hanis | D300 | Accepted
| 47 | Civil | RFI-ELE-CVL-F-G-MRI-0047 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for fire rated door for Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-13 | 2025-05-14 | 16:00 | H | W | N/A | W | Hanis | D300 | Accepted
| 48 | Civil | RFI-ELE-CVL-F-G-MRI-0048 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for fire rated door frame for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-04 | 2025-06-05 | 16:00 | H | W | N/A | W | Hanis | D300 | Accepted
| 49 | Civil | RFI-ELE-CVL-F-G-MRI-0049 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for anti climb fence from ECMAX Industry | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-18 | 2025-06-19 | 16:00 | H | W | N/A | W | Hanis | D300 | Accepted
| 49 | Civil | RFI-ELE-CVL-F-G-MRI-0050 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for precast U drain from OKA Concrete Industries | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-20 | 2025-11-21 | 16:00 | H | W | N/A | W | Hanis | D300 | Accepted
| 49 | Civil | RFI-ELE-CVL-F-G-MRI-0051 | External | ELECO | Civil Work | N/A | Material Receiving | Material Receiving | Material Receiving for precast box culvert from OKA Concrete Industries | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-13 | 2025-12-15 | 16:00 | H | W | N/A | W | Hanis | D300 | Accepted

## 03.RFI_GLT
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-27
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-CVL-W-G-GLT-0001 | External | ELECO | Civil Work | N/A | Testing | Rebar Testing | Inspection for rebar testing at CASTconsult Sdn. Bhd. | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-05-31 | 2024-06-05 | 10.00 AM | I | W | N/A | W | Hanis | Senai | Accepted | -
| 2 | Civil | RFI-ELE-CVL-W-G-GLT-0002 | External | ELECO | Civil Work | N/A | Testing | Soil Sampling | Inspection for backfilling material prior to Proctor Test at CAST Consult Sdn. Bhd. | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2024-08-06 | 2024-08-07 | 10.00 AM | I | W | N/A | W | Hanis | CAST Consult | Accepted | -
| 3 | Civil | RFI-ELE-CVL-W-G-GLT-0003 | External | ELECO | Civil Work | N/A | Testing | Crusher run | Inspection for backfilling material prior to Proctor Test at CAST Consult Sdn. Bhd. | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2024-09-30 | 2024-10-01 | 10.00 AM | I | W | N/A | W | Hanis | CAST Consult | Accepted | -
| 4 | Civil | RFI-ELE-CVL-F-D300-GLT-0004 | External | ELECO | Civil Work | N/A | Installation | Geomembrane | Inspection for 2mm HDPE Geomembrane Lining Installation for TK-16234 | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2024-12-06 | 2024-12-06 | 4.00 PM | I | W | N/A | W | Hanis | D300 | Accepted | -
| 5 | Civil | RFI-ELE-CVL-F-D300-GLT-0005 | External | ELECO | Civil Work | N/A | Installation | Sand Bitumen | Inspection for Sand Bitumen installation work at Tank TK-16234 | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2024-12-11 | 2024-12-12 | 10.00 AM | I | W | N/A | W | Hanis | D300 | Accepted | -
| 6 | Civil | RFI-ELE-CVL-F-D300-GLT-0006 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection for handing over Tank TK-16234 to mechanical | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2024-12-17 | 2024-12-17 | 9.00 AM | I | W | N/A | W | Hanis | D300 | Accepted | -
| 7 | Civil | RFI-ELE-CVL-F-D300-GLT-0007 | External | ELECO | Civil Work | N/A | Installation | Anti Termite | Inspection for anti termite application for WMB | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2024-12-19 | 2024-12-19 | 7.00 PM | I | W | N/A | W | Hanis | D300 | Accepted | -
| 8 | Civil | RFI-ELE-CVL-F-D300-GLT-0008 | External | ELECO | Civil Work | N/A | Installation | Anti Termite | Inspection for anti termite application for WMB | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2024-12-27 | 2024-12-28 | 9:00 | I | W | N/A | W | Hanis | D300 | Accepted | -
| 9 | Civil | RFI-ELE-CVL-F-D300-GLT-0009 | External | ELECO | Civil Work | N/A | Installation | Plumbing | Inspection of embedded Cold Water Pipe Fitting for Ground Floor WMB prior to slab casting | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2025-01-03 | 2025-01-04 | 9:00 | I | W | N/A | W | Hanis | D300 | Accepted | -
| 10 | Civil | RFI-ELE-CVL-F-D300-GLT-0010 | External | ELECO | Civil Work | N/A | Installation | Anti Termite | Inspection for anti termite application for WMB GL B-D/1-4 | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2025-01-09 | 2025-01-10 | 9.00 AM | I | W | N/A | W | Hanis | D300 | Accepted | -
| 11 | Civil | RFI-ELE-CVL-F-D300-GLT-0011 | External | ELECO | Civil Work | N/A | Installation | General Test | Inspection for handing over P-16235A, P-16235B and P-16236 Pump Foundation at Pump Shelter | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2025-02-27 | 2025-02-28 | 9.00 AM | I | W | N/A | W | Hanis | D300 | Accepted | -
| 12 | Civil | RFI-ELE-CVL-F-D300-GLT-0012 | External | ELECO | Civil Work | N/A | Installation | General Test | Inspection for handing over E-16235 Heat Exchanger at Pump Shelter | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2025-02-27 | 2025-02-28 | 9.00 AM | I | W | N/A | W | Hanis | D300 | Accepted | -
| 13 | Civil | RFI-ELE-CVL-F-D300-GLT-0013 | External | ELECO | Civil Work | N/A | Installation | General Test | Inspection of anchor bolt grouting for TK 16234 | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2025-09-03 | 2025-09-04 | 9.00 AM | I | W | N/A | W | Hanis | D300 | Accepted | -
| 14 | Civil | RFI-ELE-CVL-F-D300-GLT-0014 | External | ELECO | Civil Work | N/A | Installation | General Test | Inspection for handing over pump foundation (3 nos) and 1 nos of Heat Exchanger Foundation at Pump Shelter | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2025-11-05 | 2025-11-06 | 9.00 AM | I | W | N/A | W | Hanis | D300 | Accepted | -
| 14 | Civil | RFI-ELE-CVL-F-D300-GLT-0014 | External | ELECO | Civil Work | N/A | Installation | General Test | Inspection for handing over pump foundation (3 nos) and 1 nos of Heat Exchanger Foundation at Pump Shelter | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2025-11-05 | 2025-11-06 | 9.00 AM | I | W | N/A | W | Hanis | D300 | Accepted | -
| 15 | Civil | RFI-ELE-CVL-F-D300-GLT-0015 | External | ELECO | Civil Work | N/A | Installation | General Test | Inspection for installation MA9 Manholes for D300 | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2025-12-03 | 2025-12-04 | 9.00 AM | I | W | N/A | W | Hanis | D300 | Accepted | -
| 16 | Civil | RFI-ELE-CVL-F-D300-GLT-0016 | External | ELECO | Civil Work | N/A | Installation | General Test | Inspection for installation MA10 Manholes for D300 | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2025-12-04 | 2025-12-05 | 9.00 AM | I | W | N/A | W | Hanis | D300 | Accepted | -
| 17 | Civil | RFI-ELE-CVL-F-D300-GLT-0017 | External | ELECO | Civil Work | N/A | Installation | General Test | Inspection for installation MA1 and MA1B Manholes for D300 | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2025-12-08 | 2025-12-09 | 9.00 AM | I | W | N/A | W | Hanis | D300 | Accepted | -
| 18 | Civil | RFI-ELE-CVL-F-D300-GLT-0018 | External | ELECO | Civil Work | N/A | Installation | General Test | Inspection for installation MA2 and MA3 Manholes for D300 | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2025-12-10 | 2025-12-11 | 9.00 AM | I | W | N/A | W | Hanis | D300 | Accepted | -
| 19 | Civil | RFI-ELE-CVL-F-D300-GLT-0019 | External | ELECO | Civil Work | N/A | Installation | General Test | Inspection for installation MA4 MS10 MS5A MS5 and MS6 Manholes for D300 | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2025-12-12 | 2025-12-13 | 9.00 AM | I | W | N/A | W | Hanis | D300 | Accepted | -
| 20 | Civil | RFI-ELE-CVL-F-D300-GLT-0020 | External | ELECO | Civil Work | N/A | Installation | General Test | Inspection for installation of Precast Box Culvert PC4 for D300 | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2025-12-13 | 2025-12-15 | 9.00 AM | I | W | N/A | W | Hanis | D300 | Accepted | -
| 21 | Civil | RFI-ELE-CVL-F-D300-GLT-0021 | External | ELECO | Civil Work | N/A | Installation | General Test | Inspection for installation of MA5, MA6 and MA7 Manholes for D300 | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2025-12-23 | 2025-12-24 | 9.00 AM | I | W | N/A | W | Hanis | D300 | Accepted | -
| 22 | Civil | RFI-ELE-CVL-F-D300-GLT-0022 | External | ELECO | Civil Work | N/A | Installation | General Test | Inspection for grouting MA9-MA8 MA8-MA7 MA1-MA1B MA1-MA1A MA1B-CB2 GRE Pipe Opening | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2025-12-23 | 2025-12-24 | 9.00 AM | I | W | N/A | W | Hanis | D300 | Accepted | -
| 23 | Civil | RFI-ELE-CVL-F-D300-GLT-0023 | External | ELECO | Civil Work | N/A | Installation | General Test | Inspection for installation of Precast Box Culvert PC2 for D300 | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2025-12-27 | 2025-12-28 | 9.00 AM | I | W | N/A | W | Hanis | D300 | Accepted | -
| 24 | Civil | RFI-ELE-CVL-F-D300-GLT-0024 | External | ELECO | Civil Work | N/A | Installation | General Test | Inspection for installation of MS4, MS4A, MS9A and MS9 Manholes for D300 | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2025-12-27 | 2025-12-28 | 9.00 AM | I | W | N/A | W | Hanis | D300 | Accepted | -
| 25 | Civil | RFI-ELE-CVL-F-D300-GLT-0025 | External | ELECO | Civil Work | N/A | Installation | General Test | Inspection for installation of Precast Box Culvert PC3 for D300 | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2025-12-27 | 2025-12-29 | 9.00 AM | I | W | N/A | W | Hanis | D300 | Accepted | -
| 26 | Civil | RFI-ELE-CVL-F-D300-GLT-0026 | External | ELECO | Civil Work | N/A | Installation | General Test | Inspection for grouting MA7-MA6 MA6-MA5 MA6-MA10 GRE Pipe Opening | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2025-12-27 | 2025-12-29 | 9.00 AM | I | W | N/A | W | Hanis | D300 | Accepted | -
| 27 | Civil | RFI-ELE-CVL-F-D300-GLT-0027 | External | ELECO | Civil Work | N/A | Installation | General Test | Inspection for installation of Manholes MS8 for D300 | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2025-12-30 | 2025-12-31 | 9.00 AM | I | W | N/A | W | Hanis | D300 | Accepted | -
| 28 | Civil | RFI-ELE-CVL-F-D300-GLT-0028 | External | ELECO | Civil Work | N/A | Installation | General Test | Inspection for installation of Precast Box Culvert PC5 for D300 | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2025-12-30 | 2025-12-31 | 9.00 AM | I | W | N/A | W | Hanis | D300 | Accepted | -
| 29 | Civil | RFI-ELE-CVL-F-D300-GLT-0029 | External | ELECO | Civil Work | N/A | Installation | General Test | Inspection for grouting Grout GRE pipe MA9-ACW MA2-MA3 line, MA2-schedule waste shelter line, and MA9- pump shelter CB6a line GRE Pipe Opening | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2026-01-03 | 2026-01-05 | 9.00 AM | I | W | N/A | W | Hanis | D300 | Accepted
| 30 | Civil | RFI-ELE-CVL-F-D300-GLT-0030 | External | ELECO | Civil Work | N/A | Installation | General Test | Inspection for grouting MA2-CB4 MA2-CB3 CB9 GRE Pipe Opening | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2026-01-09 | 2026-01-10 | 9.00 AM | I | W | N/A | W | Hanis | D300 | Accepted
| 31 | Civil | RFI-ELE-CVL-F-D300-GLT-0031 | External | ELECO | Civil Work | N/A | Installation | General Test | Inspection for grouting MA5 - MA4, MA6 - CB6, MA10 - CB5 GRE Pipe Opening | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2026-01-12 | 2026-01-13 | 9.00 AM | I | W | N/A | W | Hanis | D300 | Accepted
| 32 | Civil | RFI-ELE-CVL-F-D300-GLT-0032 | External | ELECO | Civil Work | N/A | Installation | General Test | Inspection for installation of Precast Box Culvert PC1 for D300 | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2026-01-23 | 2026-01-24 | 9.00 AM | I | W | N/A | W | Hanis | D300 | Accepted
| 33 | Civil | RFI-ELE-CVL-F-D300-GLT-0033 | External | ELECO | Civil Work | N/A | Installation | General Test | Inspection for grouting MC4-MC3 and MC1-MC2 GRE Pipe Opening | BASIL-01-EXE-HQC-000-CVS-SPC-0003 | B | 2026-01-24 | 2026-01-26 | 9.00 AM | I | W | N/A | W | Hanis | D300 | Accepted

## 04.RFI_SVW
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-27
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-CVL-F-D300-SVW-0001 | External | ELECO | Civil Work | N/A | Earth work | Survey | Inspection for survey work at workshop and maintenance office buiding | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-05-09 | 2024-05-10 | 10:00 | H | W | N/A | R | Hanis | D300 | Accepted | -
| 2 | Civil | RFI-ELE-CVL-F-D300-SVW-0002 | External | ELECO | Civil Work | N/A | Earth work | Survey | Inspection for control point survey Benchmark (BM) and Temporary Benchmark (TBM) at D300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-05-18 | 2024-05-20 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted | -
| 3 | Civil | RFI-ELE-CVL-F-D300-SVW-0003 | External | ELECO | Civil Work | N/A | Earth work | Survey | Inspection for setting out survey work at tank and bundwall | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-05-18 | 2024-05-20 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted | -
| 4 | Civil | RFI-ELE-CVL-F-D300-SVW-0004 | External | ELECO | Civil Work | N/A | Earth work | Survey | Inspection for survey work at workshop and maintenance office buiding | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-06-14 | 2024-06-15 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted | -
| 5 | Civil | RFI-ELE-CVL-F-D300-SVW-0005 | External | ELECO | Civil Work | N/A | Earth work | Survey | Inspection for setting out Temporary Benchmark at D300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-19 | 2024-08-20 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 6 | Civil | RFI-ELE-CVL-F-D300-SVW-0006 | External | ELECO | Civil Work | N/A | Earth work | Survey | Inspection for survey work prior to pile cutting activity for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-24 | 2024-08-25 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 7 | Civil | RFI-ELE-CVL-F-D300-SVW-0007 | External | ELECO | Civil Work | N/A | Earth work | Survey | Inspection for survey work prior to pile cutting activity for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-17 | 2024-09-18 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 8 | Civil | RFI-ELE-CVL-F-D300-SVW-0008 | External | ELECO | Civil Work | N/A | Earth work | Survey | Inspection for survey work prior to pile cutting activity for Tank TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-28 | 2024-09-30 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 9 | Civil | RFI-ELE-CVL-F-D300-SVW-0009 | External | ELECO | Civil Work | N/A | Earth work | Survey | Inspection for survey work prior to pile cutting activity for Truck Loading Shelter Area | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-16 | 2024-10-16 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 10 | Civil | RFI-ELE-CVL-F-D300-SVW-0010 | External | ELECO | Civil Work | N/A | Earth work | Survey | Inspection for survey work prior to pile cutting activity for Piperack Area | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | b | 2024-10-21 | 2024-10-21 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 11 | Civil | RFI-ELE-CVL-F-D300-SVW-0011 | External | ELECO | Civil Work | N/A | Earth work | Survey | Inspection for setting out Schedule Waste Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-23 | 2024-11-23 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 12 | Civil | RFI-ELE-CVL-F-D300-SVW-0012 | External | ELECO | Civil Work | N/A | Earth work | Survey | Inspection for survey work prior to pile cutting activity for Firewater Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-16 | 2024-12-16 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 13 | Civil | RFI-ELE-CVL-F-D300-SVW-0013 | External | ELECO | Civil Work | N/A | Earth work | Survey | Inspection for survey work prior to pilehead installation for Micropile Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-16 | 2024-12-16 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
-

## 05.RFI_EXC
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-27
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-CVL-F-D300-EXC-0001 | External | ELECO | Civil Work | N/A | Earth work | Excavation | Inspection for excavation work at workshop and maintenance office buiding | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-05-09 | 2024-05-10 | 10:00 | H | W | N/A | R | Hanis | D300 | Accepted | -
| 2 | Civil | RFI-ELE-CVL-F-D300-EXC-0002 | External | ELECO | Civil Work | N/A | Earth work | Excavation | Inspection for excavation work at workshop and maintenance office buiding | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-05-15 | 2024-05-16 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted | -
| 3 | Civil | RFI-ELE-CVL-F-D300-EXC-0003 | External | ELECO | Civil Work | N/A | Earth work | Excavation | Inspection for excavation work at workshop and maintenance office buiding | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-05-18 | 2024-05-20 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted | -
| 4 | Civil | RFI-ELE-CVL-F-D300-EXC-0004 | External | ELECO | Civil Work | N/A | Earth work | Excavation | Inspection for excavation work prior to foundation installation for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-24 | 2024-08-26 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted | -
| 5 | Civil | RFI-ELE-CVL-F-D300-EXC-0005 | External | ELECO | Civil Work | N/A | Earth work | Excavation | Inspection for excavation work prior to foundation installation for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-07 | 2024-09-09 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted | -
| 6 | Civil | RFI-ELE-CVL-F-D300-EXC-0006 | External | ELECO | Civil Work | N/A | Earth work | Excavation | Inspection for excavation work prior to foundation installation for Tank TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-28 | 2024-09-30 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 7 | Civil | RFI-ELE-CVL-F-D300-EXC-0007 | External | ELECO | Civil Work | N/A | Earth work | Excavation | Inspection for excavation work prior to foundation installation for Truck Loading Shelter Area | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-16 | 2024-10-16 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 8 | Civil | RFI-ELE-CVL-F-D300-EXC-0008 | External | ELECO | Civil Work | N/A | Earth work | Excavation | Inspection for excavation work prior to foundation installation for Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-21 | 2024-10-21 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 9 | Civil | RFI-ELE-CVL-F-D300-EXC-0009 | External | ELECO | Civil Work | N/A | Earth work | Excavation | Inspection for excavation work prior to foundation installation for Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-18 | 2024-11-19 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Cancelled | -
| 10 | Civil | RFI-ELE-CVL-F-D300-EXC-0010 | External | ELECO | Civil Work | N/A | Earth work | Excavation | Inspection for excavation work prior to foundation installation for Schedule Waste Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-23 | 2024-11-23 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 11 | Civil | RFI-ELE-CVL-F-D300-EXC-0011 | External | ELECO | Civil Work | N/A | Earth work | Excavation | Inspection for excavation work prior to foundation installation for Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-14 | 2024-12-14 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 12 | Civil | RFI-ELE-CVL-F-D300-EXC-0012 | External | ELECO | Civil Work | N/A | Earth work | Excavation | Inspection for excavation work prior to foundation installation for Firewater Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-16 | 2024-12-16 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 13 | Civil | RFI-ELE-CVL-F-D300-EXC-0013 | External | ELECO | Civil Work | N/A | Earth work | Excavation | Inspection for excavation work prior to foundation installation for Piperack2 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-16 | 2024-12-16 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 14 | Civil | RFI-ELE-CVL-F-D300-EXC-0014 | External | ELECO | Civil Work | N/A | Earth work | Excavation | Inspection for excavation work prior ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-31 | 2025-06-03 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -

## 06.RFI_PRC
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-27
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-CVL-F-D300-PRC-0001 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pile plug installation for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-25 | 2024-08-26 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 2 | Civil | RFI-ELE-CVL-F-D300-PRC-0002 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap leancon WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-25 | 2024-08-26 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 3 | Civil | RFI-ELE-CVL-F-D300-PRC-0003 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-03 | 2024-09-04 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 4 | Civil | RFI-ELE-CVL-F-D300-PRC-0004 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-04 | 2024-09-06 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 5 | Civil | RFI-ELE-CVL-F-D300-PRC-0005 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for stump column WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-10 | 2024-09-12 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 6 | Civil | RFI-ELE-CVL-F-D300-PRC-0006 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for groundbeam's leancon WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-17 | 2024-09-18 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 7 | Civil | RFI-ELE-CVL-F-D300-PRC-0007 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pile plug installation for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-20 | 2024-09-21 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 8 | Civil | RFI-ELE-CVL-F-D300-PRC-0008 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap leancon WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-20 | 2024-09-21 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 9 | Civil | RFI-ELE-CVL-F-D300-PRC-0009 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-24 | 2024-09-25 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 10 | Civil | RFI-ELE-CVL-F-D300-PRC-0010 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pile plug installation for Tank TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-28 | 2024-09-30 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 11 | Civil | RFI-ELE-CVL-F-D300-PRC-0011 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for stump column WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-30 | 2024-10-01 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 12 | Civil | RFI-ELE-CVL-F-D300-PRC-0012 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for groundbeam WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-03 | 2024-10-04 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 13 | Civil | RFI-ELE-CVL-F-D300-PRC-0013 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pile plug installation for Tank TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-08 | 2024-10-09 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 14 | Civil | RFI-ELE-CVL-F-D300-PRC-0014 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for groundbeam WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-09 | 2024-10-10 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 15 | Civil | RFI-ELE-CVL-F-D300-PRC-0015 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pile plug installation for Tank TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-11 | 2024-10-11 | 3.30 PM | H | W | N/A | R | Hanis | D300 | Accepted
| 16 | Civil | RFI-ELE-CVL-F-D300-PRC-0016 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation leancon Tank TK - 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-15 | 2024-10-16 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 17 | Civil | RFI-ELE-CVL-F-D300-PRC-0017 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pile plug installation for Tank TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-21 | 2024-10-22 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 18 | Civil | RFI-ELE-CVL-F-D300-PRC-0018 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pile plug installation for Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-21 | 2024-10-22 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 19 | Civil | RFI-ELE-CVL-F-D300-PRC-0019 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap leancon for Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-29 | 2024-10-30 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 20 | Civil | RFI-ELE-CVL-F-D300-PRC-0020 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pile plug installation for Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-29 | 2024-10-30 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 21 | Civil | RFI-ELE-CVL-F-D300-PRC-0021 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap for Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-29 | 2024-10-30 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 22 | Civil | RFI-ELE-CVL-F-D300-PRC-0022 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap leancon for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-29 | 2024-10-30 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 23 | Civil | RFI-ELE-CVL-F-D300-PRC-0023 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pileplug installation for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-29 | 2024-10-30 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 24 | Civil | RFI-ELE-CVL-F-D300-PRC-0024 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap for Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-01 | 2024-11-02 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 25 | Civil | RFI-ELE-CVL-F-D300-PRC-0025 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation installation Tank TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-06 | 2024-11-07 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 26 | Civil | RFI-ELE-CVL-F-D300-PRC-0026 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-06 | 2024-11-07 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 27 | Civil | RFI-ELE-CVL-F-D300-PRC-0027 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pileplug installation for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-06 | 2024-11-07 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 28 | Civil | RFI-ELE-CVL-F-D300-PRC-0028 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation leancon Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-11 | 2024-11-11 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 29 | Civil | RFI-ELE-CVL-F-D300-PRC-0029 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation leancon Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-12 | 2024-11-13 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 30 | Civil | RFI-ELE-CVL-F-D300-PRC-0030 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation Pad footing Piperack GL T/2a-3 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-13 | 2024-11-13 | 5.00 PM | H | W | N/A | R | Hanis | D300 | Accepted
| 31 | Civil | RFI-ELE-CVL-F-D300-PRC-0031 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-15 | 2024-11-16 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 32 | Civil | RFI-ELE-CVL-F-D300-PRC-0032 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation Pad footing Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-15 | 2024-11-16 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 33 | Civil | RFI-ELE-CVL-F-D300-PRC-0033 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation leancon Scheduled Waste Storage Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-07 | 2024-12-09 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 34 | Civil | RFI-ELE-CVL-F-D300-PRC-0034 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation leancon Pump Shelter Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-13 | 2024-12-16 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 35 | Civil | RFI-ELE-CVL-F-D300-PRC-0035 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation leancon Piperack foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-13 | 2024-12-16 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 36 | Civil | RFI-ELE-CVL-F-D300-PRC-0036 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for groundslab leancon Switch Room WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-14 | 2024-12-16 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 37 | Civil | RFI-ELE-CVL-F-D300-PRC-0037 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for piperack pedestal GL O-V/2a -8 at D300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-14 | 2024-12-16 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 38 | Civil | RFI-ELE-CVL-F-D300-PRC-0038 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for leancon prior to slab at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-19 | 2024-12-19 | 7.00 PM | H | W | N/A | R | Hanis | D300 | Accepted
| 39 | Civil | RFI-ELE-CVL-F-D300-PRC-0039 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for leancon prior to foundation surrounding slab TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-19 | 2024-12-20 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 40 | Civil | RFI-ELE-CVL-F-D300-PRC-0040 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pump foundation (3 nos) and 1 nos of Heat Exchanger Foundation at Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-21 | 2024-12-23 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 41 | Civil | RFI-ELE-CVL-F-D300-PRC-0041 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for GL 1/ A-B pilecap for Fire Water Pipe Bridge Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-21 | 2024-12-23 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 42 | Civil | RFI-ELE-CVL-F-D300-PRC-0042 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for leancon for piperack GL M-N/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-24 | 2024-12-24 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 43 | Civil | RFI-ELE-CVL-F-D300-PRC-0043 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for leancon for piperack GL D-H/1-2 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-26 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 44 | Civil | RFI-ELE-CVL-F-D300-PRC-0044 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pileplug for piperack GL M-N/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-26 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 45 | Civil | RFI-ELE-CVL-F-D300-PRC-0045 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for leancon WMB GL B-D/ 5-6 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-27 | 2024-12-28 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 46 | Civil | RFI-ELE-CVL-F-D300-PRC-0046 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for non suspended slab WMB GL A-B/1-6 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-28 | 2024-12-30 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 47 | Civil | RFI-ELE-CVL-F-D300-PRC-0047 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pile cap for piperack GL M-N/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-28 | 2024-12-30 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 48 | Civil | RFI-ELE-CVL-F-D300-PRC-0048 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection pedestal GL 1/A-B Firewater bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-01 | 2025-01-02 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 49 | Civil | RFI-ELE-CVL-F-D300-PRC-0049 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection pedestal GL M-N/3-4 Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-01 | 2025-01-02 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 50 | Civil | RFI-ELE-CVL-F-D300-PRC-0050 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection pedestal GL A/1-3 Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-01 | 2025-01-02 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 51 | Civil | RFI-ELE-CVL-F-D300-PRC-0051 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection pilecap for GL C-H/1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-02 | 2025-01-03 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 52 | Civil | RFI-ELE-CVL-F-D300-PRC-0052 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection leancon for pilecap GL J-L/1-4 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-03 | 2025-01-04 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 53 | Civil | RFI-ELE-CVL-F-D300-PRC-0053 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for non suspended slab WMB GL A-B/1-6 Second Phase ( GL A-B/ 4-6) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-04 | 2025-01-06 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 54 | Civil | RFI-ELE-CVL-F-D300-PRC-0054 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for leancon pilecap GL A2-B / 30' - 31' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-06 | 2025-01-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 55 | Civil | RFI-ELE-CVL-F-D300-PRC-0055 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for slab concreting for Tank - 16234 and Bundwall at D300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-07 | 2025-01-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 56 | Civil | RFI-ELE-CVL-F-D300-PRC-0056 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pedestal for GL C-H/1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-09 | 2025-01-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 57 | Civil | RFI-ELE-CVL-F-D300-PRC-0057 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for groundslab leancon WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-10 | 2025-01-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 58 | Civil | RFI-ELE-CVL-F-D300-PRC-0058 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for groundslab WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-10 | 2025-01-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 59 | Civil | RFI-ELE-CVL-F-D300-PRC-0059 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap GL A2-B / 30' - 31' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-16 | 2025-01-17 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 60 | Civil | RFI-ELE-CVL-F-D300-PRC-0060 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for cable trench for switch room at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-22 | 2025-01-23 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 61 | Civil | RFI-ELE-CVL-F-D300-PRC-0061 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for non suspended slab GL A-B/ 5-6 at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-22 | 2025-01-23 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 62 | Civil | RFI-ELE-CVL-F-D300-PRC-0062 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for GroundFloor Slab GL B-D/1-3 at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-24 | 2025-01-25 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 63 | Civil | RFI-ELE-CVL-F-D300-PRC-0063 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Ground Floor to First Floor Column GL A/1-6, GL A-D/5 at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-24 | 2025-01-25 | 9:00 | H | W | N/A | R | Hanis | D300 | Cancelled
| 64 | Civil | RFI-ELE-CVL-F-D300-PRC-0064 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pedestal for GL A1' - A2'/ 29' and GL A-B / 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-25 | 2025-01-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 65 | Civil | RFI-ELE-CVL-F-D300-PRC-0065 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Pilecap for GL A1' - A2'/ 27' - 28', GL A1' - A2' / 30' and GL I / 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-25 | 2025-01-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 66 | Civil | RFI-ELE-CVL-F-D300-PRC-0066 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for cable trench wall for switch room at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-03 | 2025-02-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 67 | Civil | RFI-ELE-CVL-F-D300-PRC-0067 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pedestal for GL A-B / 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-05 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 68 | Civil | RFI-ELE-CVL-F-D300-PRC-0068 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Pilecap for GL J-K/1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-05 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 69 | Civil | RFI-ELE-CVL-F-D300-PRC-0069 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Ground Floor to First Floor Column at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-06 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 70 | Civil | RFI-ELE-CVL-F-D300-PRC-0070 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Ground Floor to First Floor Column at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-06 | 2025-02-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 71 | Civil | RFI-ELE-CVL-F-D300-PRC-0071 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pedestal 2nos Heat Exchanger Foundation at Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-06 | 2025-02-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 72 | Civil | RFI-ELE-CVL-F-D300-PRC-0072 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pedestal for GL J-K / 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-07 | 2025-02-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 73 | Civil | RFI-ELE-CVL-F-D300-PRC-0073 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Ground Floor to First Floor Column at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-10 | 2025-02-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 74 | Civil | RFI-ELE-CVL-F-D300-PRC-0074 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Pilecap for GL A1' - A2' / 30' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-11 | 2025-02-12 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 75 | Civil | RFI-ELE-CVL-F-D300-PRC-0075 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pedestal for GL A1' - A2' / 30' nad J-K/1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-13 | 2025-02-14 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 76 | Civil | RFI-ELE-CVL-F-D300-PRC-0076 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap for GL I / 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-18 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 77 | Civil | RFI-ELE-CVL-F-D300-PRC-0077 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pedestal for Heat Exchanger at Pump Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-18 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 78 | Civil | RFI-ELE-CVL-F-D300-PRC-0078 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pedestal for GL I / 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-19 | 2025-02-20 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 79 | Civil | RFI-ELE-CVL-F-D300-PRC-0079 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean concrete for sump pit at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-24 | 2025-02-25 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 80 | Civil | RFI-ELE-CVL-F-D300-PRC-0080 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for column for GF to 1st Floor GL B/5-6, and D/3,5-6 at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-28 | 2025-03-01 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 81 | Civil | RFI-ELE-CVL-F-D300-PRC-0081 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for bundwall for Product Tank D300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-07 | 2025-03-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 82 | Civil | RFI-ELE-CVL-F-D300-PRC-0082 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean concrete for Chemical and Catalyst Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 83 | Civil | RFI-ELE-CVL-F-D300-PRC-0083 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for concrete for sump pit at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-11 | 2025-03-12 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 84 | Civil | RFI-ELE-CVL-F-D300-PRC-0084 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for concrete for sump pit at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-18 | 2025-03-19 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 85 | Civil | RFI-ELE-CVL-F-D300-PRC-0085 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean concrete for sump pit at Chemical and Catalyst Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-18 | 2025-03-19 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 86 | Civil | RFI-ELE-CVL-F-D300-PRC-0086 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for 1 st Floor Slab at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-25 | 2025-03-26 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 87 | Civil | RFI-ELE-CVL-F-D300-PRC-0087 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for 1 st Column (12 nos) at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-05 | 2025-04-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 88 | Civil | RFI-ELE-CVL-F-D300-PRC-0088 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for CB2 and CB3 and MA2 Pit at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-07 | 2025-04-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 89 | Civil | RFI-ELE-CVL-F-D300-PRC-0089 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean concrete GL A/1-3 for Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 90 | Civil | RFI-ELE-CVL-F-D300-PRC-0090 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for groundfloor slab GL A-B/1-3 for Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-10 | 2025-04-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 91 | Civil | RFI-ELE-CVL-F-D300-PRC-0091 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for 1 st Column (6 nos) GL D/1-6 at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-10 | 2025-04-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 92 | Civil | RFI-ELE-CVL-F-D300-PRC-0092 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for base sump pit for CB1 and MA1A for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-14 | 2025-04-15 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 93 | Civil | RFI-ELE-CVL-F-D300-PRC-0093 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for column pedestal GL A-B/1-3 at Scheule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-15 | 2025-04-16 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 94 | Civil | RFI-ELE-CVL-F-D300-PRC-0094 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for leancon staircase landing at Tank 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-21 | 2025-04-22 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 95 | Civil | RFI-ELE-CVL-F-D300-PRC-0095 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for ground beam staircase landing at Tank 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-22 | 2025-04-23 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 96 | Civil | RFI-ELE-CVL-F-D300-PRC-0096 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Sump Pit for CB1 and MA1A for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-23 | 2025-02-24 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 97 | Civil | RFI-ELE-CVL-F-D300-PRC-0097 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for leancon for CB1 and MA1A area for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-29 | 2025-04-30 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 98 | Civil | RFI-ELE-CVL-F-D300-PRC-0098 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for leancon for CB2 base for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-30 | 2025-05-02 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 99 | Civil | RFI-ELE-CVL-F-D300-PRC-0099 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for CB2 base and MA1A Top for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-03 | 2025-05-05 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 100 | Civil | RFI-ELE-CVL-F-D300-PRC-0100 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for roof slab and roof beam for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-05 | 2025-05-06 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 101 | Civil | RFI-ELE-CVL-F-D300-PRC-0101 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for CB2 wall for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-06 | 2025-05-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 102 | Civil | RFI-ELE-CVL-F-D300-PRC-0102 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean con Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-07 | 2025-05-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 103 | Civil | RFI-ELE-CVL-F-D300-PRC-0103 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for slab Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-09 | 2025-05-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 104 | Civil | RFI-ELE-CVL-F-D300-PRC-0104 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for column Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-21 | 2025-05-23 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 105 | Civil | RFI-ELE-CVL-F-D300-PRC-0105 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for South Staircase for TK16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-28 | 2025-05-29 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 106 | Civil | RFI-ELE-CVL-F-D300-PRC-0106 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for bottom Landing beam North Staircase for TK16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-28 | 2025-05-29 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 107 | Civil | RFI-ELE-CVL-F-D300-PRC-0107 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean con ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-31 | 2025-06-03 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 108 | Civil | RFI-ELE-CVL-F-D300-PRC-0108 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for south roof beam for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-03 | 2025-06-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 109 | Civil | RFI-ELE-CVL-F-D300-PRC-0109 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for South Staircase (internal) for TK16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-04 | 2025-06-05 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 110 | Civil | RFI-ELE-CVL-F-D300-PRC-0110 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for base ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-13 | 2025-06-14 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 111 | Civil | RFI-ELE-CVL-F-D300-PRC-0111 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean concrete Groundslab Switchroom at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-16 | 2025-06-17 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 112 | Civil | RFI-ELE-CVL-F-D300-PRC-0112 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Groundslab Switchroom at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-18 | 2025-06-19 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 113 | Civil | RFI-ELE-CVL-F-D300-PRC-0113 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for North Staircase (internal and external) for TK16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-19 | 2025-06-20 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 114 | Civil | RFI-ELE-CVL-F-D300-PRC-0114 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean concrete trench for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-19 | 2025-06-20 | 9:00 | H | W | N/A | R | Hanis | D300 | Cancelled
| 115 | Civil | RFI-ELE-CVL-F-D300-PRC-0115 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean concrete trench for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-23 | 2025-06-24 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 116 | Civil | RFI-ELE-CVL-F-D300-PRC-0116 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for roof beam for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-23 | 2025-06-24 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 117 | Civil | RFI-ELE-CVL-F-D300-PRC-0117 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean con north east Staircase for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-24 | 2025-06-25 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 118 | Civil | RFI-ELE-CVL-F-D300-PRC-0118 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation north east Staircase for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-26 | 2025-06-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 119 | Civil | RFI-ELE-CVL-F-D300-PRC-0119 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for base trench and sump pit for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-26 | 2025-06-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 120 | Civil | RFI-ELE-CVL-F-D300-PRC-0120 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Wall 1 st Cast ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-26 | 2025-06-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 121 | Civil | RFI-ELE-CVL-F-D300-PRC-0121 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for insternal staircase flight for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-27 | 2025-06-28 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 122 | Civil | RFI-ELE-CVL-F-D300-PRC-0122 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Wall 1 st Cast ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-01 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 123 | Civil | RFI-ELE-CVL-F-D300-PRC-0123 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pileplug for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-02 | 2025-07-03 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 124 | Civil | RFI-ELE-CVL-F-D300-PRC-0124 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for leancon for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-02 | 2025-07-03 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 125 | Civil | RFI-ELE-CVL-F-D300-PRC-0125 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for trench for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-02 | 2025-07-03 | 9:00 | H | W | N/A | R | Hanis | D300 | Cancelled
| 126 | Civil | RFI-ELE-CVL-F-D300-PRC-0126 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for flight north east Staircase for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-08 | 2025-07-09 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 127 | Civil | RFI-ELE-CVL-F-D300-PRC-0127 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pileplug for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-08 | 2025-07-09 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 128 | Civil | RFI-ELE-CVL-F-D300-PRC-0128 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for leancon for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-08 | 2025-07-09 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 129 | Civil | RFI-ELE-CVL-F-D300-PRC-0129 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 130 | Civil | RFI-ELE-CVL-F-D300-PRC-0130 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for trench for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 131 | Civil | RFI-ELE-CVL-F-D300-PRC-0131 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-10 | 2025-07-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 132 | Civil | RFI-ELE-CVL-F-D300-PRC-0132 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Wall 2nd Cast ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-12 | 2025-07-14 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 133 | Civil | RFI-ELE-CVL-F-D300-PRC-0133 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-14 | 2025-07-15 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 134 | Civil | RFI-ELE-CVL-F-D300-PRC-0134 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of slab for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-01 | 2025-08-02 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 135 | Civil | RFI-ELE-CVL-F-D300-PRC-0135 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of Lean con for GL J-L/3-4 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-01 | 2025-08-02 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 136 | Civil | RFI-ELE-CVL-F-D300-PRC-0136 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap for GL J-L/3-4 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-02 | 2025-08-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 137 | Civil | RFI-ELE-CVL-F-D300-PRC-0137 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal for GL J-L/3-4 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-06 | 2025-08-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 138 | Civil | RFI-ELE-CVL-F-D300-PRC-0138 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-06 | 2025-08-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 139 | Civil | RFI-ELE-CVL-F-D300-PRC-0139 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean con Pipe Support for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-06 | 2025-08-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 140 | Civil | RFI-ELE-CVL-F-D300-PRC-0140 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of foundation Pipe Support for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-12 | 2025-08-13 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 141 | Civil | RFI-ELE-CVL-F-D300-PRC-0141 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Top slab ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-14 | 2025-08-15 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 142 | Civil | RFI-ELE-CVL-F-D300-PRC-0142 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal F4 and F5 Pipe Support for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-19 | 2025-08-20 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 143 | Civil | RFI-ELE-CVL-F-D300-PRC-0143 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for bottom gate valve pit ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-21 | 2025-08-22 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 144 | Civil | RFI-ELE-CVL-F-D300-PRC-0144 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon Pipe support foundation East Side for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-25 | 2025-08-26 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 145 | Civil | RFI-ELE-CVL-F-D300-PRC-0145 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon CCW Pit S-18242 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-25 | 2025-08-26 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 146 | Civil | RFI-ELE-CVL-F-D300-PRC-0146 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of base sump CCW Pit S-18242 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-28 | 2025-08-29 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 147 | Civil | RFI-ELE-CVL-F-D300-PRC-0147 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of Pipe support foundation East Side for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-28 | 2025-08-29 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 148 | Civil | RFI-ELE-CVL-F-D300-PRC-0148 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection oh HVAC Power and Control Panel Foundation at Switchroom WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-30 | 2025-09-02 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 149 | Civil | RFI-ELE-CVL-F-D300-PRC-0149 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of Pipe support foundation pedestal East Side for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 150 | Civil | RFI-ELE-CVL-F-D300-PRC-0150 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for wall gate valve pit ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 151 | Civil | RFI-ELE-CVL-F-D300-PRC-0151 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for stiffener at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 152 | Civil | RFI-ELE-CVL-F-D300-PRC-0152 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of 1st cast wall sump CCW Pit S-18242 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-04 | 2025-09-05 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 153 | Civil | RFI-ELE-CVL-F-D300-PRC-0153 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of 2ndt cast wall and top slab sump CCW Pit S-18242 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-12 | 2025-09-13 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 154 | Civil | RFI-ELE-CVL-F-D300-PRC-0154 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon for SP1 and SP2 sump pit at Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-17 | 2025-09-18 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 155 | Civil | RFI-ELE-CVL-F-D300-PRC-0155 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of base for SP1 and SP2 sump pit at Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-22 | 2025-09-23 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 156 | Civil | RFI-ELE-CVL-F-D300-PRC-0156 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of Wall for SP1 and SP2 sump pit at Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 157 | Civil | RFI-ELE-CVL-F-D300-PRC-0157 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of precast manhole base for MS4, MS4A, MS5, MS5A, MS9, MS9A and MS10 for D300 at M-One Fabrication Yard | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-26 | 2025-09-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 158 | Civil | RFI-ELE-CVL-F-D300-PRC-0158 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean concrete for slab Pump Foundation Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-08 | 2025-10-09 | 9:00 | H | W | N/A | R | Hanis | D300 | Cancelled
| 159 | Civil | RFI-ELE-CVL-F-D300-PRC-0159 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean concrete for slab Pump Foundation Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-18 | 2025-10-20 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 160 | Civil | RFI-ELE-CVL-F-D300-PRC-0160 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of slab and plinth Pump Foundation Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-29 | 2025-10-30 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 161 | Civil | RFI-ELE-CVL-F-D300-PRC-0161 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of slab Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-29 | 2025-10-30 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 162 | Civil | RFI-ELE-CVL-F-D300-PRC-0162 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal plinth Pump Foundation Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-31 | 2025-11-01 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 163 | Civil | RFI-ELE-CVL-F-D300-PRC-0163 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of kerb plinth Pump Foundation Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-03 | 2025-11-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 164 | Civil | RFI-ELE-CVL-F-D300-PRC-0164 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of kerb Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-03 | 2025-11-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 165 | Civil | RFI-ELE-CVL-F-D300-PRC-0165 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of precast manhole base for D300 at M-One Fabrication Yard | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-03 | 2025-11-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 166 | Civil | RFI-ELE-CVL-F-D300-PRC-0166 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean con pipe support foundation around TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-10 | 2025-11-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 167 | Civil | RFI-ELE-CVL-F-D300-PRC-0167 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pipe support foundation around TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-19 | 2025-11-20 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 168 | Civil | RFI-ELE-CVL-F-D300-PRC-0168 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean con pipe support foundation around Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-20 | 2025-11-21 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 169 | Civil | RFI-ELE-CVL-F-D300-PRC-0169 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pipe support foundation around New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-20 | 2025-11-21 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 170 | Civil | RFI-ELE-CVL-F-D300-PRC-0170 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pipe support foundation around Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-21 | 2025-11-22 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 171 | Civil | RFI-ELE-CVL-F-D300-PRC-0171 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pipe support pedestal around New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-26 | 2025-11-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 172 | Civil | RFI-ELE-CVL-F-D300-PRC-0172 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pipe support pedestal around ACW First Flush Basin | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-26 | 2025-11-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 173 | Civil | RFI-ELE-CVL-F-D300-PRC-0173 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pipe support foundation around Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-26 | 2025-11-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 174 | Civil | RFI-ELE-CVL-F-D300-PRC-0174 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pipe support pedestal around Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-26 | 2025-11-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 175 | Civil | RFI-ELE-CVL-F-D300-PRC-0175 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean concrete pipe support around TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-29 | 2025-12-01 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 176 | Civil | RFI-ELE-CVL-F-D300-PRC-0176 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pipe support pedestal around Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-29 | 2025-12-01 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 177 | Civil | RFI-ELE-CVL-F-D300-PRC-0177 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pipe support pedestal around New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-29 | 2025-12-01 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 178 | Civil | RFI-ELE-CVL-F-D300-PRC-0178 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of Precast Manholes for MS and MA at Fabrication Yard | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-29 | 2025-12-01 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 179 | Civil | RFI-ELE-CVL-F-D300-PRC-0179 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pipe support around TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-01 | 2025-12-02 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 180 | Civil | RFI-ELE-CVL-F-D300-PRC-0180 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal pipe support around TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-05 | 2025-12-06 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 181 | Civil | RFI-ELE-CVL-F-D300-PRC-0181 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pipe support foundation around New Piperack GL J-L/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-05 | 2025-12-06 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 182 | Civil | RFI-ELE-CVL-F-D300-PRC-0182 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean con pipe support foundation F1 around New Piperack GL J-L/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-08 | 2025-12-09 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 183 | Civil | RFI-ELE-CVL-F-D300-PRC-0183 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean con pipe support foundation F1 and F2 around Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-08 | 2025-12-09 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 184 | Civil | RFI-ELE-CVL-F-D300-PRC-0184 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal pipe support foundation around New Piperack GL J-L/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-09 | 2025-12-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 185 | Civil | RFI-ELE-CVL-F-D300-PRC-0185 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pipe support foundation F1 around New Piperack GL J-L/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-09 | 2025-12-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 186 | Civil | RFI-ELE-CVL-F-D300-PRC-0186 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pipe support foundation F1 and F2 around Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-09 | 2025-12-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 187 | Civil | RFI-ELE-CVL-F-D300-PRC-0187 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of Precast Manholes for MA1, MA2, MA3 and MA4 Wall at Fabrication Yard | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-09 | 2025-12-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 188 | Civil | RFI-ELE-CVL-F-D300-PRC-0188 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean con for safety shower foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-16 | 2025-12-17 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 189 | Civil | RFI-ELE-CVL-F-D300-PRC-0189 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pipe support pedestal F1 and F2 around Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-16 | 2025-12-17 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 190 | Civil | RFI-ELE-CVL-F-D300-PRC-0190 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal pipe support foundation around New Piperack GL J-L/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-16 | 2025-12-17 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 191 | Civil | RFI-ELE-CVL-F-D300-PRC-0191 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of Precast light pole foundation at D300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-16 | 2025-12-17 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 192 | Civil | RFI-ELE-CVL-F-D300-PRC-0192 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pipe support pedestal F1 and F2 around Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-23 | 2025-12-24 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 193 | Civil | RFI-ELE-CVL-F-D300-PRC-0193 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of foundation for safety shower foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-23 | 2025-12-24 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 194 | Civil | RFI-ELE-CVL-F-D300-PRC-0194 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon for Chemical and Catalyst Storage Shelter ramp | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-30 | 2025-12-31 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 195 | Civil | RFI-ELE-CVL-F-D300-PRC-0195 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Chemical and Catalyst Storage Shelter ramp | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-02 | 2026-01-03 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 196 | Civil | RFI-ELE-CVL-F-D300-PRC-0196 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon for Scheduled Waste Storage Building ramp | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-02 | 2026-01-03 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 197 | Civil | RFI-ELE-CVL-F-D300-PRC-0197 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of DB foundation AL06 and AL03 at D300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-02 | 2026-01-03 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 198 | Civil | RFI-ELE-CVL-F-D300-PRC-0198 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Scheduled Waste Storage Building ramp | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-06 | 2026-01-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 199 | Civil | RFI-ELE-CVL-F-D300-PRC-0199 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean con pipe support 'F1" around Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-23 | 2026-01-24 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 200 | Civil | RFI-ELE-CVL-F-D300-PRC-0200 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pipe support 'F1" around Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-24 | 2026-01-26 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 201 | Civil | RFI-ELE-CVL-F-D300-PRC-0201 | External | ELECO | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pipe support pedestal 'F1" around Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-27 | 2026-01-28 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing

## 07.RFI_CON
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-27
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-CVL-F-D300-CON-0001 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pile plug installation for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-25 | 2024-08-27 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 2 | Civil | RFI-ELE-CVL-F-D300-CON-0002 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap leancon WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-25 | 2024-08-27 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 3 | Civil | RFI-ELE-CVL-F-D300-CON-0003 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-03 | 2024-09-04 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 4 | Civil | RFI-ELE-CVL-F-D300-CON-0004 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-04 | 2024-09-06 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 5 | Civil | RFI-ELE-CVL-F-D300-CON-0005 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for stump column WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-10 | 2024-09-12 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 6 | Civil | RFI-ELE-CVL-F-D300-CON-0006 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for groundbeam's leancon WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-17 | 2024-09-18 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 7 | Civil | RFI-ELE-CVL-F-D300-CON-0007 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pile plug installation for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-20 | 2024-09-21 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 8 | Civil | RFI-ELE-CVL-F-D300-CON-0008 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap leancon WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-20 | 2024-09-21 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 9 | Civil | RFI-ELE-CVL-F-D300-CON-0009 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-24 | 2024-09-25 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 10 | Civil | RFI-ELE-CVL-F-D300-CON-0010 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pile plug installation for Tank TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-28 | 2024-09-30 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 11 | Civil | RFI-ELE-CVL-F-D300-CON-0011 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for stump column WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-30 | 2024-10-01 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 12 | Civil | RFI-ELE-CVL-F-D300-CON-0012 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for groundbeam WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-03 | 2024-10-04 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 13 | Civil | RFI-ELE-CVL-F-D300-CON-0013 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pile plug installation for Tank TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-08 | 2024-10-09 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 14 | Civil | RFI-ELE-CVL-F-D300-CON-0014 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for groundbeam WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-09 | 2024-10-10 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 15 | Civil | RFI-ELE-CVL-F-D300-CON-0015 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pile plug installation for Tank TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-11 | 2024-10-11 | 3.30 PM | H | W | N/A | R | Hanis | D300 | Accepted
| 16 | Civil | RFI-ELE-CVL-F-D300-CON-0016 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation leancon Tank TK - 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-15 | 2024-10-16 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 17 | Civil | RFI-ELE-CVL-F-D300-CON-0017 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pile plug installation for Tank TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-21 | 2024-10-22 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 18 | Civil | RFI-ELE-CVL-F-D300-CON-0018 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pile plug installation for Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-21 | 2024-10-22 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 19 | Civil | RFI-ELE-CVL-F-D300-CON-0019 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap leancon for Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-29 | 2024-10-30 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 20 | Civil | RFI-ELE-CVL-F-D300-CON-0020 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pile plug installation for Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-29 | 2024-10-30 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 21 | Civil | RFI-ELE-CVL-F-D300-CON-0021 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap for Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-29 | 2024-10-30 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 22 | Civil | RFI-ELE-CVL-F-D300-CON-0022 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap leancon for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-29 | 2024-10-30 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 23 | Civil | RFI-ELE-CVL-F-D300-CON-0023 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pileplug installation for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-29 | 2024-10-30 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 24 | Civil | RFI-ELE-CVL-F-D300-CON-0024 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap for Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-01 | 2024-11-02 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 25 | Civil | RFI-ELE-CVL-F-D300-CON-0025 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation installation Tank TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-06 | 2024-11-07 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 26 | Civil | RFI-ELE-CVL-F-D300-CON-0026 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-06 | 2024-11-07 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 27 | Civil | RFI-ELE-CVL-F-D300-CON-0027 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pileplug installation for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-06 | 2024-11-07 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 28 | Civil | RFI-ELE-CVL-F-D300-CON-0028 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation leancon Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-11 | 2024-11-11 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 29 | Civil | RFI-ELE-CVL-F-D300-CON-0029 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation leancon Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-12 | 2024-11-13 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 30 | Civil | RFI-ELE-CVL-F-D300-CON-0030 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation Pad footing Piperack GL T/2a-3 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-13 | 2024-11-13 | 5.00 PM | H | W | N/A | R | Hanis | D300 | Accepted
| 31 | Civil | RFI-ELE-CVL-F-D300-CON-0031 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-15 | 2024-11-16 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 32 | Civil | RFI-ELE-CVL-F-D300-CON-0032 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation Pad footing Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-15 | 2024-11-16 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 33 | Civil | RFI-ELE-CVL-F-D300-CON-0033 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation leancon Scheduled Waste Storage Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-07 | 2024-12-09 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 34 | Civil | RFI-ELE-CVL-F-D300-CON-0034 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation leancon Pump Shelter Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-13 | 2024-12-16 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 35 | Civil | RFI-ELE-CVL-F-D300-CON-0035 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation leancon Piperack foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-13 | 2024-12-16 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 36 | Civil | RFI-ELE-CVL-F-D300-CON-0036 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for groundslab leancon Switch Room WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-14 | 2024-12-16 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 37 | Civil | RFI-ELE-CVL-F-D300-CON-0037 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for piperack pedestal GL O-V/2a -8 at D300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-14 | 2024-12-16 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 38 | Civil | RFI-ELE-CVL-F-D300-CON-0038 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for leancon prior to slab at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-19 | 2024-12-19 | 7.00 PM | H | W | N/A | R | Hanis | D300 | Accepted
| 39 | Civil | RFI-ELE-CVL-F-D300-CON-0039 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for leancon prior to foundation surrounding slab TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-19 | 2024-12-20 | 7.00 PM | H | W | N/A | R | Hanis | D300 | Accepted
| 40 | Civil | RFI-ELE-CVL-F-D300-CON-0040 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pump foundation (3 nos) and 1 nos of Heat Exchanger Foundation at Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-21 | 2024-12-23 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 41 | Civil | RFI-ELE-CVL-F-D300-CON-0041 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for GL 1/ A-B pilecap for Fire Water Pipe Bridge Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-21 | 2024-12-23 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 42 | Civil | RFI-ELE-CVL-F-D300-CON-0042 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for leancon for piperack GL M-N/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-24 | 2024-12-24 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 43 | Civil | RFI-ELE-CVL-F-D300-CON-0043 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for leancon for piperack GL D-H/2-3 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-26 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 44 | Civil | RFI-ELE-CVL-F-D300-CON-0044 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pileplug for piperack GL M-N/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-26 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 45 | Civil | RFI-ELE-CVL-F-D300-CON-0045 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for leancon WMB GL B-D/ 5-6 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-27 | 2024-12-28 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 46 | Civil | RFI-ELE-CVL-F-D300-CON-0046 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for non suspended slab WMB GL A-B/1-6 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-28 | 2024-12-30 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 47 | Civil | RFI-ELE-CVL-F-D300-CON-0047 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pile cap for piperack GL M-N/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-28 | 2024-12-30 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 48 | Civil | RFI-ELE-CVL-F-D300-CON-0048 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection pedestal GL 1/A-B Firewater bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-01 | 2025-01-02 | 19:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 49 | Civil | RFI-ELE-CVL-F-D300-CON-0049 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection pedestal GL M-N/3-4 Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-01 | 2025-01-02 | 20:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 50 | Civil | RFI-ELE-CVL-F-D300-CON-0050 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection pedestal GL A/1-3 Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-01 | 2025-01-02 | 21:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 51 | Civil | RFI-ELE-CVL-F-D300-CON-0051 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection pilecap for GL C-H/1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-02 | 2025-01-03 | 21:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 52 | Civil | RFI-ELE-CVL-F-D300-CON-0052 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection leancon for pilecap GL J-L/1-4 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-03 | 2025-01-04 | 21:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 53 | Civil | RFI-ELE-CVL-F-D300-CON-0053 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for non suspended slab WMB GL A-B/1-6 Second Phase ( GL A-B/ 4-6) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-04 | 2025-01-06 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 54 | Civil | RFI-ELE-CVL-F-D300-CON-0054 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for leancon pilecap GL A2-B / 30' - 31' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-06 | 2025-01-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 55 | Civil | RFI-ELE-CVL-F-D300-CON-0055 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for slab concreting for Tank - 16234 and Bundwall at D300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-07 | 2025-01-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 56 | Civil | RFI-ELE-CVL-F-D300-CON-0056 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pedestal for GL C-H/1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-09 | 2025-01-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 57 | Civil | RFI-ELE-CVL-F-D300-CON-0057 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for groundslab leancon WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-10 | 2025-01-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 58 | Civil | RFI-ELE-CVL-F-D300-CON-0058 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for groundslab WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-10 | 2025-01-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 59 | Civil | RFI-ELE-CVL-F-D300-CON-0059 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap GL A2-B / 30' - 31' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-16 | 2025-01-17 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 60 | Civil | RFI-ELE-CVL-F-D300-CON-0060 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for cable trench for switch room at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-22 | 2025-01-23 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 61 | Civil | RFI-ELE-CVL-F-D300-CON-0061 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for non suspended slab GL A-B/ 5-6 at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-22 | 2025-01-23 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 62 | Civil | RFI-ELE-CVL-F-D300-CON-0062 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for GroundFloor Slab GL B-D/1-3 at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-24 | 2025-01-25 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 63 | Civil | RFI-ELE-CVL-F-D300-CON-0063 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for Ground Floor to First Floor Column GL A/1-6, GL A-D/5 at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-24 | 2025-01-25 | 9:00 | H | W | N/A | R | Hanis | D300 | Cancelled
| 64 | Civil | RFI-ELE-CVL-F-D300-CON-0064 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pedestal for GL A1' - A2'/ 29' and GL A-B / 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-25 | 2025-01-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 65 | Civil | RFI-ELE-CVL-F-D300-CON-0065 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for Pilecap for GL A1' - A2'/ 27' - 28', GL A1' - A2' / 30' and GL I / 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-25 | 2025-01-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 66 | Civil | RFI-ELE-CVL-F-D300-CON-0066 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for cable trench wall for switch room at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-03 | 2025-02-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 67 | Civil | RFI-ELE-CVL-F-D300-CON-0067 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pedestal for GL A-B / 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-05 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 68 | Civil | RFI-ELE-CVL-F-D300-CON-0068 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for Pilecap for GL J-K/1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-05 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 69 | Civil | RFI-ELE-CVL-F-D300-CON-0069 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for Ground Floor to First Floor Column at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-06 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 70 | Civil | RFI-ELE-CVL-F-D300-CON-0070 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for Ground Floor to First Floor Column at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-06 | 2025-02-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 71 | Civil | RFI-ELE-CVL-F-D300-CON-0071 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pedestal 2nos Heat Exchanger Foundation at Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-06 | 2025-02-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 72 | Civil | RFI-ELE-CVL-F-D300-CON-0072 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pedestal for GL J-K / 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-07 | 2025-02-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 73 | Civil | RFI-ELE-CVL-F-D300-CON-0073 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for Ground Floor to First Floor Column at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-10 | 2025-02-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 74 | Civil | RFI-ELE-CVL-F-D300-CON-0074 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for Pilecap for GL A1' - A2' / 30' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-11 | 2025-02-12 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 75 | Civil | RFI-ELE-CVL-F-D300-CON-0075 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pedestal for GL A1' - A2' / 30' nad J-K/1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-13 | 2025-02-14 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 76 | Civil | RFI-ELE-CVL-F-D300-CON-0076 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap for GL I / 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-18 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 77 | Civil | RFI-ELE-CVL-F-D300-CON-0077 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pedestal for Heat Exchanger at Pump Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-18 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 78 | Civil | RFI-ELE-CVL-F-D300-CON-0078 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pedestal for GL I / 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-19 | 2025-02-20 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 79 | Civil | RFI-ELE-CVL-F-D300-CON-0079 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean concrete for sump pit at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-24 | 2025-02-25 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 80 | Civil | RFI-ELE-CVL-F-D300-CON-0080 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for column for GF to 1st Floor GL B/5-6, and D/3,5-6 at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-28 | 2025-03-01 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 81 | Civil | RFI-ELE-CVL-F-D300-CON-0081 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for bundwall for Product Tank D300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-07 | 2025-03-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 82 | Civil | RFI-ELE-CVL-F-D300-CON-0082 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean concrete for Chemical and Catalyst Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 83 | Civil | RFI-ELE-CVL-F-D300-CON-0083 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for concrete for sump pit at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-11 | 2025-03-12 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 84 | Civil | RFI-ELE-CVL-F-D300-CON-0084 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for concrete for sump pit at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-18 | 2025-03-19 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 85 | Civil | RFI-ELE-CVL-F-D300-CON-0085 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean concrete for sump pit at Chemical and Catalyst Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-18 | 2025-03-19 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 86 | Civil | RFI-ELE-CVL-F-D300-CON-0086 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for 1 st Floor Slab at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-25 | 2025-03-26 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 87 | Civil | RFI-ELE-CVL-F-D300-CON-0087 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for 1 st Column (12 nos) at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-05 | 2025-04-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 88 | Civil | RFI-ELE-CVL-F-D300-CON-0088 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for CB2 and CB3 and MA2 Pit at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-07 | 2025-04-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 89 | Civil | RFI-ELE-CVL-F-D300-CON-0089 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean concrete GL A/1-3 for Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 90 | Civil | RFI-ELE-CVL-F-D300-CON-0090 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for groundfloor slab GL A-B/1-3 for Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-10 | 2025-04-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 91 | Civil | RFI-ELE-CVL-F-D300-CON-0091 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for 1 st Column (6 nos) GL D/1-6 at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-10 | 2025-04-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 92 | Civil | RFI-ELE-CVL-F-D300-CON-0092 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for base sump pit for CB1 and MA1A for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-14 | 2025-04-15 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 93 | Civil | RFI-ELE-CVL-F-D300-CON-0093 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for column pedestal GL A-B/1-3 at Scheule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-15 | 2025-04-16 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 94 | Civil | RFI-ELE-CVL-F-D300-CON-0094 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for leancon staircase landing at Tank 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-21 | 2025-04-22 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 95 | Civil | RFI-ELE-CVL-F-D300-CON-0095 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for ground beam staircase landing at Tank 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-22 | 2025-04-23 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 96 | Civil | RFI-ELE-CVL-F-D300-CON-0096 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for Sump Pit for CB1 and MA1A for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-23 | 2025-02-24 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 97 | Civil | RFI-ELE-CVL-F-D300-CON-0097 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for leancon for CB1 and MA1A area for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-29 | 2025-04-30 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 98 | Civil | RFI-ELE-CVL-F-D300-CON-0098 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for leancon for CB2 base for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-30 | 2025-05-02 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 99 | Civil | RFI-ELE-CVL-F-D300-CON-0099 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for CB2 base and MA1A Top for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-03 | 2025-05-05 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 100 | Civil | RFI-ELE-CVL-F-D300-CON-0100 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for roof slab and roof beam for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-05 | 2025-05-06 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 101 | Civil | RFI-ELE-CVL-F-D300-CON-0101 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for CB2 wall for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-06 | 2025-05-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 102 | Civil | RFI-ELE-CVL-F-D300-CON-0102 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean con Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-07 | 2025-05-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 103 | Civil | RFI-ELE-CVL-F-D300-CON-0103 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for slab Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-09 | 2025-05-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 104 | Civil | RFI-ELE-CVL-F-D300-CON-0104 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for column Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-21 | 2025-05-23 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 105 | Civil | RFI-ELE-CVL-F-D300-CON-0105 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for South Staircase for TK16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-28 | 2025-05-29 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 106 | Civil | RFI-ELE-CVL-F-D300-CON-0106 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for bottom Landing beam North Staircase for TK16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-28 | 2025-05-29 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 107 | Civil | RFI-ELE-CVL-F-D300-CON-0107 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean con ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-31 | 2025-06-03 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 108 | Civil | RFI-ELE-CVL-F-D300-CON-0108 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for south roof beam for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-03 | 2025-06-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 109 | Civil | RFI-ELE-CVL-F-D300-CON-0109 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for South Staircase (internal) for TK16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-04 | 2025-06-05 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 110 | Civil | RFI-ELE-CVL-F-D300-CON-0110 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for base ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-13 | 2025-06-14 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 111 | Civil | RFI-ELE-CVL-F-D300-CON-0111 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean concrete Groundslab Switchroom at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-16 | 2025-06-17 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 112 | Civil | RFI-ELE-CVL-F-D300-CON-0112 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for Groundslab Switchroom at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-18 | 2025-06-19 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 113 | Civil | RFI-ELE-CVL-F-D300-CON-0113 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for North Staircase (internal and external) for TK16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-19 | 2025-06-20 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 114 | Civil | RFI-ELE-CVL-F-D300-CON-0114 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean concrete trench for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-19 | 2025-06-20 | 9:00 | H | W | N/A | R | Hanis | D300 | Cancelled
| 115 | Civil | RFI-ELE-CVL-F-D300-CON-0115 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean concrete trench for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-23 | 2025-06-24 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 116 | Civil | RFI-ELE-CVL-F-D300-CON-0116 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for roof beam for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-23 | 2025-06-24 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 117 | Civil | RFI-ELE-CVL-F-D300-CON-0117 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean con north east Staircase for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-24 | 2025-06-25 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 118 | Civil | RFI-ELE-CVL-F-D300-CON-0118 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation north east Staircase for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-26 | 2025-06-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 119 | Civil | RFI-ELE-CVL-F-D300-CON-0119 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for base trench and sump pit for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-26 | 2025-06-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 120 | Civil | RFI-ELE-CVL-F-D300-CON-0120 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for Wall 1 st Cast ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-26 | 2025-06-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 121 | Civil | RFI-ELE-CVL-F-D300-CON-0121 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for insternal staircase flight for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-27 | 2025-06-28 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 122 | Civil | RFI-ELE-CVL-F-D300-CON-0122 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for Wall 1 st Cast ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-01 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 123 | Civil | RFI-ELE-CVL-F-D300-CON-0123 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pileplug for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-02 | 2025-07-03 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 124 | Civil | RFI-ELE-CVL-F-D300-CON-0124 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for leancon for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-02 | 2025-07-03 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 125 | Civil | RFI-ELE-CVL-F-D300-CON-0125 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for trench for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-02 | 2025-07-03 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 126 | Civil | RFI-ELE-CVL-F-D300-CON-0126 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for flight north east Staircase for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-08 | 2025-07-09 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 127 | Civil | RFI-ELE-CVL-F-D300-CON-0127 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for pileplug for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-08 | 2025-07-09 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 128 | Civil | RFI-ELE-CVL-F-D300-CON-0128 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for leancon for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-08 | 2025-07-09 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 129 | Civil | RFI-ELE-CVL-F-D300-CON-0129 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 130 | Civil | RFI-ELE-CVL-F-D300-CON-0130 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for trench for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 131 | Civil | RFI-ELE-CVL-F-D300-CON-0131 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-10 | 2025-07-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 132 | Civil | RFI-ELE-CVL-F-D300-CON-0132 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for Wall 2nd Cast ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-12 | 2025-07-14 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 133 | Civil | RFI-ELE-CVL-F-D300-CON-0133 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-14 | 2025-07-15 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 134 | Civil | RFI-ELE-CVL-F-D300-CON-0134 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of slab for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-01 | 2025-08-02 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 135 | Civil | RFI-ELE-CVL-F-D300-CON-0135 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of Lean con for GL J-L/3-4 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-01 | 2025-08-02 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 136 | Civil | RFI-ELE-CVL-F-D300-CON-0136 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap for GL J-L/3-4 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-02 | 2025-08-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 137 | Civil | RFI-ELE-CVL-F-D300-CON-0137 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal for GL J-L/3-4 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-06 | 2025-08-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 138 | Civil | RFI-ELE-CVL-F-D300-CON-0138 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-06 | 2025-08-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 139 | Civil | RFI-ELE-CVL-F-D300-CON-0139 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean con Pipe Support for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-06 | 2025-08-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 140 | Civil | RFI-ELE-CVL-F-D300-CON-0140 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of foundation Pipe Support for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-12 | 2025-08-13 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 141 | Civil | RFI-ELE-CVL-F-D300-CON-0141 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for Top slab ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-14 | 2025-08-15 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 142 | Civil | RFI-ELE-CVL-F-D300-CON-0142 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal F4 and F5 Pipe Support for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-19 | 2025-08-20 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 143 | Civil | RFI-ELE-CVL-F-D300-CON-0143 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for bottom gate valve pit ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-21 | 2025-08-22 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 144 | Civil | RFI-ELE-CVL-F-D300-CON-0144 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon Pipe support foundation East Side for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-25 | 2025-08-26 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 145 | Civil | RFI-ELE-CVL-F-D300-CON-0145 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon CCW Pit S-18242 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-25 | 2025-08-26 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 146 | Civil | RFI-ELE-CVL-F-D300-CON-0146 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of base sump CCW Pit S-18242 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-28 | 2025-08-29 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 147 | Civil | RFI-ELE-CVL-F-D300-CON-0147 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of Pipe support foundation East Side for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-28 | 2025-08-29 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 148 | Civil | RFI-ELE-CVL-F-D300-CON-0148 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection oh HVAC Power and Control Panel Foundation at Switchroom WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-30 | 2025-09-02 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 149 | Civil | RFI-ELE-CVL-F-D300-CON-0149 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of Pipe support foundation pedestal East Side for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 150 | Civil | RFI-ELE-CVL-F-D300-CON-0150 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for wall gate valve pit ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 151 | Civil | RFI-ELE-CVL-F-D300-CON-0151 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for stiffener at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 152 | Civil | RFI-ELE-CVL-F-D300-CON-0152 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of 1st cast wall sump CCW Pit S-18242 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-04 | 2025-09-05 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 153 | Civil | RFI-ELE-CVL-F-D300-CON-0153 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of 2ndt cast wall and top slab sump CCW Pit S-18242 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-12 | 2025-09-13 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 154 | Civil | RFI-ELE-CVL-F-D300-CON-0154 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon for SP1 and SP2 sump pit at Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-17 | 2025-09-18 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 155 | Civil | RFI-ELE-CVL-F-D300-CON-0155 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of base for SP1 and SP2 sump pit at Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-22 | 2025-09-23 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 156 | Civil | RFI-ELE-CVL-F-D300-CON-0156 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of Wall for SP1 and SP2 sump pit at Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 157 | Civil | RFI-ELE-CVL-F-D300-CON-0157 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of precast manhole base for MS4, MS4A, MS5, MS5A, MS9, MS9A and MS10 for D300 at M-One Fabrication Yard | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-26 | 2025-09-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 158 | Civil | RFI-ELE-CVL-F-D300-CON-0158 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean concrete for slab Pump Foundation Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-08 | 2025-10-09 | 9:00 | H | W | N/A | R | Hanis | D300 | Cancelled
| 159 | Civil | RFI-ELE-CVL-F-D300-CON-0159 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean concrete for slab Pump Foundation Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-18 | 2025-10-20 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 160 | Civil | RFI-ELE-CVL-F-D300-CON-0160 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of slab and plinth Pump Foundation Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-29 | 2025-10-30 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 161 | Civil | RFI-ELE-CVL-F-D300-CON-0161 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of slab Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-29 | 2025-10-30 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 162 | Civil | RFI-ELE-CVL-F-D300-CON-0162 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal plinth Pump Foundation Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-31 | 2025-11-01 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 163 | Civil | RFI-ELE-CVL-F-D300-CON-0163 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of kerb plinth Pump Foundation Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-03 | 2025-11-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 164 | Civil | RFI-ELE-CVL-F-D300-CON-0164 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of kerb Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-03 | 2025-11-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 165 | Civil | RFI-ELE-CVL-F-D300-CON-0165 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of precast manhole base for D300 at M-One Fabrication Yard | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-03 | 2025-11-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 166 | Civil | RFI-ELE-CVL-F-D300-CON-0166 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pipe support foundation around TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-10 | 2025-11-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 167 | Civil | RFI-ELE-CVL-F-D300-CON-0167 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pipe support foundation around TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-19 | 2025-11-20 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 168 | Civil | RFI-ELE-CVL-F-D300-CON-0168 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean con pipe support foundation around Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-20 | 2025-11-21 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 169 | Civil | RFI-ELE-CVL-F-D300-CON-0169 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pipe support foundation around New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-20 | 2025-11-21 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 170 | Civil | RFI-ELE-CVL-F-D300-CON-0170 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pipe support foundation around Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-21 | 2025-11-22 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 171 | Civil | RFI-ELE-CVL-F-D300-CON-0171 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pipe support pedestal around New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-26 | 2025-11-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 172 | Civil | RFI-ELE-CVL-F-D300-CON-0172 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pipe support pedestal around ACW First Flush Basin | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-26 | 2025-11-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 173 | Civil | RFI-ELE-CVL-F-D300-CON-0173 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pipe support foundation around Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-26 | 2025-11-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 174 | Civil | RFI-ELE-CVL-F-D300-CON-0174 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pipe support pedestal around Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-26 | 2025-11-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 175 | Civil | RFI-ELE-CVL-F-D300-CON-0175 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean concrete pipe support around TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-29 | 2025-12-01 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 176 | Civil | RFI-ELE-CVL-F-D300-CON-0176 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pipe support pedestal around Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-29 | 2025-12-01 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 177 | Civil | RFI-ELE-CVL-F-D300-CON-0177 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pipe support pedestal around New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-29 | 2025-12-01 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 178 | Civil | RFI-ELE-CVL-F-D300-CON-0178 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of Precast Manholes for MS and MA at Fabrication Yard | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-29 | 2025-12-01 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 179 | Civil | RFI-ELE-CVL-F-D300-CON-0179 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pipe support around TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-01 | 2025-12-02 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 180 | Civil | RFI-ELE-CVL-F-D300-CON-0180 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal pipe support around TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-05 | 2025-12-06 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 181 | Civil | RFI-ELE-CVL-F-D300-CON-0181 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pipe support foundation around New Piperack GL J-L/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-05 | 2025-12-06 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 182 | Civil | RFI-ELE-CVL-F-D300-CON-0182 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean con pipe support foundation F1 around New Piperack GL J-L/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-08 | 2025-12-09 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 183 | Civil | RFI-ELE-CVL-F-D300-CON-0183 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean con pipe support foundation F1 and F2 around Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-08 | 2025-12-09 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 184 | Civil | RFI-ELE-CVL-F-D300-CON-0184 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal pipe support foundation around New Piperack GL J-L/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-09 | 2025-12-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 185 | Civil | RFI-ELE-CVL-F-D300-CON-0185 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pipe support foundation F1 around New Piperack GL J-L/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-09 | 2025-12-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 186 | Civil | RFI-ELE-CVL-F-D300-CON-0186 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pipe support foundation F1 and F2 around Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-09 | 2025-12-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 187 | Civil | RFI-ELE-CVL-F-D300-CON-0187 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of Precast Manholes for MA1, MA2, MA3 and MA4 Wall at Fabrication Yard | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-09 | 2025-12-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 188 | Civil | RFI-ELE-CVL-F-D300-CON-0188 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean con for safety shower foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-16 | 2025-12-17 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 189 | Civil | RFI-ELE-CVL-F-D300-CON-0189 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pipe support pedestal F1 and F2 around Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-16 | 2025-12-17 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 190 | Civil | RFI-ELE-CVL-F-D300-CON-0190 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal pipe support foundation around New Piperack GL J-L/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-16 | 2025-12-17 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 191 | Civil | RFI-ELE-CVL-F-D300-CON-0191 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of Precast light pole foundation at D300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-16 | 2025-12-17 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 192 | Civil | RFI-ELE-CVL-F-D300-CON-0192 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pipe support pedestal F1 and F2 around Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-23 | 2025-12-24 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 193 | Civil | RFI-ELE-CVL-F-D300-CON-0193 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of foundation for safety shower foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-23 | 2025-12-24 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 194 | Civil | RFI-ELE-CVL-F-D300-CON-0194 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon for Chemical and Catalyst Storage Shelter ramp | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-30 | 2025-12-31 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 195 | Civil | RFI-ELE-CVL-F-D300-CON-0195 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for Chemical and Catalyst Storage Shelter ramp | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-02 | 2026-01-03 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 196 | Civil | RFI-ELE-CVL-F-D300-CON-0196 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon for Scheduled Waste Storage Building ramp | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-02 | 2026-01-03 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 197 | Civil | RFI-ELE-CVL-F-D300-CON-0197 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of DB foundation AL06 and AL03 at D300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-02 | 2026-01-03 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 198 | Civil | RFI-ELE-CVL-F-D300-CON-0198 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection for Scheduled Waste Storage Building ramp | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-06 | 2026-01-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 199 | Civil | RFI-ELE-CVL-F-D300-CON-0199 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean con pipe support 'F1" around Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-23 | 2026-01-24 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 200 | Civil | RFI-ELE-CVL-F-D300-CON-0200 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pipe support 'F1" around Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-24 | 2026-01-26 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 201 | Civil | RFI-ELE-CVL-F-D300-CON-0201 | External | ELECO | Civil Work | N/A | RC Work | Pour concrete | Inspection of pipe support pedestal 'F1" around Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-27 | 2026-01-28 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing

## 08.RFI_PSC
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-27
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-CVL-F-D300-PSC-0001 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pile plug installation for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-25 | 2024-08-28 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 2 | Civil | RFI-ELE-CVL-F-D300-PSC-0002 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap leancon WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-25 | 2024-08-28 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 3 | Civil | RFI-ELE-CVL-F-D300-PSC-0003 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-03 | 2024-09-05 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 4 | Civil | RFI-ELE-CVL-F-D300-PSC-0004 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-04 | 2024-09-07 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 5 | Civil | RFI-ELE-CVL-F-D300-PSC-0005 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for stump column WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-10 | 2024-09-13 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 6 | Civil | RFI-ELE-CVL-F-D300-PSC-0006 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for groundbeam's leancon WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-17 | 2024-09-19 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 7 | Civil | RFI-ELE-CVL-F-D300-PSC-0007 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pile plug installation for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-20 | 2024-09-23 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 8 | Civil | RFI-ELE-CVL-F-D300-PSC-0008 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap leancon WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-20 | 2024-09-23 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 9 | Civil | RFI-ELE-CVL-F-D300-PSC-0009 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-24 | 2024-09-26 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 10 | Civil | RFI-ELE-CVL-F-D300-PSC-0010 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pile plug installation for Tank TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-28 | 2024-10-01 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 11 | Civil | RFI-ELE-CVL-F-D300-PSC-0011 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for stump column WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-30 | 2024-10-02 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 12 | Civil | RFI-ELE-CVL-F-D300-PSC-0012 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for groundbeam WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-03 | 2024-10-05 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 13 | Civil | RFI-ELE-CVL-F-D300-PSC-0013 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pile plug installation for Tank TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-08 | 2024-10-09 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 14 | Civil | RFI-ELE-CVL-F-D300-PSC-0014 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for groundbeam WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-09 | 2024-10-11 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 15 | Civil | RFI-ELE-CVL-F-D300-PSC-0015 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pile plug installation for Tank TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-11 | 2024-10-12 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 16 | Civil | RFI-ELE-CVL-F-D300-PSC-0016 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation leancon Tank TK - 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-15 | 2024-10-17 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 17 | Civil | RFI-ELE-CVL-F-D300-PSC-0017 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pile plug installation for Tank TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-21 | 2024-10-23 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 18 | Civil | RFI-ELE-CVL-F-D300-PSC-0018 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pile plug installation for Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-21 | 2024-10-23 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 19 | Civil | RFI-ELE-CVL-F-D300-PSC-0019 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap leancon for Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-29 | 2024-10-31 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 20 | Civil | RFI-ELE-CVL-F-D300-PSC-0020 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pile plug installation for Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-29 | 2024-10-31 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 21 | Civil | RFI-ELE-CVL-F-D300-PSC-0021 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap for Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-29 | 2024-10-31 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 22 | Civil | RFI-ELE-CVL-F-D300-PSC-0022 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap leancon for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-29 | 2024-10-31 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 23 | Civil | RFI-ELE-CVL-F-D300-PSC-0023 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pileplug installation for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-29 | 2024-10-31 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 24 | Civil | RFI-ELE-CVL-F-D300-PSC-0024 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap for Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-01 | 2024-11-04 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 25 | Civil | RFI-ELE-CVL-F-D300-PSC-0025 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation installation Tank TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-06 | 2024-11-08 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 26 | Civil | RFI-ELE-CVL-F-D300-PSC-0026 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-06 | 2024-11-08 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 27 | Civil | RFI-ELE-CVL-F-D300-PSC-0027 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pileplug installation for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-06 | 2024-11-08 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 28 | Civil | RFI-ELE-CVL-F-D300-PSC-0028 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation leancon Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-11 | 2024-11-12 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 29 | Civil | RFI-ELE-CVL-F-D300-PSC-0029 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation leancon Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-12 | 2024-11-14 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 30 | Civil | RFI-ELE-CVL-F-D300-PSC-0030 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation Pad footing Piperack GL T/2a-3 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-13 | 2024-11-14 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 31 | Civil | RFI-ELE-CVL-F-D300-PSC-0031 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-15 | 2024-11-18 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 32 | Civil | RFI-ELE-CVL-F-D300-PSC-0032 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation Pad footing Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-15 | 2024-11-18 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 33 | Civil | RFI-ELE-CVL-F-D300-PSC-0033 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation leancon Scheduled Waste Storage Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-07 | 2024-12-09 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 34 | Civil | RFI-ELE-CVL-F-D300-PSC-0034 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation leancon Pump Shelter Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-13 | 2024-12-17 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 35 | Civil | RFI-ELE-CVL-F-D300-PSC-0035 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation leancon Piperack foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-13 | 2024-12-17 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 36 | Civil | RFI-ELE-CVL-F-D300-PSC-0036 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for groundslab leancon Switch Room WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-14 | 2024-12-17 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 37 | Civil | RFI-ELE-CVL-F-D300-PSC-0037 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for piperack pedestal GL O-V/2a -8 at D300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-14 | 2024-12-17 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 38 | Civil | RFI-ELE-CVL-F-D300-PSC-0038 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for leancon prior to slab at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-19 | 2024-12-20 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 39 | Civil | RFI-ELE-CVL-F-D300-PSC-0039 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for leancon prior to foundation surrounding slab TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-19 | 2024-12-21 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 40 | Civil | RFI-ELE-CVL-F-D300-PSC-0040 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pump foundation (3 nos) and 1 nos of Heat Exchanger Foundation at Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-21 | 2024-12-24 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 41 | Civil | RFI-ELE-CVL-F-D300-PSC-0041 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for GL 1/ A-B pilecap for Fire Water Pipe Bridge Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-21 | 2024-12-24 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 42 | Civil | RFI-ELE-CVL-F-D300-PSC-0042 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for leancon for piperack GL M-N/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-24 | 2024-12-25 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 43 | Civil | RFI-ELE-CVL-F-D300-PSC-0043 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for leancon for piperack GL D-H/2-3 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-27 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 44 | Civil | RFI-ELE-CVL-F-D300-PSC-0044 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pileplug for piperack GL M-N/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-27 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 45 | Civil | RFI-ELE-CVL-F-D300-PSC-0045 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for leancon WMB GL B-D/ 5-6 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-27 | 2024-12-29 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 46 | Civil | RFI-ELE-CVL-F-D300-PSC-0046 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for non suspended slab WMB GL A-B/1-6 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-28 | 2024-12-31 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 47 | Civil | RFI-ELE-CVL-F-D300-PSC-0047 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pile cap for piperack GL M-N/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-28 | 2024-12-31 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 48 | Civil | RFI-ELE-CVL-F-D300-PSC-0048 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection pedestal GL 1/A-B Firewater bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-01 | 2025-01-03 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 49 | Civil | RFI-ELE-CVL-F-D300-PSC-0049 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection pedestal GL M-N/3-4 Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-01 | 2025-01-03 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 50 | Civil | RFI-ELE-CVL-F-D300-PSC-0050 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection pedestal GL A/1-3 Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-01 | 2025-01-03 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 51 | Civil | RFI-ELE-CVL-F-D300-PSC-0051 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection pilecap for GL C-H/1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-01 | 2025-01-04 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 52 | Civil | RFI-ELE-CVL-F-D300-PSC-0052 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection leancon for pilecap GL J-L/1-4 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-03 | 2025-01-05 | 18:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 53 | Civil | RFI-ELE-CVL-F-D300-PSC-0053 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for non suspended slab WMB GL A-B/1-6 Second Phase ( GL A-B/ 4-6) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-04 | 2025-01-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 54 | Civil | RFI-ELE-CVL-F-D300-PSC-0054 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for leancon pilecap GL A2-B / 30' - 31' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-06 | 2025-01-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 55 | Civil | RFI-ELE-CVL-F-D300-PSC-0055 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for slab concreting for Tank - 16234 and Bundwall at D300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-07 | 2025-01-09 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 56 | Civil | RFI-ELE-CVL-F-D300-PSC-0056 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pedestal for GL C-H/1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-09 | 2025-01-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 57 | Civil | RFI-ELE-CVL-F-D300-PSC-0057 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for groundslab leancon WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-10 | 2025-01-12 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 58 | Civil | RFI-ELE-CVL-F-D300-PSC-0058 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for groundslab WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-10 | 2025-01-12 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 59 | Civil | RFI-ELE-CVL-F-D300-PSC-0059 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap GL A2-B / 30' - 31' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-16 | 2025-01-18 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 60 | Civil | RFI-ELE-CVL-F-D300-PSC-0060 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for cable trench for switch room at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-22 | 2025-01-24 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 61 | Civil | RFI-ELE-CVL-F-D300-PSC-0061 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for non suspended slab GL A-B/ 5-6 at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-22 | 2025-01-24 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 62 | Civil | RFI-ELE-CVL-F-D300-PSC-0062 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for GroundFloor Slab GL B-D/1-3 at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-24 | 2025-01-26 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 63 | Civil | RFI-ELE-CVL-F-D300-PSC-0063 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Ground Floor to First Floor Column GL A/1-6, GL A-D/5 at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-24 | 2025-01-26 | 9:00 | H | W | N/A | R | Hanis | D300 | Cancelled
| 64 | Civil | RFI-ELE-CVL-F-D300-PSC-0064 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pedestal for GL A1' - A2'/ 29' and GL A-B / 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-25 | 2025-01-28 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 65 | Civil | RFI-ELE-CVL-F-D300-PSC-0065 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Pilecap for GL A1' - A2'/ 27' - 28', GL A1' - A2' / 30' and GL I / 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-25 | 2025-01-28 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 66 | Civil | RFI-ELE-CVL-F-D300-PSC-0066 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for cable trench wall for switch room at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-03 | 2025-02-05 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 67 | Civil | RFI-ELE-CVL-F-D300-PSC-0067 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pedestal for GL A-B / 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-06 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 68 | Civil | RFI-ELE-CVL-F-D300-PSC-0068 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Pilecap for GL J-K/1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-06 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 69 | Civil | RFI-ELE-CVL-F-D300-PSC-0069 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Ground Floor to First Floor Column at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 70 | Civil | RFI-ELE-CVL-F-D300-PSC-0070 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Ground Floor to First Floor Column at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-06 | 2025-02-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 71 | Civil | RFI-ELE-CVL-F-D300-PSC-0071 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pedestal 2nos Heat Exchanger Foundation at Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-06 | 2025-02-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 72 | Civil | RFI-ELE-CVL-F-D300-PSC-0072 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pedestal for GL J-K / 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-07 | 2025-02-09 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 73 | Civil | RFI-ELE-CVL-F-D300-PSC-0073 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Ground Floor to First Floor Column at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-10 | 2025-02-12 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 74 | Civil | RFI-ELE-CVL-F-D300-PSC-0074 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Pilecap for GL A1' - A2' / 30' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-11 | 2025-02-13 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 75 | Civil | RFI-ELE-CVL-F-D300-PSC-0075 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pedestal for GL A1' - A2' / 30' nad J-K/1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-13 | 2025-02-15 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 76 | Civil | RFI-ELE-CVL-F-D300-PSC-0076 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap for GL I / 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-19 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 77 | Civil | RFI-ELE-CVL-F-D300-PSC-0077 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pedestal for Heat Exchanger at Pump Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-19 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 78 | Civil | RFI-ELE-CVL-F-D300-PSC-0078 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pedestal for GL I / 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-19 | 2025-02-21 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 79 | Civil | RFI-ELE-CVL-F-D300-PSC-0079 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean concrete for sump pit at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-24 | 2025-02-26 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 80 | Civil | RFI-ELE-CVL-F-D300-PSC-0080 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for column for GF to 1st Floor GL B/5-6, and D/3,5-6 at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-28 | 2025-03-02 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 81 | Civil | RFI-ELE-CVL-F-D300-PSC-0081 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for bundwall for Product Tank D300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-07 | 2025-03-09 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 82 | Civil | RFI-ELE-CVL-F-D300-PSC-0082 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean concrete for Chemical and Catalyst Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-12 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 83 | Civil | RFI-ELE-CVL-F-D300-PSC-0083 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for concrete for sump pit at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-11 | 2025-03-13 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 84 | Civil | RFI-ELE-CVL-F-D300-PSC-0084 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for concrete for sump pit at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-18 | 2025-03-20 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 85 | Civil | RFI-ELE-CVL-F-D300-PSC-0085 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean concrete for sump pit at Chemical and Catalyst Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-18 | 2025-03-20 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 86 | Civil | RFI-ELE-CVL-F-D300-PSC-0086 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for 1 st Floor Slab at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-25 | 2025-03-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 87 | Civil | RFI-ELE-CVL-F-D300-PSC-0087 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for 1 st Column (12 nos) at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-05 | 2025-04-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 88 | Civil | RFI-ELE-CVL-F-D300-PSC-0088 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for CB2 and CB3 and MA2 Pit at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-07 | 2025-04-09 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 89 | Civil | RFI-ELE-CVL-F-D300-PSC-0089 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean concrete GL A/1-3 for Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 90 | Civil | RFI-ELE-CVL-F-D300-PSC-0090 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for groundfloor slab GL A-B/1-3 for Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-10 | 2025-04-12 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 91 | Civil | RFI-ELE-CVL-F-D300-PSC-0091 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for 1 st Column (6 nos) GL D/1-6 at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-10 | 2025-04-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 92 | Civil | RFI-ELE-CVL-F-D300-PSC-0092 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for base sump pit for CB1 and MA1A for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-14 | 2025-04-16 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 93 | Civil | RFI-ELE-CVL-F-D300-PSC-0093 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for column pedestal GL A-B/1-3 at Scheule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-15 | 2025-04-17 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 94 | Civil | RFI-ELE-CVL-F-D300-PSC-0094 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for leancon staircase landing at Tank 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-21 | 2025-04-23 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 95 | Civil | RFI-ELE-CVL-F-D300-PSC-0095 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for ground beam staircase landing at Tank 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-22 | 2025-04-24 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 96 | Civil | RFI-ELE-CVL-F-D300-PSC-0096 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Sump Pit for CB1 and MA1A for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-23 | 2025-04-25 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 97 | Civil | RFI-ELE-CVL-F-D300-PSC-0097 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for leancon for CB1 and MA1A area for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-29 | 2025-05-01 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 98 | Civil | RFI-ELE-CVL-F-D300-PSC-0098 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for leancon for CB2 base for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-30 | 2025-05-03 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 99 | Civil | RFI-ELE-CVL-F-D300-PSC-0099 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for CB2 base and MA1A Top for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-03 | 2025-05-06 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 100 | Civil | RFI-ELE-CVL-F-D300-PSC-0100 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for roof slab and roof beam for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-05 | 2025-05-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 101 | Civil | RFI-ELE-CVL-F-D300-PSC-0101 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for CB2 wall for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-06 | 2025-05-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 102 | Civil | RFI-ELE-CVL-F-D300-PSC-0102 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean con Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-07 | 2025-05-09 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 103 | Civil | RFI-ELE-CVL-F-D300-PSC-0103 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for slab Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-09 | 2025-05-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 104 | Civil | RFI-ELE-CVL-F-D300-PSC-0104 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for column Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-21 | 2025-05-24 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 105 | Civil | RFI-ELE-CVL-F-D300-PSC-0105 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for South Staircase for TK16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-28 | 2025-05-30 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 106 | Civil | RFI-ELE-CVL-F-D300-PSC-0106 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for bottom Landing beam North Staircase for TK16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-28 | 2025-05-30 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 107 | Civil | RFI-ELE-CVL-F-D300-PSC-0107 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean con ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-31 | 2025-06-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 108 | Civil | RFI-ELE-CVL-F-D300-PSC-0108 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for south roof beam for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-03 | 2025-06-05 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 109 | Civil | RFI-ELE-CVL-F-D300-PSC-0109 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for South Staircase (internal) for TK16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-04 | 2025-06-06 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 110 | Civil | RFI-ELE-CVL-F-D300-PSC-0110 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for base ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-13 | 2025-06-15 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 111 | Civil | RFI-ELE-CVL-F-D300-PSC-0111 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean concrete Groundslab Switchroom at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-16 | 2025-06-18 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 112 | Civil | RFI-ELE-CVL-F-D300-PSC-0112 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Groundslab Switchroom at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-18 | 2025-06-20 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 113 | Civil | RFI-ELE-CVL-F-D300-PSC-0113 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for North Staircase (internal and external) for TK16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-19 | 2025-06-21 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 114 | Civil | RFI-ELE-CVL-F-D300-PSC-0114 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean concrete trench for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-19 | 2025-06-21 | 9:00 | H | W | N/A | R | Hanis | D300 | Cancelled
| 115 | Civil | RFI-ELE-CVL-F-D300-PSC-0115 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean concrete trench for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-23 | 2025-06-25 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 116 | Civil | RFI-ELE-CVL-F-D300-PSC-0116 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for roof beam for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-23 | 2025-06-25 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 117 | Civil | RFI-ELE-CVL-F-D300-PSC-0117 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean con north east Staircase for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-24 | 2025-06-26 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 118 | Civil | RFI-ELE-CVL-F-D300-PSC-0118 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation north east Staircase for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-26 | 2025-06-28 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 119 | Civil | RFI-ELE-CVL-F-D300-PSC-0119 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for base trench and sump pit for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-26 | 2025-06-28 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 120 | Civil | RFI-ELE-CVL-F-D300-PSC-0120 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Wall 1 st Cast ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-26 | 2025-06-28 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 121 | Civil | RFI-ELE-CVL-F-D300-PSC-0121 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for insternal staircase flight for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-27 | 2025-06-29 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 122 | Civil | RFI-ELE-CVL-F-D300-PSC-0122 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Wall 1 st Cast ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-02 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 123 | Civil | RFI-ELE-CVL-F-D300-PSC-0123 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pileplug for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-02 | 2025-07-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 124 | Civil | RFI-ELE-CVL-F-D300-PSC-0124 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for leancon for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-02 | 2025-07-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 125 | Civil | RFI-ELE-CVL-F-D300-PSC-0125 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for trench for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-02 | 2025-07-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 126 | Civil | RFI-ELE-CVL-F-D300-PSC-0126 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for flight north east Staircase for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-08 | 2025-07-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 127 | Civil | RFI-ELE-CVL-F-D300-PSC-0127 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pileplug for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-08 | 2025-07-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 128 | Civil | RFI-ELE-CVL-F-D300-PSC-0128 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for leancon for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-08 | 2025-07-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 129 | Civil | RFI-ELE-CVL-F-D300-PSC-0129 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 130 | Civil | RFI-ELE-CVL-F-D300-PSC-0130 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for trench for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 131 | Civil | RFI-ELE-CVL-F-D300-PSC-0131 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-10 | 2025-07-12 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 132 | Civil | RFI-ELE-CVL-F-D300-PSC-0132 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Wall 2nd Cast ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-12 | 2025-07-15 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 133 | Civil | RFI-ELE-CVL-F-D300-PSC-0133 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-14 | 2025-07-16 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 134 | Civil | RFI-ELE-CVL-F-D300-PSC-0134 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of slab for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-01 | 2025-08-03 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 135 | Civil | RFI-ELE-CVL-F-D300-PSC-0135 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of Lean con for GL J-L/3-4 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-01 | 2025-08-03 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 136 | Civil | RFI-ELE-CVL-F-D300-PSC-0136 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap for GL J-L/3-4 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-02 | 2025-08-05 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 137 | Civil | RFI-ELE-CVL-F-D300-PSC-0137 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal for GL J-L/3-4 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-06 | 2025-08-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 138 | Civil | RFI-ELE-CVL-F-D300-PSC-0138 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-06 | 2025-08-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 139 | Civil | RFI-ELE-CVL-F-D300-PSC-0139 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean con Pipe Support for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-06 | 2025-08-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 140 | Civil | RFI-ELE-CVL-F-D300-PSC-0140 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of foundation Pipe Support for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-12 | 2025-08-14 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 141 | Civil | RFI-ELE-CVL-F-D300-PSC-0141 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Top slab ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-14 | 2025-08-16 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 142 | Civil | RFI-ELE-CVL-F-D300-PSC-0142 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal F4 and F5 Pipe Support for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-19 | 2025-08-21 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 143 | Civil | RFI-ELE-CVL-F-D300-PSC-0143 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for bottom gate valve pit ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-21 | 2025-08-23 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 144 | Civil | RFI-ELE-CVL-F-D300-PSC-0144 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon Pipe support foundation East Side for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-25 | 2025-08-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 145 | Civil | RFI-ELE-CVL-F-D300-PSC-0145 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon CCW Pit S-18242 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-25 | 2025-08-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 146 | Civil | RFI-ELE-CVL-F-D300-PSC-0146 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of base sump CCW Pit S-18242 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-28 | 2025-08-30 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 147 | Civil | RFI-ELE-CVL-F-D300-PSC-0147 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of Pipe support foundation East Side for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-28 | 2025-08-30 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 148 | Civil | RFI-ELE-CVL-F-D300-PSC-0148 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection oh HVAC Power and Control Panel Foundation at Switchroom WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-30 | 2025-09-03 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 149 | Civil | RFI-ELE-CVL-F-D300-PSC-0149 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of Pipe support foundation pedestal East Side for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-05 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 150 | Civil | RFI-ELE-CVL-F-D300-PSC-0150 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for wall gate valve pit ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-05 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 151 | Civil | RFI-ELE-CVL-F-D300-PSC-0151 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for stiffener at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-05 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 152 | Civil | RFI-ELE-CVL-F-D300-PSC-0152 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of 1st cast wall sump CCW Pit S-18242 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-04 | 2025-09-06 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 153 | Civil | RFI-ELE-CVL-F-D300-PSC-0153 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of 2ndt cast wall and top slab sump CCW Pit S-18242 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-12 | 2025-09-14 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 154 | Civil | RFI-ELE-CVL-F-D300-PSC-0154 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon for SP1 and SP2 sump pit at Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-17 | 2025-09-19 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 155 | Civil | RFI-ELE-CVL-F-D300-PSC-0155 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of base for SP1 and SP2 sump pit at Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-22 | 2025-09-24 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 156 | Civil | RFI-ELE-CVL-F-D300-PSC-0156 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of Wall for SP1 and SP2 sump pit at Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-28 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 157 | Civil | RFI-ELE-CVL-F-D300-PSC-0157 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of precast manhole base for MS4, MS4A, MS5, MS5A, MS9, MS9A and MS10 for D300 at M-One Fabrication Yard | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-26 | 2025-09-28 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 158 | Civil | RFI-ELE-CVL-F-D300-PSC-0158 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean concrete for slab Pump Foundation Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-08 | 2025-10-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Cancelled
| 159 | Civil | RFI-ELE-CVL-F-D300-PSC-0159 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean concrete for slab Pump Foundation Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-18 | 2025-10-21 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 160 | Civil | RFI-ELE-CVL-F-D300-PSC-0160 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of slab and plinth Pump Foundation Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-29 | 2025-10-31 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 161 | Civil | RFI-ELE-CVL-F-D300-PSC-0161 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of slab Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-29 | 2025-10-31 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 162 | Civil | RFI-ELE-CVL-F-D300-PSC-0162 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal plinth Pump Foundation Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-31 | 2025-11-02 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 163 | Civil | RFI-ELE-CVL-F-D300-PSC-0163 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of kerb plinth Pump Foundation Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-03 | 2025-11-05 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 164 | Civil | RFI-ELE-CVL-F-D300-PSC-0164 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of kerb Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-03 | 2025-11-05 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 165 | Civil | RFI-ELE-CVL-F-D300-PSC-0165 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of precast manhole base for D300 at M-One Fabrication Yard | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-03 | 2025-11-05 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 166 | Civil | RFI-ELE-CVL-F-D300-PSC-0166 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pipe support foundation around TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-10 | 2025-11-12 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 167 | Civil | RFI-ELE-CVL-F-D300-PSC-0167 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pipe support foundation around TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-19 | 2025-11-21 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 168 | Civil | RFI-ELE-CVL-F-D300-PSC-0168 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean con pipe support foundation around Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-20 | 2025-11-22 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 169 | Civil | RFI-ELE-CVL-F-D300-PSC-0169 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pipe support foundation around New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-20 | 2025-11-22 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 170 | Civil | RFI-ELE-CVL-F-D300-PSC-0170 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pipe support foundation around Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-21 | 2025-11-23 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 171 | Civil | RFI-ELE-CVL-F-D300-PSC-0171 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pipe support pedestal around New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-26 | 2025-11-28 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 172 | Civil | RFI-ELE-CVL-F-D300-PSC-0172 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pipe support pedestal around ACW First Flush Basin | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-26 | 2025-11-28 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 173 | Civil | RFI-ELE-CVL-F-D300-PSC-0173 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pipe support foundation around Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-26 | 2025-11-28 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 174 | Civil | RFI-ELE-CVL-F-D300-PSC-0174 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pipe support pedestal around Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-26 | 2025-11-28 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 175 | Civil | RFI-ELE-CVL-F-D300-PSC-0175 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean concrete pipe support around TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-29 | 2025-12-02 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 176 | Civil | RFI-ELE-CVL-F-D300-PSC-0176 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pipe support pedestal around Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-29 | 2025-12-02 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 177 | Civil | RFI-ELE-CVL-F-D300-PSC-0177 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pipe support pedestal around New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-29 | 2025-12-02 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 178 | Civil | RFI-ELE-CVL-F-D300-PSC-0178 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of Precast Manholes for MS and MA at Fabrication Yard | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-29 | 2025-12-02 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 179 | Civil | RFI-ELE-CVL-F-D300-PSC-0179 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pipe support around TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-01 | 2025-12-03 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 180 | Civil | RFI-ELE-CVL-F-D300-PSC-0180 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal pipe support around TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-05 | 2025-12-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 181 | Civil | RFI-ELE-CVL-F-D300-PSC-0181 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pipe support foundation around New Piperack GL J-L/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-05 | 2025-12-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 182 | Civil | RFI-ELE-CVL-F-D300-PSC-0182 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean con pipe support foundation F1 around New Piperack GL J-L/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-08 | 2025-12-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 183 | Civil | RFI-ELE-CVL-F-D300-PSC-0183 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean con pipe support foundation F1 and F2 around Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-08 | 2025-12-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 184 | Civil | RFI-ELE-CVL-F-D300-PSC-0184 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal pipe support foundation around New Piperack GL J-L/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-09 | 2025-12-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 185 | Civil | RFI-ELE-CVL-F-D300-PSC-0185 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pipe support foundation F1 around New Piperack GL J-L/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-09 | 2025-12-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 186 | Civil | RFI-ELE-CVL-F-D300-PSC-0186 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pipe support foundation F1 and F2 around Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-09 | 2025-12-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 187 | Civil | RFI-ELE-CVL-F-D300-PSC-0187 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of Precast Manholes for MA1, MA2, MA3 and MA4 Wall at Fabrication Yard | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-09 | 2025-12-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 188 | Civil | RFI-ELE-CVL-F-D300-PSC-0188 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean con for safety shower foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-16 | 2025-12-18 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 189 | Civil | RFI-ELE-CVL-F-D300-PSC-0189 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pipe support pedestal F1 and F2 around Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-16 | 2025-12-18 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 190 | Civil | RFI-ELE-CVL-F-D300-PSC-0190 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal pipe support foundation around New Piperack GL J-L/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-16 | 2025-12-18 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 191 | Civil | RFI-ELE-CVL-F-D300-PSC-0191 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of Precast light pole foundation at D300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-16 | 2025-12-18 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 192 | Civil | RFI-ELE-CVL-F-D300-PSC-0192 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pipe support pedestal F1 and F2 around Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-23 | 2025-12-25 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 193 | Civil | RFI-ELE-CVL-F-D300-PSC-0193 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of foundation for safety shower foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-23 | 2025-12-25 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 194 | Civil | RFI-ELE-CVL-F-D300-PSC-0194 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon for Chemical and Catalyst Storage Shelter ramp | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-30 | 2026-01-01 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 195 | Civil | RFI-ELE-CVL-F-D300-PSC-0195 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Chemical and Catalyst Storage Shelter ramp | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-02 | 2026-01-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 196 | Civil | RFI-ELE-CVL-F-D300-PSC-0196 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon for Scheduled Waste Storage Building ramp | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-02 | 2026-01-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 197 | Civil | RFI-ELE-CVL-F-D300-PSC-0197 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of DB foundation AL06 and AL03 at D300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-02 | 2026-01-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 198 | Civil | RFI-ELE-CVL-F-D300-PSC-0198 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Scheduled Waste Storage Building ramp | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-06 | 2026-01-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 199 | Civil | RFI-ELE-CVL-F-D300-PSC-0199 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean con pipe support 'F1" around Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-23 | 2026-01-25 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 200 | Civil | RFI-ELE-CVL-F-D300-PSC-0200 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pipe support 'F1" around Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-24 | 2026-01-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 201 | Civil | RFI-ELE-CVL-F-D300-PSC-0201 | External | ELECO | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pipe support pedestal 'F1" around Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-27 | 2026-01-29 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing

## 09.RFI_ASB
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-27
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-CVL-F-D300-ASB-0001 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for as built survey for stump WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-27 | 2024-09-28 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 2 | Civil | RFI-ELE-CVL-F-D300-ASB-0002 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for as built survey for pilecap WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-27 | 2024-09-28 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 3 | Civil | RFI-ELE-CVL-F-D300-ASB-0003 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for as built survey for groundbeam WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-03 | 2024-10-05 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 4 | Civil | RFI-ELE-CVL-F-D300-ASB-0004 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for as built survey for groundbeam WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-09 | 2024-10-11 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 5 | Civil | RFI-ELE-CVL-F-D300-ASB-0005 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for as built survey for foundation leancon Tank TK - 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-15 | 2024-10-17 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 6 | Civil | RFI-ELE-CVL-F-D300-ASB-0006 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for as built survey for pilecap leancon Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-29 | 2024-10-31 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 7 | Civil | RFI-ELE-CVL-F-D300-ASB-0007 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for as built survey for pilecap Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-29 | 2024-10-31 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 8 | Civil | RFI-ELE-CVL-F-D300-ASB-0008 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for as built survey for pilecap leancon Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-29 | 2024-10-31 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 9 | Civil | RFI-ELE-CVL-F-D300-ASB-0009 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for as built survey for pilecap Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-01 | 2024-11-04 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 10 | Civil | RFI-ELE-CVL-F-D300-ASB-0010 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for as built survey foundation Tank TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-06 | 2024-11-08 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 11 | Civil | RFI-ELE-CVL-F-D300-ASB-0011 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for as built survey for pilecap Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-06 | 2024-11-08 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 12 | Civil | RFI-ELE-CVL-F-D300-ASB-0012 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for as built survey foundation leancon Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-11 | 2024-11-12 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 13 | Civil | RFI-ELE-CVL-F-D300-ASB-0013 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for foundation Pad footing Piperack GL T/2a-3 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-13 | 2024-11-14 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 14 | Civil | RFI-ELE-CVL-F-D300-ASB-0014 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for as built survey for pilecap Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-15 | 2024-11-18 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 15 | Civil | RFI-ELE-CVL-F-D300-ASB-0015 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for foundation Pad footing Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-15 | 2024-11-18 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 16 | Civil | RFI-ELE-CVL-F-D300-ASB-0016 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for asbuilt survey foundation leancon Scheduled Waste Storage Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-07 | 2024-12-09 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 17 | Civil | RFI-ELE-CVL-F-D300-ASB-0017 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for as built survey groundslab leancon Switch Room WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-14 | 2024-12-17 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 18 | Civil | RFI-ELE-CVL-F-D300-ASB-0018 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for piperack pedestal GL O-V/2a -8 at D300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-14 | 2024-12-17 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 19 | Civil | RFI-ELE-CVL-F-D300-ASB-0019 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for leancon prior to slab at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-19 | 2024-12-20 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 20 | Civil | RFI-ELE-CVL-F-D300-ASB-0020 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for leancon prior to foundation surrounding slab TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-19 | 2024-12-21 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 21 | Civil | RFI-ELE-CVL-F-D300-ASB-0021 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for pump foundation (3 nos) and 1 nos of Heat Exchanger Foundation at Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-21 | 2024-12-24 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 22 | Civil | RFI-ELE-CVL-F-D300-ASB-0022 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for GL 1/ A-B pilecap for Fire Water Pipe Bridge Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-21 | 2024-12-24 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 23 | Civil | RFI-ELE-CVL-F-D300-ASB-0023 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for leancon for piperack GL M-N/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-24 | 2024-12-25 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 24 | Civil | RFI-ELE-CVL-F-D300-ASB-0024 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for leancon for piperack GL D-H/2-3 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-27 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 25 | Civil | RFI-ELE-CVL-F-D300-ASB-0025 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for leancon WMB GL B-D/ 5-6 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-27 | 2024-12-29 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 26 | Civil | RFI-ELE-CVL-F-D300-ASB-0026 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for non suspended slab WMB GL A-B/1-6 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-28 | 2024-12-31 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 27 | Civil | RFI-ELE-CVL-F-D300-ASB-0027 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for pile cap for piperack GL M-N/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-28 | 2024-12-31 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 28 | Civil | RFI-ELE-CVL-F-D300-ASB-0028 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection pedestal GL 1/A-B Firewater bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-01 | 2025-01-03 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 29 | Civil | RFI-ELE-CVL-F-D300-ASB-0029 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection pedestal GL M-N/3-4 Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-01 | 2025-01-03 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 30 | Civil | RFI-ELE-CVL-F-D300-ASB-0030 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection pedestal GL A/1-3 Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-01 | 2025-01-03 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 31 | Civil | RFI-ELE-CVL-F-D300-ASB-0031 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection pilecap for GL C-H/1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-02 | 2025-01-04 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 32 | Civil | RFI-ELE-CVL-F-D300-ASB-0032 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection leancon for pilecap GL J-L/1-4 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-03 | 2025-01-05 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 33 | Civil | RFI-ELE-CVL-F-D300-ASB-0033 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for non suspended slab WMB GL A-B/1-6 Second Phase ( GL A-B/ 4-6) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-04 | 2025-01-07 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 34 | Civil | RFI-ELE-CVL-F-D300-ASB-0034 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for leancon pilecap GL A2-B / 30' - 31' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-06 | 2025-01-08 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 35 | Civil | RFI-ELE-CVL-F-D300-ASB-0035 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for slab concreting for Tank - 16234 and Bundwall at D300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-07 | 2025-01-09 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 36 | Civil | RFI-ELE-CVL-F-D300-ASB-0036 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for pedestal for GL C-H/1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-09 | 2025-01-11 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 37 | Civil | RFI-ELE-CVL-F-D300-ASB-0037 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for groundslab leancon WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-10 | 2025-01-12 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 38 | Civil | RFI-ELE-CVL-F-D300-ASB-0038 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for groundslab WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-10 | 2025-01-12 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 39 | Civil | RFI-ELE-CVL-F-D300-ASB-0039 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for pilecap GL A2-B / 30' - 31' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-16 | 2025-01-18 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 40 | Civil | RFI-ELE-CVL-F-D300-ASB-0040 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for cable trench for switch room at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-22 | 2025-01-24 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 41 | Civil | RFI-ELE-CVL-F-D300-ASB-0041 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for non suspended slab GL A-B/ 5-6 at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-22 | 2025-01-24 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 42 | Civil | RFI-ELE-CVL-F-D300-ASB-0042 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for GroundFloor Slab GL B-D/1-3 at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-24 | 2025-01-26 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 43 | Civil | RFI-ELE-CVL-F-D300-ASB-0043 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for Ground Floor to First Floor Column GL A/1-6, GL A-D/5 at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-24 | 2025-01-26 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Cancelled
| 44 | Civil | RFI-ELE-CVL-F-D300-ASB-0044 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for pedestal for GL A1' - A2'/ 29' and GL A-B / 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-25 | 2025-01-28 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 45 | Civil | RFI-ELE-CVL-F-D300-ASB-0045 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for Pilecap for GL A1' - A2'/ 27' - 28', GL A1' - A2' / 30' and GL I / 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-25 | 2025-01-28 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 46 | Civil | RFI-ELE-CVL-F-D300-ASB-0046 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for cable trench wall for switch room at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-03 | 2025-02-05 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 47 | Civil | RFI-ELE-CVL-F-D300-ASB-0047 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for pedestal for GL A-B / 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-06 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 48 | Civil | RFI-ELE-CVL-F-D300-ASB-0048 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for Pilecap for GL J-K/1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-06 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 49 | Civil | RFI-ELE-CVL-F-D300-ASB-0049 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for Ground Floor to First Floor Column at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 50 | Civil | RFI-ELE-CVL-F-D300-ASB-0050 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for Ground Floor to First Floor Column at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-06 | 2025-02-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 51 | Civil | RFI-ELE-CVL-F-D300-ASB-0051 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for pedestal 2nos Heat Exchanger Foundation at Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-06 | 2025-02-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 52 | Civil | RFI-ELE-CVL-F-D300-ASB-0052 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for pedestal for GL J-K / 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-07 | 2025-02-09 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 53 | Civil | RFI-ELE-CVL-F-D300-ASB-0053 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for Ground Floor to First Floor Column at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-10 | 2025-02-12 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 54 | Civil | RFI-ELE-CVL-F-D300-ASB-0054 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for Pilecap for GL A1' - A2' / 30' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-11 | 2025-02-13 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 55 | Civil | RFI-ELE-CVL-F-D300-ASB-0055 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for pedestal for GL A1' - A2' / 30' nad J-K/1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-13 | 2025-02-15 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 56 | Civil | RFI-ELE-CVL-F-D300-ASB-0056 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for pilecap for GL I / 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-19 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 57 | Civil | RFI-ELE-CVL-F-D300-ASB-0057 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for pedestal for Heat Exchanger at Pump Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-19 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 58 | Civil | RFI-ELE-CVL-F-D300-ASB-0058 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for pedestal for GL I / 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-19 | 2025-02-21 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 59 | Civil | RFI-ELE-CVL-F-D300-ASB-0059 | External | Eleco | Civil Work | N/A | Survey work | As Built | Inspection for lean concrete for sump pit at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-24 | 2025-02-26 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 60 | Civil | RFI-ELE-CVL-F-D300-ASB-0060 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for column for GF to 1st Floor GL B/5-6, and D/3,5-6 at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-28 | 2025-03-02 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 61 | Civil | RFI-ELE-CVL-F-D300-ASB-0061 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for bundwall for Product Tank D300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-07 | 2025-03-09 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 62 | Civil | RFI-ELE-CVL-F-D300-ASB-0062 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for lean concrete for Chemical and Catalyst Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-12 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 63 | Civil | RFI-ELE-CVL-F-D300-ASB-0063 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for concrete for sump pit at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-11 | 2025-03-13 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 64 | Civil | RFI-ELE-CVL-F-D300-ASB-0064 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for concrete for sump pit at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-18 | 2025-03-20 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 65 | Civil | RFI-ELE-CVL-F-D300-ASB-0065 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for lean concrete for sump pit at Chemical and Catalyst Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-18 | 2025-03-20 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 66 | Civil | RFI-ELE-CVL-F-D300-ASB-0066 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for 1 st Floor Slab at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-25 | 2025-03-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 67 | Civil | RFI-ELE-CVL-F-D300-ASB-0067 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for 1 st Column (12 nos) GL C-D/1-6 at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-05 | 2025-04-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 68 | Civil | RFI-ELE-CVL-F-D300-ASB-0068 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for CB2 and CB3 and MA2 Pit at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-07 | 2025-04-09 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 69 | Civil | RFI-ELE-CVL-F-D300-ASB-0069 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for lean concrete GL A/1-3 for Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 70 | Civil | RFI-ELE-CVL-F-D300-ASB-0070 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for groundfloor slab GL A-B/1-3 for Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-10 | 2025-04-12 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 71 | Civil | RFI-ELE-CVL-F-D300-ASB-0071 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for 1 st Column (6 nos) GL D/1-6 at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-10 | 2025-04-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 72 | Civil | RFI-ELE-CVL-F-D300-ASB-0072 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for base sump pit for CB1 and MA1A for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-14 | 2025-04-16 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 73 | Civil | RFI-ELE-CVL-F-D300-ASB-0073 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for column pedestal GL A-B/1-3 at Scheule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-15 | 2025-04-17 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 74 | Civil | RFI-ELE-CVL-F-D300-ASB-0074 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for leancon staircase landing at Tank 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-21 | 2025-04-23 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 75 | Civil | RFI-ELE-CVL-F-D300-ASB-0075 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for ground beam staircase landing at Tank 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-22 | 2025-04-24 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 76 | Civil | RFI-ELE-CVL-F-D300-ASB-0076 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for Sump Pit for CB1 and MA1A for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-23 | 2025-04-25 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 77 | Civil | RFI-ELE-CVL-F-D300-ASB-0077 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for leancon for CB1 and MA1A area for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-29 | 2025-05-01 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 78 | Civil | RFI-ELE-CVL-F-D300-ASB-0078 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for leancon for CB2 base for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-30 | 2025-05-03 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 79 | Civil | RFI-ELE-CVL-F-D300-ASB-0079 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for CB2 base and MA1A Top for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-03 | 2025-05-06 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 80 | Civil | RFI-ELE-CVL-F-D300-ASB-0080 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for roof slab and roof beam for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-05 | 2025-05-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 81 | Civil | RFI-ELE-CVL-F-D300-ASB-0081 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for CB2 wall for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-06 | 2025-05-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 82 | Civil | RFI-ELE-CVL-F-D300-ASB-0082 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for lean con Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-07 | 2025-05-09 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 83 | Civil | RFI-ELE-CVL-F-D300-ASB-0083 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for slab Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-09 | 2025-05-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 84 | Civil | RFI-ELE-CVL-F-D300-ASB-0084 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for column Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-21 | 2025-05-24 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 85 | Civil | RFI-ELE-CVL-F-D300-ASB-0085 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for South Staircase for TK16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-28 | 2025-05-30 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 86 | Civil | RFI-ELE-CVL-F-D300-ASB-0086 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for bottom Landing beam North Staircase for TK16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-28 | 2025-05-30 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 87 | Civil | RFI-ELE-CVL-F-D300-ASB-0087 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for lean con ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-31 | 2025-06-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 88 | Civil | RFI-ELE-CVL-F-D300-ASB-0088 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for south lintel beam for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-03 | 2025-06-05 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 89 | Civil | RFI-ELE-CVL-F-D300-ASB-0089 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for South Staircase (internal) for TK16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-04 | 2025-06-06 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 90 | Civil | RFI-ELE-CVL-F-D300-ASB-0090 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for base ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-13 | 2025-06-15 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 91 | Civil | RFI-ELE-CVL-F-D300-ASB-0091 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for lean concrete Groundslab Switchroom at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-16 | 2025-06-18 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 92 | Civil | RFI-ELE-CVL-F-D300-ASB-0092 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for Groundslab Switchroom at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-18 | 2025-06-20 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 93 | Civil | RFI-ELE-CVL-F-D300-ASB-0093 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for North Staircase (internal and external) for TK16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-19 | 2025-06-21 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 94 | Civil | RFI-ELE-CVL-F-D300-ASB-0094 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for lean concrete trench for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-19 | 2025-06-21 | 9:00 | H | W | N/A | R | Hanis | D300 | Cancelled
| 95 | Civil | RFI-ELE-CVL-F-D300-ASB-0095 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for lean concrete trench for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-23 | 2025-06-25 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 96 | Civil | RFI-ELE-CVL-F-D300-ASB-0096 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for roof beam for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-23 | 2025-06-25 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 97 | Civil | RFI-ELE-CVL-F-D300-ASB-0097 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for lean con north east Staircase for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-24 | 2025-06-26 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 98 | Civil | RFI-ELE-CVL-F-D300-ASB-0098 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for foundation north east Staircase for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-26 | 2025-06-28 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 99 | Civil | RFI-ELE-CVL-F-D300-ASB-0099 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for base trench and sump pit for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-26 | 2025-06-28 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 100 | Civil | RFI-ELE-CVL-F-D300-ASB-0100 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for Wall 1 st Cast ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-26 | 2025-06-28 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 101 | Civil | RFI-ELE-CVL-F-D300-ASB-0101 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for internal staircase flight for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-27 | 2025-06-28 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 102 | Civil | RFI-ELE-CVL-F-D300-ASB-0102 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for Wall 1 st Cast ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-02 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 103 | Civil | RFI-ELE-CVL-F-D300-ASB-0103 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for leancon for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-02 | 2025-07-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 104 | Civil | RFI-ELE-CVL-F-D300-ASB-0104 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for trench for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-02 | 2025-07-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Cancelled
| 105 | Civil | RFI-ELE-CVL-F-D300-ASB-0105 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for flight north east Staircase for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-08 | 2025-07-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 106 | Civil | RFI-ELE-CVL-F-D300-ASB-0106 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for leancon for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-08 | 2025-07-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 107 | Civil | RFI-ELE-CVL-F-D300-ASB-0107 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for foundation for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 108 | Civil | RFI-ELE-CVL-F-D300-ASB-0108 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for trench for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 109 | Civil | RFI-ELE-CVL-F-D300-ASB-0109 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for foundation for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-10 | 2025-07-12 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 110 | Civil | RFI-ELE-CVL-F-D300-ASB-0110 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for Wall 2nd Cast ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-12 | 2025-07-15 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 111 | Civil | RFI-ELE-CVL-F-D300-ASB-0111 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pedestal for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-14 | 2025-07-16 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 112 | Civil | RFI-ELE-CVL-F-D300-ASB-0112 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of slab for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-01 | 2025-08-03 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 113 | Civil | RFI-ELE-CVL-F-D300-ASB-0113 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of Lean con for GL J-L/3-4 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-01 | 2025-08-03 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 114 | Civil | RFI-ELE-CVL-F-D300-ASB-0114 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pilecap for GL J-L/3-4 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-02 | 2025-08-05 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 115 | Civil | RFI-ELE-CVL-F-D300-ASB-0115 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pedestal for GL J-L/3-4 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-06 | 2025-08-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 116 | Civil | RFI-ELE-CVL-F-D300-ASB-0116 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pedestal for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-06 | 2025-08-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 117 | Civil | RFI-ELE-CVL-F-D300-ASB-0117 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of lean con Pipe Support for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-06 | 2025-08-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 118 | Civil | RFI-ELE-CVL-F-D300-ASB-0118 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of foundation Pipe Support for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-12 | 2025-08-14 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 119 | Civil | RFI-ELE-CVL-F-D300-ASB-0119 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for Top slab ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-14 | 2025-08-16 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 120 | Civil | RFI-ELE-CVL-F-D300-ASB-0120 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pedestal F4 and F5 Pipe Support for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-19 | 2025-08-21 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 121 | Civil | RFI-ELE-CVL-F-D300-ASB-0121 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for bottom gate valve pit ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-21 | 2025-08-23 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 122 | Civil | RFI-ELE-CVL-F-D300-ASB-0122 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of leancon Pipe support foundation East Side for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-25 | 2025-08-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 123 | Civil | RFI-ELE-CVL-F-D300-ASB-0123 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of leancon CCW Pit S-18242 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-25 | 2025-08-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 124 | Civil | RFI-ELE-CVL-F-D300-ASB-0124 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of base sump CCW Pit S-18242 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-28 | 2025-08-30 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 125 | Civil | RFI-ELE-CVL-F-D300-ASB-0125 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of Pipe support foundation East Side for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-28 | 2025-08-30 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 126 | Civil | RFI-ELE-CVL-F-D300-ASB-0126 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection oh HVAC Power and Control Panel Foundation at Switchroom WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-30 | 2025-09-03 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 127 | Civil | RFI-ELE-CVL-F-D300-ASB-0127 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of Pipe support foundation pedestal East Side for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-05 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 128 | Civil | RFI-ELE-CVL-F-D300-ASB-0128 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for wall gate valve pit ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-05 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 129 | Civil | RFI-ELE-CVL-F-D300-ASB-0129 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for stiffener at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-05 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 130 | Civil | RFI-ELE-CVL-F-D300-ASB-0130 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of 1st cast wall sump CCW Pit S-18242 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-04 | 2025-09-06 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 131 | Civil | RFI-ELE-CVL-F-D300-ASB-0131 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of 2ndt cast wall and top slab sump CCW Pit S-18242 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-12 | 2025-09-14 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 132 | Civil | RFI-ELE-CVL-F-D300-ASB-0132 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of leancon for SP1 and SP2 sump pit at Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-17 | 2025-09-19 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 133 | Civil | RFI-ELE-CVL-F-D300-ASB-0133 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of base for SP1 and SP2 sump pit at Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-22 | 2025-09-24 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 134 | Civil | RFI-ELE-CVL-F-D300-ASB-0134 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of Wall for SP1 and SP2 sump pit at Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-28 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 135 | Civil | RFI-ELE-CVL-F-D300-ASB-0135 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of lean concrete for slab Pump Foundation Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-08 | 2025-10-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Cancelled
| 136 | Civil | RFI-ELE-CVL-F-D300-ASB-0136 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of lean concrete for slab Pump Foundation Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-18 | 2025-10-21 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 137 | Civil | RFI-ELE-CVL-F-D300-ASB-0137 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of slab and plinth Pump Foundation Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-29 | 2025-10-31 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 138 | Civil | RFI-ELE-CVL-F-D300-ASB-0138 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of slab Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-29 | 2025-10-31 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 139 | Civil | RFI-ELE-CVL-F-D300-ASB-0139 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pedestal plinth Pump Foundation Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-31 | 2025-11-02 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 140 | Civil | RFI-ELE-CVL-F-D300-ASB-0140 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of kerb plinth Pump Foundation Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-03 | 2025-11-05 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 141 | Civil | RFI-ELE-CVL-F-D300-ASB-0141 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of kerb Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-03 | 2025-11-05 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 142 | Civil | RFI-ELE-CVL-F-D300-ASB-0142 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pipe support foundation around TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-10 | 2025-11-12 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 143 | Civil | RFI-ELE-CVL-F-D300-ASB-0143 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pipe support foundation around TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-19 | 2025-11-21 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 144 | Civil | RFI-ELE-CVL-F-D300-ASB-0144 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of lean con pipe support foundation around Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-20 | 2025-11-22 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 145 | Civil | RFI-ELE-CVL-F-D300-ASB-0145 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pipe support foundation around New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-20 | 2025-11-22 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 146 | Civil | RFI-ELE-CVL-F-D300-ASB-0146 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pipe support foundation around Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-21 | 2025-11-23 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 147 | Civil | RFI-ELE-CVL-F-D300-ASB-0147 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pipe support pedestal around New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-26 | 2025-11-28 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 148 | Civil | RFI-ELE-CVL-F-D300-ASB-0148 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pipe support pedestal around ACW First Flush Basin | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-26 | 2025-11-28 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 149 | Civil | RFI-ELE-CVL-F-D300-ASB-0149 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pipe support foundation around Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-26 | 2025-11-28 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 150 | Civil | RFI-ELE-CVL-F-D300-ASB-0150 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pipe support pedestal around Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-26 | 2025-11-28 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 151 | Civil | RFI-ELE-CVL-F-D300-ASB-0151 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of lean concrete pipe support around TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-29 | 2025-12-02 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 152 | Civil | RFI-ELE-CVL-F-D300-ASB-0152 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pipe support pedestal around Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-29 | 2025-12-02 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 153 | Civil | RFI-ELE-CVL-F-D300-ASB-0153 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pipe support pedestal around New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-29 | 2025-12-02 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 154 | Civil | RFI-ELE-CVL-F-D300-ASB-0154 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pipe support around TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-01 | 2025-12-03 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 155 | Civil | RFI-ELE-CVL-F-D300-ASB-0155 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pedestal pipe support around TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-05 | 2025-12-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 156 | Civil | RFI-ELE-CVL-F-D300-ASB-0156 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pipe support foundation around New Piperack GL J-L/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-05 | 2025-12-07 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 157 | Civil | RFI-ELE-CVL-F-D300-ASB-0157 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of lean con pipe support foundation F1 around New Piperack GL J-L/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-08 | 2025-12-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 158 | Civil | RFI-ELE-CVL-F-D300-ASB-0158 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of lean con pipe support foundation F1 and F2 around Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-08 | 2025-12-10 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 159 | Civil | RFI-ELE-CVL-F-D300-ASB-0159 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pedestal pipe support foundation around New Piperack GL J-L/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-09 | 2025-12-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 160 | Civil | RFI-ELE-CVL-F-D300-ASB-0160 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pipe support foundation F1 around New Piperack GL J-L/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-09 | 2025-12-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 161 | Civil | RFI-ELE-CVL-F-D300-ASB-0161 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pipe support foundation F1 and F2 around Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-09 | 2025-12-11 | 9:00 | H | W | N/A | R | Hanis | D300 | Accepted
| 162 | Civil | RFI-ELE-CVL-F-D300-ASB-0162 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of lean con for safety shower foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-16 | 2025-12-18 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 163 | Civil | RFI-ELE-CVL-F-D300-ASB-0163 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pipe support pedestal F1 and F2 around Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-16 | 2025-12-18 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 164 | Civil | RFI-ELE-CVL-F-D300-ASB-0164 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pedestal pipe support foundation around New Piperack GL J-L/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-16 | 2025-12-18 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 165 | Civil | RFI-ELE-CVL-F-D300-ASB-0165 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pipe support pedestal F1 and F2 around Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-23 | 2025-12-25 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 166 | Civil | RFI-ELE-CVL-F-D300-ASB-0166 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of lean con for safety shower foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-23 | 2025-12-25 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 167 | Civil | RFI-ELE-CVL-F-D300-ASB-0167 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of leancon for Chemical and Catalyst Storage Shelter ramp | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-30 | 2026-01-01 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 168 | Civil | RFI-ELE-CVL-F-D300-ASB-0168 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for Chemical and Catalyst Storage Shelter ramp | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-02 | 2026-01-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 169 | Civil | RFI-ELE-CVL-F-D300-ASB-0169 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of leancon for Scheduled Waste Storage Building ramp | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-02 | 2026-01-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 170 | Civil | RFI-ELE-CVL-F-D300-ASB-0170 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of DB foundation AL06 and AL03 at D300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-02 | 2026-01-04 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 171 | Civil | RFI-ELE-CVL-F-D300-ASB-0171 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection for Scheduled Waste Storage Building ramp | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-06 | 2026-01-08 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 172 | Civil | RFI-ELE-CVL-F-D300-ASB-0172 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of lean con pipe support 'F1" around Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-23 | 2026-01-25 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 173 | Civil | RFI-ELE-CVL-F-D300-ASB-0173 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pipe support 'F1" around Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-24 | 2026-01-27 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing
| 174 | Civil | RFI-ELE-CVL-F-D300-ASB-0174 | External | ELECO | Civil Work | N/A | RC Work | As Built | Inspection of pipe support pedestal 'F1" around Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-27 | 2026-01-29 | 9:00 | H | W | N/A | R | Hanis | D300 | Ongoing

## 10.RFI_CUB
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-27
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-CVL-W-G-CUB-0001 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G30 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-26 | 2024-08-28 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted | -
| 2 | Civil | RFI-ELE-CVL-W-G-CUB-0002 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G37 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-30 | 2024-09-03 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted | -
| 3 | Civil | RFI-ELE-CVL-W-G-CUB-0003 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G30 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-04 | 2024-09-06 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted | -
| 4 | Civil | RFI-ELE-CVL-W-G-CUB-0004 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G37 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-07 | 2024-09-09 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted | -
| 5 | Civil | RFI-ELE-CVL-W-G-CUB-0005 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G37 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-09 | 2024-09-11 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted | -
| 6 | Civil | RFI-ELE-CVL-W-G-CUB-0006 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G37 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-11 | 2024-09-12 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted | -
| 7 | Civil | RFI-ELE-CVL-W-G-CUB-0007 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G37 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-11 | 2024-09-13 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted | -
| 8 | Civil | RFI-ELE-CVL-W-G-CUB-0008 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G37 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-11 | 2024-09-14 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted | -
| 9 | Civil | RFI-ELE-CVL-W-G-CUB-0009 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G37 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-17 | 2024-09-19 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted | -
| 10 | Civil | RFI-ELE-CVL-W-G-CUB-0010 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G30 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-18 | 2024-09-18 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted | -
| 11 | Civil | RFI-ELE-CVL-W-G-CUB-0011 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G37 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-19 | 2024-09-20 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted | -
| 12 | Civil | RFI-ELE-CVL-W-G-CUB-0012 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G37 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-23 | 2024-09-24 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted | -
| 13 | Civil | RFI-ELE-CVL-W-G-CUB-0013 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G30 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-25 | 2024-09-26 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted | -
| 14 | Civil | RFI-ELE-CVL-W-G-CUB-0014 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G30 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-27 | 2024-09-28 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted | -
| 15 | Civil | RFI-ELE-CVL-W-G-CUB-0015 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G30 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-28 | 2024-09-30 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 16 | Civil | RFI-ELE-CVL-W-G-CUB-0016 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G37 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-28 | 2024-09-30 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 17 | Civil | RFI-ELE-CVL-W-G-CUB-0017 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G37 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-01 | 2024-10-02 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 18 | Civil | RFI-ELE-CVL-W-G-CUB-0018 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G37 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-01 | 2024-10-02 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 19 | Civil | RFI-ELE-CVL-W-G-CUB-0019 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G37 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-01 | 2024-10-02 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 20 | Civil | RFI-ELE-CVL-W-G-CUB-0020 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G37 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-02 | 2024-10-03 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 21 | Civil | RFI-ELE-CVL-W-G-CUB-0021 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G37 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-03 | 2024-10-04 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 22 | Civil | RFI-ELE-CVL-W-G-CUB-0022 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G37 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-03 | 2024-10-04 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 23 | Civil | RFI-ELE-CVL-W-G-CUB-0023 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 9 days epoxy grout at Cast Consult Sdn Bhd | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-04 | 2024-10-05 | 9.00 AM | I/R | W | N/A | W | Hanis | Cast Consult Sdn Bhd | Accepted
| 24 | Civil | RFI-ELE-CVL-W-G-CUB-0024 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G37 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-04 | 2024-10-05 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 25 | Civil | RFI-ELE-CVL-W-G-CUB-0025 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G37 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-07 | 2024-10-08 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 26 | Civil | RFI-ELE-CVL-W-G-CUB-0026 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G37 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-07 | 2024-10-08 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 27 | Civil | RFI-ELE-CVL-W-G-CUB-0027 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G37 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-07 | 2024-10-08 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 28 | Civil | RFI-ELE-CVL-W-G-CUB-0028 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G37 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-09 | 2024-10-10 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 29 | Civil | RFI-ELE-CVL-W-G-CUB-0029 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G37 at Hanson Batching Plant | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-10 | 2024-10-11 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 30 | Civil | RFI-ELE-CVL-W-G-CUB-0030 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G37Pump at Hanson Batching Plant-D300-Groundbeam WMB & pileplug Tank TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-15 | 2024-10-16 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 31 | Civil | RFI-ELE-CVL-W-G-CUB-0031 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G37Pump at Hanson Batching Plant - D300-Groundbeam WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-16 | 2024-10-17 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 32 | Civil | RFI-ELE-CVL-W-G-CUB-0032 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G30 at Hanson Batching Plant - C300-Pileplug WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-18 | 2024-10-19 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 33 | Civil | RFI-ELE-CVL-W-G-CUB-0033 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G30 at Hanson Batching Plant -C300-Pileplug Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-21 | 2024-10-21 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 34 | Civil | RFI-ELE-CVL-W-G-CUB-0034 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G37 at Hanson Batching Plant D-300 WMB Pilecap | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-23 | 2024-10-23 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 35 | Civil | RFI-ELE-CVL-W-G-CUB-0035 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G37 at Hanson Batching Plant -C300 Substation- Pilecap | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-23 | 2024-10-23 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 36 | Civil | RFI-ELE-CVL-W-G-CUB-0036 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G37 at Hanson Batching Plant -C300 Substation- Pilecap | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-25 | 2024-10-25 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 37 | Civil | RFI-ELE-CVL-W-G-CUB-0037 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G37 at Hanson Batching Plant -C300 Substation- Stump | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-28 | 2024-10-29 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 38 | Civil | RFI-ELE-CVL-W-G-CUB-0038 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G37 at Hanson Batching Plant -D300 WMB- Stump | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-28 | 2024-10-29 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 39 | Civil | RFI-ELE-CVL-W-G-CUB-0039 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G37 at Hanson Batching Plant -D300 Tank TK-16234- Pileplug | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-28 | 2024-10-29 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 40 | Civil | RFI-ELE-CVL-W-G-CUB-0040 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G37Pump at Hanson Batching Plant -D300 Piperack- Pileplug | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-28 | 2024-10-29 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 41 | Civil | RFI-ELE-CVL-W-G-CUB-0041 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G37Pump at Hanson Batching Plant -D300 Tank TK-16234- Pileplug | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-28 | 2024-10-29 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 42 | Civil | RFI-ELE-CVL-W-G-CUB-0042 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G37Pump at Hanson Batching Plant -C300 Substation- Groundbeam | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-28 | 2024-10-29 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 43 | Civil | RFI-ELE-CVL-W-G-CUB-0043 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G37Pump at Hanson Batching Plant -C300 Substation- Groundbeam | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-28 | 2024-10-30 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 44 | Civil | RFI-ELE-CVL-W-G-CUB-0044 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days epoxy grout at Cast Consult Sdn Bhd | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-28 | 2024-10-30 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 45 | Civil | RFI-ELE-CVL-W-G-CUB-0045 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G37Pump at Hanson Batching Plant -D300 TK-16234- Pileplug | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-05 | 2024-11-06 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 46 | Civil | RFI-ELE-CVL-W-G-CUB-0046 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G37Pump at Hanson Batching Plant -D300 WMB- Groundbeam | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-05 | 2024-11-06 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 47 | Civil | RFI-ELE-CVL-W-G-CUB-0047 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G37Pump at Hanson Batching Plant -D300 WMB- Groundbeam | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-05 | 2024-11-07 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 48 | Civil | RFI-ELE-CVL-W-G-CUB-0048 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G30 at Hanson Batching Plant -D300 Piperack- Pileplug | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-05 | 2024-11-06 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 49 | Civil | RFI-ELE-CVL-W-G-CUB-0049 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G30 at Hanson Batching Plant -D300 Piperack- Pilecap | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-05 | 2024-11-06 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 50 | Civil | RFI-ELE-CVL-W-G-CUB-0050 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G30 at Hanson Batching Plant -D300 Piperack- Pilecap | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-11 | 2024-11-11 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 51 | Civil | RFI-ELE-CVL-W-G-CUB-0051 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G30 at Hanson Batching Plant -D300 Truck Loading- Pileplug | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-11 | 2024-11-11 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 52 | Civil | RFI-ELE-CVL-W-G-CUB-0052 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G30Pump at Hanson Batching Plant -D300 TK-16234- Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-13 | 2024-11-14 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 53 | Civil | RFI-ELE-CVL-W-G-CUB-0053 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G30 at Hanson Batching Plant -D300 Truck Loading- Pilecap | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-18 | 2024-11-18 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 54 | Civil | RFI-ELE-CVL-W-G-CUB-0054 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G37Pump at Hanson Batching Plant -D300 Piperack- Pileplug | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-18 | 2024-11-19 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 55 | Civil | RFI-ELE-CVL-W-G-CUB-0055 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G37Pump at Hanson Batching Plant -D300-Tank TK-16234- Pileplug | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-18 | 2024-11-19 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 56 | Civil | RFI-ELE-CVL-W-G-CUB-0056 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G37Pump at Hanson Batching Plant -C300 Substation- Groundbeam | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-18 | 2024-11-19 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 57 | Civil | RFI-ELE-CVL-W-G-CUB-0057 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G37Pump at Hanson Batching Plant -C300 Substation- Groundbeam | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-19 | 2024-11-20 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 58 | Civil | RFI-ELE-CVL-W-G-CUB-0058 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G30 at Hanson Batching Plant -C300 PC16 MAN Refiner- Pileplug | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-19 | 2024-11-20 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 59 | Civil | RFI-ELE-CVL-W-G-CUB-0059 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G30 at Hanson Batching Plant -D300 Piperack- Pad Footing | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-19 | 2024-11-20 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 60 | Civil | RFI-ELE-CVL-W-G-CUB-0060 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G30 at Hanson Batching Plant -D300 Truck Loading- Pileplug | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-19 | 2024-11-20 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 61 | Civil | RFI-ELE-CVL-W-G-CUB-0061 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G30 at Hanson Batching Plant -D300 Truck Loading- Pilecap | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-23 | 2024-11-23 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 62 | Civil | RFI-ELE-CVL-W-G-CUB-0062 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G30 at Hanson Batching Plant -D300 Piperack- Pad footing | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-23 | 2024-11-23 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 63 | Civil | RFI-ELE-CVL-W-G-CUB-0063 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G30 at Hanson Batching Plant -C300 MAN Refiner- Pileplug | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-23 | 2024-11-23 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 64 | Civil | RFI-ELE-CVL-W-G-CUB-0064 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G30 at Hanson Batching Plant -D300 Piperack- Pilecap | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-26 | 2024-11-27 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 65 | Civil | RFI-ELE-CVL-W-G-CUB-0065 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G30 at Hanson Batching Plant -D300 Piperack- Pileplug | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-26 | 2024-11-27 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 66 | Civil | RFI-ELE-CVL-W-G-CUB-0066 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G37 at Hanson Batching Plant -C300 PC16 MAN Refiner- Pilecap PC16 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-26 | 2024-11-27 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 67 | Civil | RFI-ELE-CVL-W-G-CUB-0067 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G37 at Hanson Batching Plant -C300 PC16 MAN Refiner- Pileplug | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-26 | 2024-11-27 | 9.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 68 | Civil | RFI-ELE-CVL-W-G-CUB-0068 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G30 at Hanson Batching Plant -D300 Piperack- Pilecap | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-02 | 2024-12-02 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 69 | Civil | RFI-ELE-CVL-W-G-CUB-0069 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G30 at Hanson Batching Plant -D300 Truck Loading- Pileplug | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-02 | 2024-12-02 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 70 | Civil | RFI-ELE-CVL-W-G-CUB-0070 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G30 at Hanson Batching Plant -C300 MAN Refiner- Pilecap | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-02 | 2024-12-02 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 71 | Civil | RFI-ELE-CVL-W-G-CUB-0071 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G30 at Hanson Batching Plant -C300 MAN Refiner- Pileplug | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-02 | 2024-12-02 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 72 | Civil | RFI-ELE-CVL-W-G-CUB-0072 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G30 at Hanson Batching Plant -C300 Substation EDG&Transformer- Pileplug | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-02 | 2024-12-02 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 73 | Civil | RFI-ELE-CVL-W-G-CUB-0073 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 3 days G37 at Hanson Batching Plant -C300 MAN Refiner- Pilecap PC16 top | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-02 | 2024-12-03 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 74 | Civil | RFI-ELE-CVL-W-G-CUB-0074 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G30P at Hanson Batching Plant -D300 Tank TK-16234- Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-05 | 2024-12-05 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 75 | Civil | RFI-ELE-CVL-W-G-CUB-0075 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G37 at Hanson Batching Plant -C300 MAN Refiner- Pilecap PC 16 top | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-07 | 2024-12-07 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 76 | Civil | RFI-ELE-CVL-W-G-CUB-0076 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G30 at Hanson Batching Plant -D300 Truck Loading- Pilecap | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-07 | 2024-12-09 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 77 | Civil | RFI-ELE-CVL-W-G-CUB-0077 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G30 at Hanson Batching Plant -C300 MAN Refiner - Pilecap | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-07 | 2024-12-09 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 78 | Civil | RFI-ELE-CVL-W-G-CUB-0078 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 8 days G37 at Hanson Batching Plant -C300 Substation - Groundslab | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-11 | 2024-12-11 | 4.00 PM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 79 | Civil | RFI-ELE-CVL-W-G-CUB-0079 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G30 at Hanson Batching Plant -C300 MAN Refiner - Pileplug PC16 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-11 | 2024-12-11 | 4.00 PM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 80 | Civil | RFI-ELE-CVL-W-G-CUB-0080 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G30 at Hanson Batching Plant -D300 Piperack - Pad footing | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-11 | 2024-12-11 | 4.00 PM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 81 | Civil | RFI-ELE-CVL-W-G-CUB-0081 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G30 at Hanson Batching Plant -D300 Truck Loading - Pileplug | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-11 | 2024-12-11 | 4.00 PM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 82 | Civil | RFI-ELE-CVL-W-G-CUB-0082 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 2 days G37 at Hanson Batching Plant -C300 Man refiner PC4c and PC4d - Pilecap | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-13 | 2024-12-13 | 4.00 PM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 83 | Civil | RFI-ELE-CVL-W-G-CUB-0083 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 8 days G37 at Hanson Batching Plant -C300 Substation - Groundbeam | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-14 | 2024-12-14 | 4.00 PM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 84 | Civil | RFI-ELE-CVL-W-G-CUB-0084 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G30 at Hanson Batching Plant -D300 Truck Loading - Pilecap | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-14 | 2024-12-14 | 4.00 PM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 85 | Civil | RFI-ELE-CVL-W-G-CUB-0085 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G30 at Hanson Batching Plant -D300 Piperack - Pad footing | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-14 | 2024-12-14 | 4.00 PM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 86 | Civil | RFI-ELE-CVL-W-G-CUB-0086 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G30 at Hanson Batching Plant -C300 Man Refiner - Pileplug | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-14 | 2024-12-14 | 4.00 PM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 87 | Civil | RFI-ELE-CVL-W-G-CUB-0087 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 3 days G37 at Hanson Batching Plant -C300 Man refiner PC4c top, PC4d top , PC8 - Pilecap | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-14 | 2024-12-16 | 4.00 PM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 88 | Civil | RFI-ELE-CVL-W-G-CUB-0088 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G30P at Hanson Batching Plant -C300 Substation - Column GF to 1F GL A-D/2-3 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-17 | 2024-12-17 | 4.00 PM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 89 | Civil | RFI-ELE-CVL-W-G-CUB-0089 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 29days G37 at Hanson Batching Plant - C300 Man Refiner - PC16 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-19 | 2024-12-19 | 4.00 PM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 90 | Civil | RFI-ELE-CVL-W-G-CUB-0090 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 29days G37 at Hanson Batching Plant - C300 Man Refiner - PilePlug | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-19 | 2024-12-19 | 4.00 PM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 91 | Civil | RFI-ELE-CVL-W-G-CUB-0091 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 8days G37 at Hanson Batching Plant - C300 Man Refiner - PC4c and PC4d | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-19 | 2024-12-19 | 4.00 PM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 92 | Civil | RFI-ELE-CVL-W-G-CUB-0092 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 8days G37 at Hanson Batching Plant - C300 Man Refiner - PilePlug | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-19 | 2024-12-19 | 4.00 PM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 93 | Civil | RFI-ELE-CVL-W-G-CUB-0093 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G30P at Hanson Batching Plant -C300 Substation - EDG Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-20 | 2024-12-21 | 9:00 | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 94 | Civil | RFI-ELE-CVL-W-G-CUB-0094 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G30 at Hanson Batching Plant -C300 MAN Refiner- Pilecap | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-21 | 2024-12-23 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 95 | Civil | RFI-ELE-CVL-W-G-CUB-0095 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G30 at Hanson Batching Plant -C300 MAN Refiner- Pileplug | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-21 | 2024-12-23 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 96 | Civil | RFI-ELE-CVL-W-G-CUB-0096 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G30 at Hanson Batching Plant -C300 Substation EDG&Transformer- Pileplug | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-21 | 2024-12-23 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 97 | Civil | RFI-ELE-CVL-W-G-CUB-0097 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 7 days G30 at Hanson Batching Plant -Pedestal around Tank TK 16234- 23 nos | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-23 | 2024-12-24 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 98 | Civil | RFI-ELE-CVL-W-G-CUB-0098 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection of Cube Testing 28 days G37 at Hanson Batching Plant -C300 Substation - Groundslab | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-30 | 2024-12-31 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 99 | Civil | RFI-ELE-CVL-W-G-CUB-0099 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 14days G30 at LCS-C300 Man Refiner-Pileplug | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-01 | 2025-01-02 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS Plant | Accepted
| 100 | Civil | RFI-ELE-CVL-W-G-CUB-0100 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7days G30 for pilecap PC5 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-03 | 2025-01-04 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS Plant | Accepted
| 101 | Civil | RFI-ELE-CVL-W-G-CUB-0101 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7days G30 for pedestal PC2/PS, PC2a/PS and PC2b/PS Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-03 | 2025-01-04 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS Plant | Accepted
| 102 | Civil | RFI-ELE-CVL-W-G-CUB-0102 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7days G30 for pileplug PC8b and PC4/C1 GL D1 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-03 | 2025-01-04 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS Plant | Accepted
| 103 | Civil | RFI-ELE-CVL-W-G-CUB-0103 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7days G30 for pilecap GL N-O/2-3 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-04 | 2025-01-06 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS Plant | Accepted
| 104 | Civil | RFI-ELE-CVL-W-G-CUB-0104 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7days G30 for pedestal PC2/PS, PC2a/PS, PC2b/PS at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-04 | 2025-01-06 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS Plant | Accepted
| 105 | Civil | RFI-ELE-CVL-W-G-CUB-0105 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7days G30 for pilecap PC5/C1 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-04 | 2025-01-06 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS Plant | Accepted
| 106 | Civil | RFI-ELE-CVL-W-G-CUB-0106 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7days G30 for pileplug for pilecap PC 8b and PC4/C1 (2 nos) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-04 | 2025-01-06 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS Plant | Accepted
| 107 | Civil | RFI-ELE-CVL-W-G-CUB-0107 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7days G30 for non suspended slab WMB GL A-B/1-6 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-09 | 2025-01-09 | 4.00 PM | I/R | W | N/A | W | Hanis | LCS Plant | Accepted
| 108 | Civil | RFI-ELE-CVL-W-G-CUB-0108 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7days G30 for pileplug PC5a, PC22, and PC6 Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-22 | 2025-01-23 | 4.00 PM | I/R | W | N/A | W | Hanis | LCS Plant | Accepted
| 109 | Civil | RFI-ELE-CVL-W-G-CUB-0109 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28days G30 for pilecap PC4 and PC6b Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-22 | 2025-01-23 | 4.00 PM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 110 | Civil | RFI-ELE-CVL-W-G-CUB-0110 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28days G30 for pileplug PC2/PS, PC2a/PS and PC2b/C1 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-22 | 2025-01-23 | 4.00 PM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 111 | Civil | RFI-ELE-CVL-W-G-CUB-0111 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28days G30 for pedestal PC11, PC8, PC6a and PC2b/PS Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-22 | 2025-01-23 | 4.00 PM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 112 | Civil | RFI-ELE-CVL-W-G-CUB-0112 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28days G30 for pileplug TK 18203 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-22 | 2025-01-23 | 4.00 PM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 113 | Civil | RFI-ELE-CVL-W-G-CUB-0113 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7days G30 for pilecap GL A2-B / 30' - 31' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-24 | 2025-01-25 | 4.00 PM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 114 | Civil | RFI-ELE-CVL-W-G-CUB-0114 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28days G30 for pilecap PC5 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-24 | 2025-01-25 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS Plant | Accepted
| 115 | Civil | RFI-ELE-CVL-W-G-CUB-0115 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28days G30 for pedestal PC2/PS, PC2a/PS and PC2b/PS Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-24 | 2025-01-25 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS Plant | Accepted
| 116 | Civil | RFI-ELE-CVL-W-G-CUB-0116 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28days G30 for pileplug PC8b and PC4/C1 GL D1 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-24 | 2025-01-25 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS Plant | Accepted
| 117 | Civil | RFI-ELE-CVL-W-G-CUB-0117 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28days G30 for pilecap GL N-O/2-3 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-25 | 2025-01-27 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS Plant | Accepted
| 118 | Civil | RFI-ELE-CVL-W-G-CUB-0118 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28days G30 for pedestal PC2/PS, PC2a/PS, PC2b/PS at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-25 | 2025-01-27 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 119 | Civil | RFI-ELE-CVL-W-G-CUB-0119 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28days G30 for pilecap PC5/C1 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-25 | 2025-01-27 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 120 | Civil | RFI-ELE-CVL-W-G-CUB-0120 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7days G30 for Column WMB GroundFloor to 1st Floor 8 nos | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-18 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 121 | Civil | RFI-ELE-CVL-W-G-CUB-0121 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7days G30 for PC3/C2 GL C/9, Pileplug PC7a/C1 and PC6b/C1 GL B/5-6 and pedestal PC4/C2 GL C/8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-25 | 2025-02-26 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 122 | Civil | RFI-ELE-CVL-W-G-CUB-0122 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7days G30 for pilecap Z-19208A Weighing Machines and Silo Foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-25 | 2025-02-26 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 123 | Civil | RFI-ELE-CVL-W-G-CUB-0123 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7days G30 for pilecap for GL I / 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-25 | 2025-02-26 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 124 | Civil | RFI-ELE-CVL-W-G-CUB-0124 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7days G30 for pedestal for Heat Exchanger at Pump Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-25 | 2025-02-26 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 125 | Civil | RFI-ELE-CVL-W-G-CUB-0125 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28days G30 for slab and beam 1st floor for Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-25 | 2025-02-26 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 126 | Civil | RFI-ELE-CVL-W-G-CUB-0126 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28days G30 for pilecap PC6 and PC5a at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-25 | 2025-02-26 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 127 | Civil | RFI-ELE-CVL-W-G-CUB-0127 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28days G30 for pilecap D-2806 at Esstar Vision Compound | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-25 | 2025-02-26 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 128 | Civil | RFI-ELE-CVL-W-G-CUB-0128 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28days G30 for pedestal PC24 (free saddle) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-25 | 2025-02-26 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 129 | Civil | RFI-ELE-CVL-W-G-CUB-0129 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7days G30 for pilecap PC6b and PC6d GL B/6-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-27 | 2025-02-28 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 130 | Civil | RFI-ELE-CVL-W-G-CUB-0130 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7days G30 for pedestal for GL I / 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-27 | 2025-02-28 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 131 | Civil | RFI-ELE-CVL-W-G-CUB-0131 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7days G30 for pilecap PC7a/C1 GL B/5 , pedestal PC3/C2 GL C/9 and pileplug PC3/C2 GL C/10 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-27 | 2025-02-28 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 132 | Civil | RFI-ELE-CVL-W-G-CUB-0132 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7days G30 for roof slab GL A-D/ 4-8 and roof beam GL A-D/1x-1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-01 | 2025-03-03 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 133 | Civil | RFI-ELE-CVL-W-G-CUB-0133 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28days G30 for GL A-D/4-8 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-01 | 2025-03-03 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 134 | Civil | RFI-ELE-CVL-W-G-CUB-0134 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7days G30 for ground beam GL A-C/ 1-5 for Briquetting Building (LCS) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-05 | 2025-03-06 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 135 | Civil | RFI-ELE-CVL-W-G-CUB-0135 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7days G30 for pilecap PC3/C2 GL C/10 at Briquetting Building (LCS) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-05 | 2025-03-06 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 136 | Civil | RFI-ELE-CVL-W-G-CUB-0136 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7days G30 for pileplug for PC4/C2 (2 nos) GL C/11-12, Z-19208B, Z-19240 Equipment foundation at Briquetting Building (LCS) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-05 | 2025-03-06 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 137 | Civil | RFI-ELE-CVL-W-G-CUB-0137 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7days G30 for foundation pilecap Z-19208B & D-19220 at Briquetting Building (HANSON) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-05 | 2025-03-06 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 138 | Civil | RFI-ELE-CVL-W-G-CUB-0138 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28days G30 for cable trench wall for switch room at WMB (HANSON) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-05 | 2025-03-06 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 139 | Civil | RFI-ELE-CVL-W-G-CUB-0139 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28days G30 for GroundFloor Slab GL B-D/1-3 at WMB (HANSON) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-05 | 2025-03-06 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 140 | Civil | RFI-ELE-CVL-W-G-CUB-0140 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28days G30 for stump column at Briquetting Building (HANSON) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-05 | 2025-03-06 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 141 | Civil | RFI-ELE-CVL-W-G-CUB-0141 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28days G30 for pilecap PC6/C1, PC6c/C1 and PC6a/C1 GL A-B/3-4 at Briquetting Building (HANSON) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-05 | 2025-03-06 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 142 | Civil | RFI-ELE-CVL-W-G-CUB-0142 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for pileplug at Briquetting Building (HANSON) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-05 | 2025-03-06 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 143 | Civil | RFI-ELE-CVL-W-G-CUB-0143 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for pilecap GL A1' -A2'/ 27-29 at New Piperack (HANSON) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-05 | 2025-03-06 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 144 | Civil | RFI-ELE-CVL-W-G-CUB-0144 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for column 1st-RL GL B-D/2-3 at Substation C2105 (HANSON) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-05 | 2025-03-06 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 145 | Civil | RFI-ELE-CVL-W-G-CUB-0145 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for Ground Floor to First Floor Column at WMB (HANSON) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-05 | 2025-03-06 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 146 | Civil | RFI-ELE-CVL-W-G-CUB-0146 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for Pilecap and Briquetting at Briquetting Building (LCS) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-11 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 147 | Civil | RFI-ELE-CVL-W-G-CUB-0147 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for raft foundation Battery Room at Substation C2105 (LCS) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-11 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 148 | Civil | RFI-ELE-CVL-W-G-CUB-0148 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for PC8/C1 and Pileplug PC4/C2 at Briquetting Building (LCS) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-11 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 149 | Civil | RFI-ELE-CVL-W-G-CUB-0149 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for column 1st-RL at Substation C2105 (HANSON) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-11 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 150 | Civil | RFI-ELE-CVL-W-G-CUB-0150 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for Ground Floor to First Floor Column at WMB (LCS) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-11 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 151 | Civil | RFI-ELE-CVL-W-G-CUB-0151 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 days G30 for ground beam GL A-C/ 1-5 for Briquetting Building (HANSON) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-11 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 152 | Civil | RFI-ELE-CVL-W-G-CUB-0152 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 days G30 for PC4/C2 (2 nos) GL C/11-12 ,PC4/C2 GL A/12, pilepug for PC6/C1 and PC7/C1 GL A/5-6, and Z-19208C at Briquetting Building (HANSON) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-11 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 153 | Civil | RFI-ELE-CVL-W-G-CUB-0153 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 days G30 for roof slab GL A-D/1-4 for Substation C2105 (LCS) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-11 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 154 | Civil | RFI-ELE-CVL-W-G-CUB-0154 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 days G30 for column for GF to 1st Floor GL B/5-6, and D/3,5-6 at WMB (LCS) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-11 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 155 | Civil | RFI-ELE-CVL-W-G-CUB-0155 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for Pilecap, Pileplug, and Pedestal at Briquetting Building (Hanson) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-21 | 2025-03-22 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 156 | Civil | RFI-ELE-CVL-W-G-CUB-0156 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for Pilecap, Pedestal at New Piperack (Hanson) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-21 | 2025-03-22 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 157 | Civil | RFI-ELE-CVL-W-G-CUB-0157 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for foundation weighing station at Briquetting Building (LCS) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-21 | 2025-03-22 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 158 | Civil | RFI-ELE-CVL-W-G-CUB-0158 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 days G30 for fascia GL 4-8 (LCS) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-21 | 2025-03-22 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 159 | Civil | RFI-ELE-CVL-W-G-CUB-0159 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 days G30 for foundation, groundbeam, pedestal at Briquetting Building (LCS) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-21 | 2025-03-22 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 160 | Civil | RFI-ELE-CVL-W-G-CUB-0160 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for column for GF to 1st Floor GL B/5-6, and D/3,5-6 at WMB (LCS) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 161 | Civil | RFI-ELE-CVL-W-G-CUB-0161 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for 7 days G30 for bundwall for Product Tank D300 (LCS) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 162 | Civil | RFI-ELE-CVL-W-G-CUB-0162 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for roof slab GL A-D/1-4 for Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 163 | Civil | RFI-ELE-CVL-W-G-CUB-0163 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for pile cap PC6/C1 GL A/4-5 and Z-19208C at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 164 | Civil | RFI-ELE-CVL-W-G-CUB-0164 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for groundbeam GL C/4-9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 165 | Civil | RFI-ELE-CVL-W-G-CUB-0165 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for lean con PC3/C2 (2nos) GL A/9-10 and PC4/C2 (2nos) GL A/11 and B/12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 166 | Civil | RFI-ELE-CVL-W-G-CUB-0166 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for pileplug PC3/C2 (2nos) GL A/9-10 and PC4/C2 (2nos) GL A/11 and B/12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 167 | Civil | RFI-ELE-CVL-W-G-CUB-0167 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for cube testing 28 days G30 for pedestal PC5a, PC6a, PC6, PC7a, PC6b, and PC6d GL B/2-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 168 | Civil | RFI-ELE-CVL-W-G-CUB-0168 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for pilecap PC4/C2 (2 nos), PC3/C2 (2 nos) GL A/8-11 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 169 | Civil | RFI-ELE-CVL-W-G-CUB-0169 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for Pedestal 2nd cast PC5/C1 GL B/1, PC6/C1 (3 nos), PC6a/C1 (2 nos), PC7/C1 (2 nos) and PC4/C2 GL A/1-8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 170 | Civil | RFI-ELE-CVL-W-G-CUB-0170 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for groundbeam GL A/1-4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 171 | Civil | RFI-ELE-CVL-W-G-CUB-0171 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for pedestal PC3/C2 and PC4/C2 (2nos) GL C/10-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 172 | Civil | RFI-ELE-CVL-W-G-CUB-0172 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for pilecap PC4/C2 GL B/12, PC7/C1 GL A/6 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 173 | Civil | RFI-ELE-CVL-W-G-CUB-0173 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for pileplug PC4/C2 GL A/8, PC3/C2 GL A/9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 174 | Civil | RFI-ELE-CVL-W-G-CUB-0174 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for Pump Foundation P-18201A and P-18201B at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 175 | Civil | RFI-ELE-CVL-W-G-CUB-0175 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for lean concrete and pile plug Stretch Hood Device and ground beam GL A 4-6 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 176 | Civil | RFI-ELE-CVL-W-G-CUB-0176 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for pilecap foundation Stretch Hood Device at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 177 | Civil | RFI-ELE-CVL-W-G-CUB-0177 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for pilecap foundation D-19220 Foundation Melt Tank at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 178 | Civil | RFI-ELE-CVL-W-G-CUB-0178 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for groundbeam GL A/4-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 179 | Civil | RFI-ELE-CVL-W-G-CUB-0179 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for 2nd cast pedestal PC6/C1 (2nos) and PC6a/C1 GL A/1-4 Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 180 | Civil | RFI-ELE-CVL-W-G-CUB-0180 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for pedestal PC4/C2 (4nos) and PC3/C2 (3nos) GL A-B/8-12 Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 181 | Civil | RFI-ELE-CVL-W-G-CUB-0181 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for cast fascia GL A-D/ 4-8 at roof floor Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 182 | Civil | RFI-ELE-CVL-W-G-CUB-0182 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for pedestal for PC6a/C1 and PC6/C1 GL A/4-5 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 183 | Civil | RFI-ELE-CVL-W-G-CUB-0183 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for groundbeam for GL A-C/8 -12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-10 | 2025-04-11 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 184 | Civil | RFI-ELE-CVL-W-G-CUB-0184 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for foundation Stretch Hood Device GL A/8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-10 | 2025-04-11 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 185 | Civil | RFI-ELE-CVL-W-G-CUB-0185 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 days G30 for 1 st Column (12 nos) at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-14 | 2025-04-15 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 186 | Civil | RFI-ELE-CVL-W-G-CUB-0186 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 days G30 for CB2 and CB3 and MA2 Pit at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-14 | 2025-04-15 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 187 | Civil | RFI-ELE-CVL-W-G-CUB-0187 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for pedestal for PC3/C2 (2 nos) and PC4/C2 (3 nos) GL B-C/9-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-14 | 2025-04-15 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 188 | Civil | RFI-ELE-CVL-W-G-CUB-0188 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for pedestal foundation D-19220 Foundation Melt Tank at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-14 | 2025-04-15 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 189 | Civil | RFI-ELE-CVL-W-G-CUB-0189 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for pileplug for PC7/C1 GL A/7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-14 | 2025-04-15 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 190 | Civil | RFI-ELE-CVL-W-G-CUB-0190 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for cast fascia GL A-D/ 4at roof floor Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-14 | 2025-04-15 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 191 | Civil | RFI-ELE-CVL-W-G-CUB-0191 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for pedestal for PC3/C2 (2 nos) and PC4/C2 (3 nos) GL A-B/9-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-14 | 2025-04-15 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 192 | Civil | RFI-ELE-CVL-W-G-CUB-0192 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for pilecap for PC7/C1 GL A/7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-14 | 2025-04-15 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 193 | Civil | RFI-ELE-CVL-W-G-CUB-0193 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for sump pit at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-15 | 2025-04-16 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 194 | Civil | RFI-ELE-CVL-W-G-CUB-0194 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 pedestal for PC7/C1 GL A/7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-15 | 2025-04-16 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 195 | Civil | RFI-ELE-CVL-W-G-CUB-0195 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 groundbeam for GL A/6-8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-22 | 2025-04-23 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 196 | Civil | RFI-ELE-CVL-W-G-CUB-0196 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 for 1 st Floor Slab at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-22 | 2025-04-23 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 197 | Civil | RFI-ELE-CVL-W-G-CUB-0197 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 days G30 groundfloor slab GL A-B/1-3 for Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-22 | 2025-04-23 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 198 | Civil | RFI-ELE-CVL-W-G-CUB-0198 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 days G30 for 1 st Column (6 nos) GL D/1-6 at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-22 | 2025-04-23 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 199 | Civil | RFI-ELE-CVL-W-G-CUB-0199 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 days G35A base sump pit for CB1 and MA1A for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-22 | 2025-04-23 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 200 | Civil | RFI-ELE-CVL-W-G-CUB-0200 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 days G30 column pedestal GL A-B/1-3 at Scheule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-22 | 2025-04-23 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 201 | Civil | RFI-ELE-CVL-W-G-CUB-0201 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 days G30 foundation for P-18203A (2 nos), P-16214, P-16247 and P-16224 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-23 | 2025-04-24 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 202 | Civil | RFI-ELE-CVL-W-G-CUB-0202 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 days G30 foudation for Pump foundation at Esstar Vission Compound | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-23 | 2025-04-24 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 203 | Civil | RFI-ELE-CVL-W-G-CUB-0203 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 days G30 groundslab GL A-C/10-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-24 | 2025-04-25 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 204 | Civil | RFI-ELE-CVL-W-G-CUB-0204 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 days G30 F9 Foundation at Man Refiner GL A-B/9 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-30 | 2025-05-01 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 205 | Civil | RFI-ELE-CVL-W-G-CUB-0205 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 days G35A Sump Pit for CB1 and MA1A for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-02 | 2025-05-03 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 206 | Civil | RFI-ELE-CVL-W-G-CUB-0206 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 days G35A CB2 base and MA1A Top for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-19 | 2025-05-20 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 207 | Civil | RFI-ELE-CVL-W-G-CUB-0207 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 days G30 roof slab and roof beam for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-19 | 2025-05-20 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 208 | Civil | RFI-ELE-CVL-W-G-CUB-0208 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 days G35A CB2 wall for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-19 | 2025-05-20 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 209 | Civil | RFI-ELE-CVL-W-G-CUB-0209 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day 1 st Column (12 nos) at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-19 | 2025-05-20 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 210 | Civil | RFI-ELE-CVL-W-G-CUB-0210 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day CB2 and CB3 and MA2 Pit at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-19 | 2025-05-20 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 211 | Civil | RFI-ELE-CVL-W-G-CUB-0211 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 groundfloor slab GL A-B/1-3 for Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-19 | 2025-05-20 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 212 | Civil | RFI-ELE-CVL-W-G-CUB-0212 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 1 st Column (6 nos) GL D/1-6 at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-19 | 2025-05-20 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 213 | Civil | RFI-ELE-CVL-W-G-CUB-0213 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day base sump pit for CB1 and MA1A for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-19 | 2025-05-20 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 214 | Civil | RFI-ELE-CVL-W-G-CUB-0214 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 column pedestal GL A-B/1-3 at Scheule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-19 | 2025-05-20 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 215 | Civil | RFI-ELE-CVL-W-G-CUB-0215 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 foudation for Pump foundation at Esstar Vission Compound | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-19 | 2025-05-20 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 216 | Civil | RFI-ELE-CVL-W-G-CUB-0216 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 of groundslab GL A-C/10-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-19 | 2025-05-20 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 217 | Civil | RFI-ELE-CVL-W-G-CUB-0217 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 of ACCU Foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-19 | 2025-05-20 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 218 | Civil | RFI-ELE-CVL-W-G-CUB-0218 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 column Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-29 | 2025-05-30 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 219 | Civil | RFI-ELE-CVL-W-G-CUB-0219 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G35A CB2 base and MA1A Top for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-05 | 2025-06-06 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 220 | Civil | RFI-ELE-CVL-W-G-CUB-0220 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 roof slab and roof beam for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-05 | 2025-06-06 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 221 | Civil | RFI-ELE-CVL-W-G-CUB-0221 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 CB2 wall for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-05 | 2025-06-06 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 222 | Civil | RFI-ELE-CVL-W-G-CUB-0222 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 South Staircase (external) for TK16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-05 | 2025-06-06 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 223 | Civil | RFI-ELE-CVL-W-G-CUB-0223 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 bottom Landing beam North Staircase for TK16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-05 | 2025-06-06 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 224 | Civil | RFI-ELE-CVL-W-G-CUB-0224 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 ground slab GL A-C/7-9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-10 | 2025-06-11 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 225 | Civil | RFI-ELE-CVL-W-G-CUB-0225 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 slab Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-10 | 2025-06-11 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 226 | Civil | RFI-ELE-CVL-W-G-CUB-0226 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 south lintel beam for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-10 | 2025-06-11 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 227 | Civil | RFI-ELE-CVL-W-G-CUB-0227 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 s South Staircase bottom plinth at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-16 | 2025-06-17 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 228 | Civil | RFI-ELE-CVL-W-G-CUB-0228 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 North Staircase Fligth at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-16 | 2025-06-17 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 229 | Civil | RFI-ELE-CVL-W-G-CUB-0229 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 South Staircase (internal) for TK16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-16 | 2025-06-17 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 230 | Civil | RFI-ELE-CVL-W-G-CUB-0230 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 base sump pit CB4 and CB5 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-01 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 231 | Civil | RFI-ELE-CVL-W-G-CUB-0231 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 base foundation for North Staircase at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-01 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 232 | Civil | RFI-ELE-CVL-W-G-CUB-0232 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G35A base CCW S-18244 sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-01 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 233 | Civil | RFI-ELE-CVL-W-G-CUB-0233 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 South Staircase bottom plinth at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-01 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 234 | Civil | RFI-ELE-CVL-W-G-CUB-0234 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 column Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-01 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 235 | Civil | RFI-ELE-CVL-W-G-CUB-0235 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 South Staircase for TK16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-01 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 236 | Civil | RFI-ELE-CVL-W-G-CUB-0236 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 bottom Landing beam North Staircase for TK16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-01 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 237 | Civil | RFI-ELE-CVL-W-G-CUB-0237 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 trench for Transfomer at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-01 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 238 | Civil | RFI-ELE-CVL-W-G-CUB-0238 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pump foundation P-16211 A and B at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-01 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 239 | Civil | RFI-ELE-CVL-W-G-CUB-0239 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 trench for Transfomer A and B at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-01 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 240 | Civil | RFI-ELE-CVL-W-G-CUB-0240 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 foundation for East IER Room RC Step Type 1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-01 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 241 | Civil | RFI-ELE-CVL-W-G-CUB-0241 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pedestal for F9 Foundation (2 nos) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-01 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 242 | Civil | RFI-ELE-CVL-W-G-CUB-0242 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G35A wall CCW S-18244 sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-01 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 243 | Civil | RFI-ELE-CVL-W-G-CUB-0243 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 base sump pit CB4 and CB5 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-01 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 244 | Civil | RFI-ELE-CVL-W-G-CUB-0244 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 base foundation for North Staircase at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-01 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 245 | Civil | RFI-ELE-CVL-W-G-CUB-0245 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day base CCW S-18244 sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-01 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 246 | Civil | RFI-ELE-CVL-W-G-CUB-0246 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 roof beam for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-01 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 247 | Civil | RFI-ELE-CVL-W-G-CUB-0247 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 column Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-01 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 248 | Civil | RFI-ELE-CVL-W-G-CUB-0248 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 South Staircase for TK16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-01 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 249 | Civil | RFI-ELE-CVL-W-G-CUB-0249 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 bottom Landing beam North Staircase for TK16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-01 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 250 | Civil | RFI-ELE-CVL-W-G-CUB-0250 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 East IER Room RC Step Type 1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2/7/6/2025 | 2025-07-03 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 251 | Civil | RFI-ELE-CVL-W-G-CUB-0251 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G35A wall and top CCW S-18244 sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2/7/6/2025 | 2025-07-03 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 252 | Civil | RFI-ELE-CVL-W-G-CUB-0252 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 precast cable support block at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2/7/6/2025 | 2025-07-03 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 253 | Civil | RFI-ELE-CVL-W-G-CUB-0253 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 south lintel beam for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2/7/6/2025 | 2025-07-03 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 254 | Civil | RFI-ELE-CVL-W-G-CUB-0254 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 South Staircase (internal) for TK16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2/7/6/2025 | 2025-07-03 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 255 | Civil | RFI-ELE-CVL-W-G-CUB-0255 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 foundation north east Staircase for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-10 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 256 | Civil | RFI-ELE-CVL-W-G-CUB-0256 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 base trench and sump pit for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-10 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 257 | Civil | RFI-ELE-CVL-W-G-CUB-0257 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 internal staircase flight for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-10 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 258 | Civil | RFI-ELE-CVL-W-G-CUB-0258 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G35A Wall 1 st Cast ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-10 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 259 | Civil | RFI-ELE-CVL-W-G-CUB-0259 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pileplug for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-10 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 260 | Civil | RFI-ELE-CVL-W-G-CUB-0260 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 south lintel beam for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-10 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 261 | Civil | RFI-ELE-CVL-W-G-CUB-0261 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 South Staircase (internal) for TK16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-10 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 262 | Civil | RFI-ELE-CVL-W-G-CUB-0262 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 South Staircase bottom plinth at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-10 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 263 | Civil | RFI-ELE-CVL-W-G-CUB-0263 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 North Staircase Fligth at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-10 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 264 | Civil | RFI-ELE-CVL-W-G-CUB-0264 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 South Staircase Fligth at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-10 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 265 | Civil | RFI-ELE-CVL-W-G-CUB-0265 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 GRE Pipe portion for Battery Room Slab at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-10 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 266 | Civil | RFI-ELE-CVL-W-G-CUB-0266 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 trench for Transfomer at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-10 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 267 | Civil | RFI-ELE-CVL-W-G-CUB-0267 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 pump foundation P-16211 A and B at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-10 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 268 | Civil | RFI-ELE-CVL-W-G-CUB-0268 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 East IER Room RC Step Type 1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-10 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 269 | Civil | RFI-ELE-CVL-W-G-CUB-0269 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 wall and top CCW S-18244 sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-10 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 270 | Civil | RFI-ELE-CVL-W-G-CUB-0270 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 precast cable support block at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-10 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 271 | Civil | RFI-ELE-CVL-W-G-CUB-0271 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 Foundation for North IER Room RC Step Type 2 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-10 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 272 | Civil | RFI-ELE-CVL-W-G-CUB-0272 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 base for trench for EDG at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-10 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 273 | Civil | RFI-ELE-CVL-W-G-CUB-0273 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 wall for trench for EDG at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-10 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 274 | Civil | RFI-ELE-CVL-W-G-CUB-0274 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 flight for North IER Room RC Step Type 2 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-09 | 2025-07-10 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 275 | Civil | RFI-ELE-CVL-W-G-CUB-0275 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 trench for Transfomer A and B at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-18 | 2025-07-19 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 276 | Civil | RFI-ELE-CVL-W-G-CUB-0276 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 foundation for East IER Room RC Step Type 1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-18 | 2025-07-19 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 277 | Civil | RFI-ELE-CVL-W-G-CUB-0277 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 pedestal for F9 Foundation (2 nos) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-18 | 2025-07-19 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 278 | Civil | RFI-ELE-CVL-W-G-CUB-0278 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G35A wall CCW S-18244 sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-18 | 2025-07-19 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 279 | Civil | RFI-ELE-CVL-W-G-CUB-0279 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 flight north east Staircase for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-18 | 2025-07-19 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 280 | Civil | RFI-ELE-CVL-W-G-CUB-0280 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pileplug for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-18 | 2025-07-19 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 281 | Civil | RFI-ELE-CVL-W-G-CUB-0281 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 foundation for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-18 | 2025-07-19 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 282 | Civil | RFI-ELE-CVL-W-G-CUB-0282 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 trench for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-18 | 2025-07-19 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 283 | Civil | RFI-ELE-CVL-W-G-CUB-0283 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G35A base ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-18 | 2025-07-19 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 284 | Civil | RFI-ELE-CVL-W-G-CUB-0284 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 Groundslab Switchroom at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-18 | 2025-07-19 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 285 | Civil | RFI-ELE-CVL-W-G-CUB-0285 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 North Staircase (internal and external) for TK16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-18 | 2025-07-19 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 286 | Civil | RFI-ELE-CVL-W-G-CUB-0286 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 groundslab GL A-C/1-4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 287 | Civil | RFI-ELE-CVL-W-G-CUB-0287 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 cable tray support foundation F1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 288 | Civil | RFI-ELE-CVL-W-G-CUB-0288 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pileplug for Z-18213A foundation for Chilled Water Package | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 289 | Civil | RFI-ELE-CVL-W-G-CUB-0289 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 groundslab GL A-C/4-8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 290 | Civil | RFI-ELE-CVL-W-G-CUB-0290 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30r cable tray support foundation pedestal F1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 291 | Civil | RFI-ELE-CVL-W-G-CUB-0291 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pileplug PC 3 (E-18206) Foundation at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 292 | Civil | RFI-ELE-CVL-W-G-CUB-0292 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 Z-18213A foundation for Chilled Water Package | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 293 | Civil | RFI-ELE-CVL-W-G-CUB-0293 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 PC 3 (E-18206) Foundation at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 294 | Civil | RFI-ELE-CVL-W-G-CUB-0294 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 roofslab GL A-C/1-3 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 295 | Civil | RFI-ELE-CVL-W-G-CUB-0295 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 1st Floor GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | Hanson Plant (Gebeng) | Accepted
| 296 | Civil | RFI-ELE-CVL-W-G-CUB-0296 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 2nd Floor GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-06 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 297 | Civil | RFI-ELE-CVL-W-G-CUB-0297 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 East IER Room RC Step Type 1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 298 | Civil | RFI-ELE-CVL-W-G-CUB-0298 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G35A wall and top CCW S-18244 sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 299 | Civil | RFI-ELE-CVL-W-G-CUB-0299 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 precast cable support block at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 300 | Civil | RFI-ELE-CVL-W-G-CUB-0300 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 Foundation for North IER Room RC Step Type 2 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 301 | Civil | RFI-ELE-CVL-W-G-CUB-0301 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 base for trench for EDG at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 302 | Civil | RFI-ELE-CVL-W-G-CUB-0302 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 wall for trench for EDG at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 303 | Civil | RFI-ELE-CVL-W-G-CUB-0303 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 flight for North IER Room RC Step Type 2 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 304 | Civil | RFI-ELE-CVL-W-G-CUB-0304 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 groundslab GL A-C/1-4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 305 | Civil | RFI-ELE-CVL-W-G-CUB-0305 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 flight north east Staircase for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 306 | Civil | RFI-ELE-CVL-W-G-CUB-0306 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 307 | Civil | RFI-ELE-CVL-W-G-CUB-0307 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 foundation for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 308 | Civil | RFI-ELE-CVL-W-G-CUB-0308 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 trench for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 309 | Civil | RFI-ELE-CVL-W-G-CUB-0309 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 foundation for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 310 | Civil | RFI-ELE-CVL-W-G-CUB-0310 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G35A Wall 2nd Cast ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 311 | Civil | RFI-ELE-CVL-W-G-CUB-0311 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pedestal for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 312 | Civil | RFI-ELE-CVL-W-G-CUB-0312 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 roof beam for Chemical and Catalyst Storage Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 313 | Civil | RFI-ELE-CVL-W-G-CUB-0313 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 foundation north east Staircase for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 314 | Civil | RFI-ELE-CVL-W-G-CUB-0314 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 base trench and sump pit for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 315 | Civil | RFI-ELE-CVL-W-G-CUB-0315 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G35A Wall 1 st Cast ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 316 | Civil | RFI-ELE-CVL-W-G-CUB-0316 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 internal staircase flight for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 317 | Civil | RFI-ELE-CVL-W-G-CUB-0317 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G35A Wall 1 st Cast ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 318 | Civil | RFI-ELE-CVL-W-G-CUB-0318 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 pileplug for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 319 | Civil | RFI-ELE-CVL-W-G-CUB-0319 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 trench for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 320 | Civil | RFI-ELE-CVL-W-G-CUB-0320 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 roofslab kerb GL A-C/1-3 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 321 | Civil | RFI-ELE-CVL-W-G-CUB-0321 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pileplug for TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 322 | Civil | RFI-ELE-CVL-W-G-CUB-0322 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pilecap for TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 323 | Civil | RFI-ELE-CVL-W-G-CUB-0323 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 1st Mezzanine Floor GL A-B/3-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 324 | Civil | RFI-ELE-CVL-W-G-CUB-0324 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pileplug for foundation T 19230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 325 | Civil | RFI-ELE-CVL-W-G-CUB-0325 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pedestal for TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 326 | Civil | RFI-ELE-CVL-W-G-CUB-0326 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 foundation T 19230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 327 | Civil | RFI-ELE-CVL-W-G-CUB-0327 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pedestal T 19230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 328 | Civil | RFI-ELE-CVL-W-G-CUB-0328 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 foundation melt tank pump P19221A/B at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 329 | Civil | RFI-ELE-CVL-W-G-CUB-0329 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 cable tray support foundation F1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 330 | Civil | RFI-ELE-CVL-W-G-CUB-0330 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 pileplug for Z-18213A foundation for Chilled Water Package | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 331 | Civil | RFI-ELE-CVL-W-G-CUB-0331 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 groundslab GL A-C/4-8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 332 | Civil | RFI-ELE-CVL-W-G-CUB-0332 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 cable tray support foundation pedestal F1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 333 | Civil | RFI-ELE-CVL-W-G-CUB-0333 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 pileplug PC 3 (E-18206) Foundation at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 334 | Civil | RFI-ELE-CVL-W-G-CUB-0334 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 Z-18213A foundation for Chilled Water Package | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 335 | Civil | RFI-ELE-CVL-W-G-CUB-0335 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 PC 3 (E-18206) Foundation at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 336 | Civil | RFI-ELE-CVL-W-G-CUB-0336 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30roofslab GL A-C/1-3 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 337 | Civil | RFI-ELE-CVL-W-G-CUB-0337 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 slab for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 338 | Civil | RFI-ELE-CVL-W-G-CUB-0338 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pilecap for GL J-L/3-4 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 339 | Civil | RFI-ELE-CVL-W-G-CUB-0339 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pedestal for GL J-L/3-4 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 340 | Civil | RFI-ELE-CVL-W-G-CUB-0340 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pedestal for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 341 | Civil | RFI-ELE-CVL-W-G-CUB-0341 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 foundation Pipe Support for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 342 | Civil | RFI-ELE-CVL-W-G-CUB-0342 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 flight north east Staircase for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 343 | Civil | RFI-ELE-CVL-W-G-CUB-0343 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 pileplug for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 344 | Civil | RFI-ELE-CVL-W-G-CUB-0344 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 foundation for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 345 | Civil | RFI-ELE-CVL-W-G-CUB-0345 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 trench for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 346 | Civil | RFI-ELE-CVL-W-G-CUB-0346 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 foundation for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 347 | Civil | RFI-ELE-CVL-W-G-CUB-0347 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G35A Wall 2nd Cast ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 348 | Civil | RFI-ELE-CVL-W-G-CUB-0348 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 pedestal for GL A-C/2-3 Foundation at Fire Water Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 349 | Civil | RFI-ELE-CVL-W-G-CUB-0349 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 2nd Floor pump foundation and kerb GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-04 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 350 | Civil | RFI-ELE-CVL-W-G-CUB-0350 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 1st Mezzanine Floor GL A-B/3-7 pump foundation and kerb at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-04 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 351 | Civil | RFI-ELE-CVL-W-G-CUB-0351 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 foundation for new pump P19231 A/B and P19232 A/B at Scubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-04 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 352 | Civil | RFI-ELE-CVL-W-G-CUB-0352 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 foundation for D16227 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-04 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 353 | Civil | RFI-ELE-CVL-W-G-CUB-0353 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pedestal for D16227 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-04 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 354 | Civil | RFI-ELE-CVL-W-G-CUB-0354 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 1st Floor GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-04 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 355 | Civil | RFI-ELE-CVL-W-G-CUB-0355 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 2nd Floor GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-04 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 356 | Civil | RFI-ELE-CVL-W-G-CUB-0356 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 roofslab kerb GL A-C/1-3 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-04 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 357 | Civil | RFI-ELE-CVL-W-G-CUB-0357 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 pileplug for TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-04 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 358 | Civil | RFI-ELE-CVL-W-G-CUB-0358 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 pilecap for TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-04 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 359 | Civil | RFI-ELE-CVL-W-G-CUB-0359 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 1st Mezzanine Floor GL A-B/3-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-04 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 360 | Civil | RFI-ELE-CVL-W-G-CUB-0360 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 pileplug for foundation T 19230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-04 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 361 | Civil | RFI-ELE-CVL-W-G-CUB-0361 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G35A Top slab ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-04 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 362 | Civil | RFI-ELE-CVL-W-G-CUB-0362 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pedestal F4 and F5 Pipe Support for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-04 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 363 | Civil | RFI-ELE-CVL-W-G-CUB-0363 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G35A bottom gate valve pit ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-04 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 364 | Civil | RFI-ELE-CVL-W-G-CUB-0364 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 slab for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-04 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 365 | Civil | RFI-ELE-CVL-W-G-CUB-0365 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 pilecap for GL J-L/3-4 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-04 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 366 | Civil | RFI-ELE-CVL-W-G-CUB-0366 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 pedestal for GL J-L/3-4 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-04 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 367 | Civil | RFI-ELE-CVL-W-G-CUB-0367 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 pedestal for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-03 | 2025-09-04 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 368 | Civil | RFI-ELE-CVL-W-G-CUB-0368 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 pileplug for foundation T 19230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 369 | Civil | RFI-ELE-CVL-W-G-CUB-0369 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 pedestal for TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 370 | Civil | RFI-ELE-CVL-W-G-CUB-0370 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 foundation T 19230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 371 | Civil | RFI-ELE-CVL-W-G-CUB-0371 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 pedestal T 19230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 372 | Civil | RFI-ELE-CVL-W-G-CUB-0372 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 foundation melt tank pump P19221A/B at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 373 | Civil | RFI-ELE-CVL-W-G-CUB-0373 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 2nd Floor pump foundation and kerb GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 374 | Civil | RFI-ELE-CVL-W-G-CUB-0374 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 1st Mezzanine Floor GL A-B/3-7 pump foundation and kerb at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 375 | Civil | RFI-ELE-CVL-W-G-CUB-0375 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 foundation for new pump P19231 A/B and P19232 A/B at Scubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 376 | Civil | RFI-ELE-CVL-W-G-CUB-0376 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 foundation for D16227 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 377 | Civil | RFI-ELE-CVL-W-G-CUB-0377 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 pedestal for D16227 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 378 | Civil | RFI-ELE-CVL-W-G-CUB-0378 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 foundation for new pump P19231 B at Scubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 379 | Civil | RFI-ELE-CVL-W-G-CUB-0379 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pedestal for D16227 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 380 | Civil | RFI-ELE-CVL-W-G-CUB-0380 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 foundation for new pump P19231 B at Scubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 381 | Civil | RFI-ELE-CVL-W-G-CUB-0381 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 compound slab TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 382 | Civil | RFI-ELE-CVL-W-G-CUB-0382 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 cable tray support foundation near Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 383 | Civil | RFI-ELE-CVL-W-G-CUB-0383 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pump foundation for P-18204A/B at Demineralise Water Pump Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 384 | Civil | RFI-ELE-CVL-W-G-CUB-0384 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 cable tray support foundation near Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 385 | Civil | RFI-ELE-CVL-W-G-CUB-0385 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30foundation for P-16232 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 386 | Civil | RFI-ELE-CVL-W-G-CUB-0386 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 1st Mezzanine Floor GL A-B/3-7 pump foundation and kerb at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 387 | Civil | RFI-ELE-CVL-W-G-CUB-0387 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 stair foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 388 | Civil | RFI-ELE-CVL-W-G-CUB-0388 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 foundation at F5 and F6 at SP 10 Platform | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 389 | Civil | RFI-ELE-CVL-W-G-CUB-0389 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 stair foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 390 | Civil | RFI-ELE-CVL-W-G-CUB-0390 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 foundation Pipe Support for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 391 | Civil | RFI-ELE-CVL-W-G-CUB-0391 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G35A Top slab ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 392 | Civil | RFI-ELE-CVL-W-G-CUB-0392 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30pedestal F4 and F5 Pipe Support for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 393 | Civil | RFI-ELE-CVL-W-G-CUB-0393 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G35A bottom gate valve pit ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 394 | Civil | RFI-ELE-CVL-W-G-CUB-0394 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G35A base sump CCW Pit S-18242 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 395 | Civil | RFI-ELE-CVL-W-G-CUB-0395 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 Pipe support foundation East Side for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 396 | Civil | RFI-ELE-CVL-W-G-CUB-0396 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G35A base sump CCW Pit S-18242 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 397 | Civil | RFI-ELE-CVL-W-G-CUB-0397 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30Pipe support foundation East Side for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 398 | Civil | RFI-ELE-CVL-W-G-CUB-0398 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 HVAC Power and Control Panel Foundation at Switchroom WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 399 | Civil | RFI-ELE-CVL-W-G-CUB-0399 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 Pipe support foundation pedestal East Side for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 400 | Civil | RFI-ELE-CVL-W-G-CUB-0400 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G35A wall gate valve pit ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 401 | Civil | RFI-ELE-CVL-W-G-CUB-0401 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 stiffener at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 402 | Civil | RFI-ELE-CVL-W-G-CUB-0402 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G35A 1st cast wall sump CCW Pit S-18242 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 403 | Civil | RFI-ELE-CVL-W-G-CUB-0403 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G35A 2nd cast wall and top slab sump CCW Pit S-18242 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 404 | Civil | RFI-ELE-CVL-W-G-CUB-0404 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 1st Mezzanine Floor GL A-B/3-7 pump foundation and kerb at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-09-27 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 405 | Civil | RFI-ELE-CVL-W-G-CUB-0405 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 1st Floor Z-19206 A/B/C Fines Sifter at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-09-27 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 406 | Civil | RFI-ELE-CVL-W-G-CUB-0406 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 2nd Floor slab GL A-B/6-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-09-27 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 407 | Civil | RFI-ELE-CVL-W-G-CUB-0407 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 Pileplug for 2 nos F2, 1 nos F3 and 4 nos F5 foundation at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-09-27 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 408 | Civil | RFI-ELE-CVL-W-G-CUB-0408 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 foundation chimney S-19232 at Roof Slab Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-09-27 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 409 | Civil | RFI-ELE-CVL-W-G-CUB-0409 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pilecap for 2 nos F2, 1 nos F3, 1 nos F7 and 4 nos F5 foundation at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-09-29 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 410 | Civil | RFI-ELE-CVL-W-G-CUB-0410 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pedestal at F5 and F6 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-09-30 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 411 | Civil | RFI-ELE-CVL-W-G-CUB-0411 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 2nd Floor kerb GL A-B/6-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-09-30 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 412 | Civil | RFI-ELE-CVL-W-G-CUB-0412 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pedestal 2 nos F5, 2 nos F1 and 2 nos F2 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-01 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 413 | Civil | RFI-ELE-CVL-W-G-CUB-0413 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-01 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 414 | Civil | RFI-ELE-CVL-W-G-CUB-0414 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-02 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 415 | Civil | RFI-ELE-CVL-W-G-CUB-0415 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pilecap 1 nos F7 and 1 nos F3 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-02 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 416 | Civil | RFI-ELE-CVL-W-G-CUB-0416 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pilecap 1 nos F1 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-02 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 417 | Civil | RFI-ELE-CVL-W-G-CUB-0417 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30pedestal 1 nos F7 and 1 nos F3 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-03 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 418 | Civil | RFI-ELE-CVL-W-G-CUB-0418 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-05 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 419 | Civil | RFI-ELE-CVL-W-G-CUB-0419 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pilecap for D 18220 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-07 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 420 | Civil | RFI-ELE-CVL-W-G-CUB-0420 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pedestal for D 18220 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-08 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 421 | Civil | RFI-ELE-CVL-W-G-CUB-0421 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 foundation for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-08 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 422 | Civil | RFI-ELE-CVL-W-G-CUB-0422 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G35A base MA5, MA6, MA7 and MC10 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-08 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 423 | Civil | RFI-ELE-CVL-W-G-CUB-0423 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 foundation for YM 18250 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-09 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 424 | Civil | RFI-ELE-CVL-W-G-CUB-0424 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G35A wall MA5, MA6, MA7 and MC10 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-01-10 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 425 | Civil | RFI-ELE-CVL-W-G-CUB-0425 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 foundation for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-11 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 426 | Civil | RFI-ELE-CVL-W-G-CUB-0426 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-11 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 427 | Civil | RFI-ELE-CVL-W-G-CUB-0427 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G35A top MA5, MA6, MA7 and MC10 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-16 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 428 | Civil | RFI-ELE-CVL-W-G-CUB-0428 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-17 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 429 | Civil | RFI-ELE-CVL-W-G-CUB-0429 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 apron slab and ramp around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-18 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 430 | Civil | RFI-ELE-CVL-W-G-CUB-0430 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 apron slab around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-19 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 431 | Civil | RFI-ELE-CVL-W-G-CUB-0431 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 foundation for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-19 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 432 | Civil | RFI-ELE-CVL-W-G-CUB-0432 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 apron slab around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 433 | Civil | RFI-ELE-CVL-W-G-CUB-0433 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 foundation for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 434 | Civil | RFI-ELE-CVL-W-G-CUB-0434 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 apron slab around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-22 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 435 | Civil | RFI-ELE-CVL-W-G-CUB-0435 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 concrete for F1 Service Platform foundation at Demin Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-22 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 436 | Civil | RFI-ELE-CVL-W-G-CUB-0436 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 pedestal for F1 Service Platform foundation at Demin Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-23 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 437 | Civil | RFI-ELE-CVL-W-G-CUB-0437 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 foundation for cable C360 support foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-23 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 438 | Civil | RFI-ELE-CVL-W-G-CUB-0438 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G35A bund wall for TK16230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 439 | Civil | RFI-ELE-CVL-W-G-CUB-0439 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 apron slab and ramp around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 440 | Civil | RFI-ELE-CVL-W-G-CUB-0440 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 stair landing foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 441 | Civil | RFI-ELE-CVL-W-G-CUB-0441 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G35A base MC2, MC7 and wall MC1 and MC6 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-28 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 442 | Civil | RFI-ELE-CVL-W-G-CUB-0442 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 gully trap GT-1 at Substation C2015 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-28 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 443 | Civil | RFI-ELE-CVL-W-G-CUB-0443 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 apron slab and ramp around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-29 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 444 | Civil | RFI-ELE-CVL-W-G-CUB-0444 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 compound slab TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-09-30 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 445 | Civil | RFI-ELE-CVL-W-G-CUB-0445 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 cable tray support foundation near Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-09-30 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 446 | Civil | RFI-ELE-CVL-W-G-CUB-0446 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 pump foundation for P-18204A/B at Demineralise Water Pump Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-06 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 447 | Civil | RFI-ELE-CVL-W-G-CUB-0447 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 cable tray support foundation near Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-06 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 448 | Civil | RFI-ELE-CVL-W-G-CUB-0448 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 foundation for P-16232 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-06 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 449 | Civil | RFI-ELE-CVL-W-G-CUB-0449 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 1st Mezzanine Floor GL A-B/3-7 pump foundation and kerb at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-09 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 450 | Civil | RFI-ELE-CVL-W-G-CUB-0450 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 stair foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-11 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 451 | Civil | RFI-ELE-CVL-W-G-CUB-0451 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 foundation at F5 and F6 at SP 10 Platform | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-16 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 452 | Civil | RFI-ELE-CVL-W-G-CUB-0452 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 stair foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-16 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 453 | Civil | RFI-ELE-CVL-W-G-CUB-0453 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 1st Mezzanine Floor GL A-B/3-7 pump foundation and kerb at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-18 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 454 | Civil | RFI-ELE-CVL-W-G-CUB-0454 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 1st Floor Z-19206 A/B/C Fines Sifter at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-18 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 455 | Civil | RFI-ELE-CVL-W-G-CUB-0455 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 2nd Floor slab GL A-B/6-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-18 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 456 | Civil | RFI-ELE-CVL-W-G-CUB-0456 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 Pileplug for 2 nos F2, 1 nos F3 and 4 nos F5 foundation at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-18 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 457 | Civil | RFI-ELE-CVL-W-G-CUB-0457 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 foundation chimney S-19232 at Roof Slab Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-18 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 458 | Civil | RFI-ELE-CVL-W-G-CUB-0458 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 pilecap for 2 nos F2, 1 nos F3, 1 nos F7 and 4 nos F5 foundation at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-20 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 459 | Civil | RFI-ELE-CVL-W-G-CUB-0459 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 pedestal at F5 and F6 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 460 | Civil | RFI-ELE-CVL-W-G-CUB-0460 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 2nd Floor kerb GL A-B/6-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 461 | Civil | RFI-ELE-CVL-W-G-CUB-0461 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 pedestal 2 nos F5, 2 nos F1 and 2 nos F2 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-22 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 462 | Civil | RFI-ELE-CVL-W-G-CUB-0462 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-22 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 463 | Civil | RFI-ELE-CVL-W-G-CUB-0463 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-23 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 464 | Civil | RFI-ELE-CVL-W-G-CUB-0464 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 pilecap 1 nos F7 and 1 nos F3 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-23 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 465 | Civil | RFI-ELE-CVL-W-G-CUB-0465 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 pilecap 1 nos F1 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-23 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 466 | Civil | RFI-ELE-CVL-W-G-CUB-0466 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 pedestal 1 nos F7 and 1 nos F3 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-24 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 467 | Civil | RFI-ELE-CVL-W-G-CUB-0467 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-26 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 468 | Civil | RFI-ELE-CVL-W-G-CUB-0468 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 pilecap for D 18220 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-28 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 469 | Civil | RFI-ELE-CVL-W-G-CUB-0469 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 pedestal for D 18220 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-29 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 470 | Civil | RFI-ELE-CVL-W-G-CUB-0470 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 foundation for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-29 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 471 | Civil | RFI-ELE-CVL-W-G-CUB-0471 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G35A base MA5, MA6, MA7 and MC10 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-29 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 472 | Civil | RFI-ELE-CVL-W-G-CUB-0472 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 foundation for YM 18250 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 2025-10-30 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 473 | Civil | RFI-ELE-CVL-W-G-CUB-0473 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G35A wall MA5, MA6, MA7 and MC10 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-30 | 31/11/2025 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 474 | Civil | RFI-ELE-CVL-W-G-CUB-0474 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 base for SP1 and SP2 sump pit at Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-31 | 2025-09-30 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 475 | Civil | RFI-ELE-CVL-W-G-CUB-0475 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G30 Wall for SP1 and SP2 sump pit at Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-31 | 2025-10-03 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 476 | Civil | RFI-ELE-CVL-W-G-CUB-0476 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 7 day G35A precast manhole base for MS4, MS4A, MS5, MS5A, MS9, MS9A and MS10 for D300 at M-One Fabrication Yard | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-31 | 2025-10-04 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 477 | Civil | RFI-ELE-CVL-W-G-CUB-0477 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 HVAC Power and Control Panel Foundation at Switchroom WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-31 | 2025-09-30 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 478 | Civil | RFI-ELE-CVL-W-G-CUB-0478 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 Pipe support foundation pedestal East Side for TK 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-31 | 2025-10-02 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 479 | Civil | RFI-ELE-CVL-W-G-CUB-0479 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G35A wall gate valve pit ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-31 | 2025-10-02 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 480 | Civil | RFI-ELE-CVL-W-G-CUB-0480 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 stiffener at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-31 | 2025-10-02 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 481 | Civil | RFI-ELE-CVL-W-G-CUB-0481 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G35A 1st cast wall sump CCW Pit S-18242 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-31 | 2025-10-03 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 482 | Civil | RFI-ELE-CVL-W-G-CUB-0482 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G35A 2nd cast wall and top slab sump CCW Pit S-18242 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-31 | 2025-10-11 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 483 | Civil | RFI-ELE-CVL-W-G-CUB-0483 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 base for SP1 and SP2 sump pit at Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-31 | 2025-10-21 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 484 | Civil | RFI-ELE-CVL-W-G-CUB-0484 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G30 Wall for SP1 and SP2 sump pit at Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-31 | 2025-10-24 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted
| 485 | Civil | RFI-ELE-CVL-W-G-CUB-0485 | External | Eleco | Civil | N/A | Cube Test | Cube Test | Inspection cube testing 28 day G35A precast manhole base for MS4, MS4A, MS5, MS5A, MS9, MS9A and MS10 for D300 at M-One Fabrication Yard | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-31 | 2025-10-25 | 11.00 AM | I/R | W | N/A | W | Hanis | LCS (DAMANSARA) | Accepted

## 11.RFI_BFL
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-27
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-CVL-F-D300-BFL-0001 | External | Eleco | Civil Work | N/A | Earthwork | Backfilling | Inspection for foundation backfilling for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-07 | 2024-09-09 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 2 | Civil | RFI-ELE-CVL-F-D300-BFL-0002 | External | Eleco | Civil Work | N/A | Earthwork | Backfilling | Inspection for foundation backfilling for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-28 | 2024-09-28 | 4.00 PM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 3 | Civil | RFI-ELE-CVL-F-D300-BFL-0003 | External | Eleco | Civil Work | N/A | Earthwork | Backfilling | Inspection for foundation backfilling using harcore material for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-30 | 2024-09-30 | 10.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 4 | Civil | RFI-ELE-CVL-F-D300-BFL-0004 | External | Eleco | Civil Work | N/A | Earthwork | Backfilling | Inspection for foundation backfilling using harcore material for Tank TK - 16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-30 | 2024-10-01 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 5 | Civil | RFI-ELE-CVL-F-D300-BFL-0005 | External | Eleco | Civil Work | N/A | Earthwork | Backfilling | Inspection for foundation backfilling for WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-01 | 2024-11-01 | 11.30 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 6 | Civil | RFI-ELE-CVL-F-D300-BFL-0006 | External | Eleco | Civil Work | N/A | Earthwork | Backfilling | Inspection for foundation backfilling at Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-01 | 2024-11-01 | 11.30 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 7 | Civil | RFI-ELE-CVL-F-D300-BFL-0007 | External | Eleco | Civil Work | N/A | Earthwork | Backfilling | Inspection for foundation backfilling at Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-13 | 2024-11-14 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 8 | Civil | RFI-ELE-CVL-F-D300-BFL-0008 | External | Eleco | Civil Work | N/A | Earthwork | Backfilling | Inspection for backfilling work Schedule Waste Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-27 | 2024-11-28 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 9 | Civil | RFI-ELE-CVL-F-D300-BFL-0009 | External | Eleco | Civil Work | N/A | Earthwork | Backfilling | Inspection for backfilling work compacted hardcore Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-14 | 2024-12-14 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 10 | Civil | RFI-ELE-CVL-F-D300-BFL-0010 | External | Eleco | Civil Work | N/A | Earthwork | Backfilling | Inspection for backfilling work compacted hardcore Firewater Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-16 | 2024-12-16 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 11 | Civil | RFI-ELE-CVL-F-D300-BFL-0011 | External | Eleco | Civil Work | N/A | Earthwork | Backfilling | Inspection for backfilling work compacted hardcore Piperack2 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-16 | 2024-12-16 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 12 | Civil | RFI-ELE-CVL-F-D300-BFL-0012 | External | Eleco | Civil Work | N/A | Earthwork | Backfilling | Inspection for backfilling work for Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-17 | 2024-12-18 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 13 | Civil | RFI-ELE-CVL-F-D300-BFL-0013 | External | Eleco | Civil Work | N/A | Earthwork | Backfilling | Inspection for backfilling work for Piperack pedestal at D300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-17 | 2024-12-18 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 14 | Civil | RFI-ELE-CVL-F-D300-BFL-0014 | External | Eleco | Civil Work | N/A | Earthwork | Backfilling | Inspection for backfilling work for foundation F2 Fire Water Pipe Bridge | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-26 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 15 | Civil | RFI-ELE-CVL-F-D300-BFL-0015 | External | Eleco | Civil Work | N/A | Earthwork | Backfilling | Inspection for backfilling work for pump foundation at Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-26 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 16 | Civil | RFI-ELE-CVL-F-D300-BFL-0016 | External | Eleco | Civil Work | N/A | Earthwork | Backfilling | Inspection for backfilling work for piperack GL M-N/3-4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-03 | 2025-01-04 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 17 | Civil | RFI-ELE-CVL-F-D300-BFL-0017 | External | Eleco | Civil Work | N/A | Earthwork | Backfilling | Inspection for backfilling work for pedestal at truck loading shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-04 | 2025-01-06 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 18 | Civil | RFI-ELE-CVL-F-D300-BFL-0018 | External | Eleco | Civil Work | N/A | Earthwork | Backfilling | Inspection for backfilling work for pilecap GL B-H/1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-09 | 2025-01-10 | 11.00 AM | H | W | N/A | R | Hanis | D300 | Accepted | -
| 19 | Civil | RFI-ELE-CVL-F-D300-BFL-0019 | External | Eleco | Civil Work | N/A | Earthwork | Backfilling | Inspection for backfilling work for Switch Room WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-10 | 2025-02-11 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 20 | Civil | RFI-ELE-CVL-F-D300-BFL-0020 | External | Eleco | Civil Work | N/A | Earthwork | Backfilling | Inspection for backfilling work for foundation GL I-K/ 1-2 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-18 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 21 | Civil | RFI-ELE-CVL-F-D300-BFL-0021 | External | Eleco | Civil Work | N/A | Earthwork | Backfilling | Inspection for backfilling work for Schedule Waste Storage Sump pit and GRE line | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 22 | Civil | RFI-ELE-CVL-F-D300-BFL-0022 | External | Eleco | Civil Work | N/A | Earthwork | Backfilling | Inspection for backfilling work for Chemical and Catalyst Storage Shelter and GRE line | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-28 | 2025-04-29 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 23 | Civil | RFI-ELE-CVL-F-D300-BFL-0023 | External | Eleco | Civil Work | N/A | Earthwork | Backfilling | Inspection for backfilling work for Hardcore at ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-31 | 2025-06-03 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted
| 23 | Civil | RFI-ELE-CVL-F-D300-BFL-0024 | External | Eleco | Civil Work | N/A | Earthwork | Backfilling | Inspection for backfilling work for Hardcore at ACW First Flush Pit S-18243 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-10 | 2025-07-11 | 9.00 AM | H | W | N/A | R | Hanis | D300 | Accepted

## 12.RFI_FDT
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-27
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-CVL-F-D300-FDT-0001 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test for foundation backfilling at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-07 | 2024-09-09 | 11.00 AM | H | W | I | W/R | Hanis | D300 | Accepted | -
| 2 | Civil | RFI-ELE-CVL-F-D300-FDT-0002 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test for foundation backfilling at stump level at WMB * additianal for groundfloor level | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-17 | 2024-09-19 | 9.00 AM | H | W | I | W/R | Hanis | D300 | Accepted | -
| 3 | Civil | RFI-ELE-CVL-F-D300-FDT-0003 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test for foundation backfilling at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-28 | 2024-10-01 | 9.00 AM | H | W | I | W/R | Hanis | D300 | Accepted | -
| 4 | Civil | RFI-ELE-CVL-F-D300-FDT-0004 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test for compacted hardcore Tank TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-11 | 2024-10-12 | 9.00 AM | H | W | I | W/R | Hanis | D300 | Accepted | -
| 5 | Civil | RFI-ELE-CVL-F-D300-FDT-0005 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test for compacted hardcore at WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-31 | 2024-11-01 | 9.00 AM | H | W | I | W/R | Hanis | D300 | Accepted | -
| 6 | Civil | RFI-ELE-CVL-F-D300-FDT-0006 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test for compacted hardcore at Scheduled Waste Storage Building Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-07 | 2024-12-09 | 9.00 AM | H | W | I | W/R | Hanis | D300 | Accepted | -
| 7 | Civil | RFI-ELE-CVL-F-D300-FDT-0007 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test compacted hardcore Switch Room WMB | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-14 | 2024-12-16 | 9.00 AM | H | W | I | W/R | Hanis | D300 | Cancelled | -
| 8 | Civil | RFI-ELE-CVL-F-D300-FDT-0008 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test compacted hardcore Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-14 | 2024-12-16 | 9.00 AM | H | W | I | W/R | Hanis | D300 | Cancelled | -
| 9 | Civil | RFI-ELE-CVL-F-D300-FDT-0009 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test compacted hardcore Piperack Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-14 | 2024-12-16 | 9.00 AM | H | W | I | W/R | Hanis | D300 | Cancelled | -
| 10 | Civil | RFI-ELE-CVL-F-D300-FDT-0010 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-06 | 2025-02-07 | 9.00 AM | H | W | I | W/R | Hanis | D300 | Accepted | -
| 11 | Civil | RFI-ELE-CVL-F-D300-FDT-0011 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test at Pump Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-18 | 9.00 AM | H | W | I | W/R | Hanis | D300 | Accepted | -
| 12 | Civil | RFI-ELE-CVL-F-D300-FDT-0012 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test at Truck Loading Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-18 | 9.00 AM | H | W | I | W/R | Hanis | D300 | Accepted | -
| 13 | Civil | RFI-ELE-CVL-F-D300-FDT-0013 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test at Chemical and Catalyst Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-11 | 9.00 AM | H | W | I | W/R | Hanis | D300 | Accepted | -
| 14 | Civil | RFI-ELE-CVL-F-D300-FDT-0014 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test at Schedule Waste Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-11 | 9.00 AM | H | W | I | W/R | Hanis | D300 | Accepted | -
| 15 | Civil | RFI-ELE-CVL-F-D300-FDT-0015 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test at Chemical and Catalyst Storage | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-30 | 2025-05-02 | 9.00 AM | H | W | I | W/R | Hanis | D300 | Accepted | -
| 16 | Civil | RFI-ELE-CVL-F-D300-FDT-0016 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test at TK-16234 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-26 | 2025-05-26 | 9.00 AM | H | W | I | W/R | Hanis | D300 | Accepted | -
| 17 | Civil | RFI-ELE-CVL-F-D300-FDT-0017 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test at Chemical and ACW First Flush Pit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-03 | 2025-06-04 | 9.00 AM | H | W | I | W/R | Hanis | D300 | Accepted | -
| 18 | Civil | RFI-ELE-CVL-F-D300-FDT-0018 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test at Chemical and ACW First Flush Pit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-10 | 2025-07-11 | 9.00 AM | H | W | I | W/R | Hanis | D300 | Accepted | -
| 19 | Civil | RFI-ELE-CVL-F-D300-FDT-0019 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test at Chemical and ACW First Flush Pit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-23 | 2025-07-24 | 9.00 AM | H | W | I | W/R | Hanis | D300 | Accepted | -
| 20 | Civil | RFI-ELE-CVL-F-D300-FDT-0020 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test at Pump Foundation Shelter | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-08 | 2025-10-09 | 9.00 AM | H | W | I | W/R | Hanis | D300 | Accepted | -