## 00. SUMMARY
Summary of RFI for ELECO
[12 empty] | Date : | 2026-01-30
01. Total Summary for RFI
| SubCon | Unit | Discipline | Code | Type | Accumulative RFI Status
[6 empty] | Issued | Accepted | Ongoing | Rejected | Cancelled | Remark
| ELECO | C300 | Trial Mix | TRM | RFI | 0 | 0 | 0 | 0 | 0 | * Cancelled due not ready to inspection.
|  |  | Material Receiving | MRI | RFI | 0 | 0 | 0 | 0 | 0
|  |  | General Test | GLT | RFI | 48 | 42 | 5 | 0 | 1
|  |  | Survey Work | SVW | RFI | 6 | 6 | 0 | 0 | 0
|  |  | Excavation | EXC | RFI | 9 | 9 | 0 | 0 | 0
|  |  | Pre-Concrete | PRC | RFI | 375 | 360 | 12 | 0 | 3
|  |  | Concrete | CON | RFI | 375 | 362 | 12 | 0 | 1
|  |  | Post-Concrete | PSC | RFI | 374 | 361 | 12 | 0 | 1
|  |  | As-Built | ASB | RFI | 326 | 312 | 12 | 0 | 2
|  |  | Cube Test | CUB | RFI | 0 | 0 | 0 | 0 | 0
|  |  | Backfilling | BFL | RFI | 13 | 13 | 0 | 0 | 0
|  |  | Field Density Test | FDT | RFI | 18 | 16 | 0 | 0 | 2
|  |  | Final Inspection | FNL | RFI | 1 | 1 | 0 | 0 | 0
| Total |  |  |  |  | 1544 | 1481 | 53 | 0 | 10 |  |  |  | Beginning Date | 2024-01-01
[14 empty] | ending date | 2025-12-31
02. Pending Items
| Item |  | ELECO
CIVIL WORK
RFI
| Ongoing |  | 53
| Pending Sign |  | 0
| Pending Attachment |  | 16
| Reschedule |  | 0
| On schedule |  | 0
| Total: |  | 69

## 01.RFI_TRM
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-30
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | [20 empty] | -
| 2 | Civil | [20 empty] | -
| 3 | Civil | [20 empty] | -
| 4 | Civil | [20 empty] | -
| 5 | Civil | [20 empty] | -
-
-
-
-
-
-
-
-
-

## 02.RFI_MRI
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-30
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 2 | Civil | [20 empty] | -
-
-
-
-
-
-
-
-
-
-
-
-

## 03.RFI_GLT
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-30
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-CVL-F-C300-GLT-0001 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection for anti termite work at Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-15 | 2024-11-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 2 | Civil | RFI-ELE-CVL-F-C300-GLT-0002 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over foundation PC 16 MAN Refiner to Mechanical | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-04 | 2024-12-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 3 | Civil | RFI-ELE-CVL-F-C300-GLT-0003 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over foundation PC4c,PC4d,PC8 MAN Refiner to Mechanical | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-16 | 2024-12-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 4 | Civil | RFI-ELE-CVL-F-C300-GLT-0004 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of Pile Integrity Test (PIT) for Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-20 | 2024-12-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 5 | Civil | RFI-ELE-CVL-F-C300-GLT-0005 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of embedded Cold Water Pipe Fitting for Ground Floor Substation C2105 prior to slab/ equipment casting | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-02 | 2025-01-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 6 | Civil | RFI-ELE-CVL-F-C300-GLT-0006 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over foundation PC8a TK-16201B MAN Refiner to Mechanical | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-06 | 2025-01-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 7 | Civil | RFI-ELE-CVL-F-C300-GLT-0007 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over foundation PC4 VP-16218 MAN Refiner to Mechanical | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-06 | 2025-01-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 8 | Civil | RFI-ELE-CVL-F-C300-GLT-0008 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of HDPE membrane installation for DEMIN Water Tank TK 18203 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-11 | 2025-01-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 9 | Civil | RFI-ELE-CVL-F-C300-GLT-0009 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of 50 mm sand bitumen layer at Tank TK 18230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-15 | 2025-01-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 10 | Civil | RFI-ELE-CVL-F-C300-GLT-0010 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over foundation Tank 18203 to Mechanical | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-21 | 2025-01-21 | 4.00 PM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 11 | Civil | RFI-ELE-CVL-F-C300-GLT-0011 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over foundation PC8b (D-16246) at Man Refiner to Mechanical | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-23 | 2025-01-24 | 4.00 PM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 12 | Civil | RFI-ELE-CVL-F-C300-GLT-0012 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over foundation D-2806 ( EV) to Mechanical | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-04 | 2025-02-05 | 4.00 PM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 13 | Civil | RFI-ELE-CVL-F-C300-GLT-0013 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over foundation PC24 ( fixed saddle ) Man Refiner to Mechanical | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 14 | Civil | RFI-ELE-CVL-F-C300-GLT-0014 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection for pedding installation work PC8a TK-18201B Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-19 | 2025-02-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Cancelled | -
| 15 | Civil | RFI-ELE-CVL-F-C300-GLT-0015 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection for pedding installation work PC8a TK-18201B Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-22 | 2025-02-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 16 | Civil | RFI-ELE-CVL-F-C300-GLT-0016 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection for material receiving for PC8a TK-18201B Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-27 | 2025-02-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 17 | Civil | RFI-ELE-CVL-F-C300-GLT-0017 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection for AAC block installation mock up (Brickwork) at Substation C2105) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-05 | 2025-03-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 18 | Civil | RFI-ELE-CVL-F-C300-GLT-0018 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection for roof slab repair with waterproofing at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-19 | 2025-03-19 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 19 | Civil | RFI-ELE-CVL-F-C300-GLT-0019 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over foundation F2 P-18201 A and B Man Refiner to Mechanical | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-21 | 2025-03-22 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 20 | Civil | RFI-ELE-CVL-F-C300-GLT-0020 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over foundation EDG CG01, Transformer T101 and T102 at Substation C2105 to E&I | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-21 | 2025-03-22 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 21 | Civil | RFI-ELE-CVL-F-C300-GLT-0021 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over foundation P-16247, P-16214, P-16224, P-18203 A and P-18203 A | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-05 | 2025-04-07 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 22 | Civil | RFI-ELE-CVL-F-C300-GLT-0022 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of Anti termite laying for Briquetting Building before ground slab | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 9:00 | H | W | N/A | R | Hanis | C300 | Accepted
| 23 | Civil | RFI-ELE-CVL-F-C300-GLT-0023 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of mock up for carborundum finish for Briquetting and Substation surface finish | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-18 | 2025-04-19 | 9:00 | H | W | N/A | R | Hanis | C300 | Accepted | PNDG ATTCH
| 24 | Civil | RFI-ELE-CVL-F-C300-GLT-0024 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over ACCU Foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-22 | 2025-04-23 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted | PNDG ATTCH
| 25 | Civil | RFI-ELE-CVL-F-C300-GLT-0025 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over Pump Foundation P-16204 A and P-16204 B to Mechanical | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-24 | 2025-04-25 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted | PNDG ATTCH
| 26 | Civil | RFI-ELE-CVL-F-C300-GLT-0026 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of pertially handing over groundslab GL A-C/10-12 at Briquetting Building to Structural | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-24 | 2025-04-25 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted | PNDG ATTCH
| 27 | Civil | RFI-ELE-CVL-F-C300-GLT-0027 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of anti termite laying for Briquetting Building GL A-C/7-9 before ground slab | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-03 | 2025-05-05 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted | PNDG ATTCH
| 28 | Civil | RFI-ELE-CVL-F-C300-GLT-0028 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over foundation Control Panel, AHU 01A and AHU 01B HVAC Room at Substation C2105 to Electrical | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-15 | 2025-05-16 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted | PNDG ATTCH
| 29 | Civil | RFI-ELE-CVL-F-C300-GLT-0029 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over battery foundation for Battery Room at Substation C2105 to Electrical | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-15 | 2025-05-16 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted | PNDG ATTCH
| 30 | Civil | RFI-ELE-CVL-F-C300-GLT-0030 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of pre final inspection for punchlisting at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-04 | 2025-06-05 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Ongoing | PNDG ATTCH
| 31 | Civil | RFI-ELE-CVL-F-C300-GLT-0031 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over pump foundation P-16211 A and B at Man Refiner to Mechanical | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-20 | 2025-06-21 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 32 | Civil | RFI-ELE-CVL-F-C300-GLT-0032 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over equpment foundation Strecth Hood Device (2 nos), Melt Tank D-19220 and Lift Z-19240, Silo Z-19208 A/B/C at Briquetting Building to Mechanical | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-15 | 2025-07-16 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 33 | Civil | RFI-ELE-CVL-F-C300-GLT-0033 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over equpment foundation PC 3 (E-18206) Foundation at Man Refiner to Mechanical | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-24 | 2025-07-25 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 34 | Civil | RFI-ELE-CVL-F-C300-GLT-0034 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over equpment foundation Z-18213A foundation for Chilled Water Package to Mechanical | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-24 | 2025-07-25 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 35 | Civil | RFI-ELE-CVL-F-C300-GLT-0035 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of bitumen installation for TK 16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-11 | 2025-08-12 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Ongoing | PNDG ATTCH
| 36 | Civil | RFI-ELE-CVL-F-C300-GLT-0036 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over equipment foundation TK 16230 Foundation at Man Refiner to Mechanical | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-11 | 2025-08-12 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted | PNDG ATTCH
| 37 | Civil | RFI-ELE-CVL-F-C300-GLT-0037 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of grouting for anchor bolt T19230 Foundation at Scubber Unit to Mechanical | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-11 | 2025-08-12 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Ongoing | PNDG ATTCH
| 38 | Civil | RFI-ELE-CVL-F-C300-GLT-0038 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over to D-16227 (F8) to Mechanical | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-26 | 2025-08-27 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 39 | Civil | RFI-ELE-CVL-F-C300-GLT-0039 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over T19230 Foundation and Pump Foundation P19231 A/B and P19232 A/B at Scubber Unit to Mechanical | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-26 | 2025-08-27 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 40 | Civil | RFI-ELE-CVL-F-C300-GLT-0040 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of grouting for anchor bolt TK 18203 Foundation Demin Water Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-28 | 2025-08-29 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Ongoing | PNDG ATTCH
| 41 | Civil | RFI-ELE-CVL-F-C300-GLT-0041 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of grouting for anchor bolt TK 16230 Foundation at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-08 | 2025-09-09 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Ongoing | PNDG ATTCH
| 42 | Civil | RFI-ELE-CVL-F-C300-GLT-0042 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over pump foundation for P-18204A/B at Demineralise Water Pump Foundation to Mechanical | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-18 | 2025-09-19 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 43 | Civil | RFI-ELE-CVL-F-C300-GLT-0043 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over foundation for P-16232 at Man Refiner to Mechanical | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-18 | 2025-09-19 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 44 | Civil | RFI-ELE-CVL-F-C300-GLT-0044 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of grouting for anchor bolt and steel plate PC 24 Foundation at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-13 | 2025-10-14 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 45 | Civil | RFI-ELE-CVL-F-C300-GLT-0045 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over foundation for S-19232 (Fan Foundation) and S-19233 (Chimney Foundation) at Man Refiner to Mechanical | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-14 | 2025-11-15 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 46 | Civil | RFI-ELE-CVL-F-C300-GLT-0046 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over foundation for P-19221 A/B at Briquetting Building to Mechanical | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-17 | 2025-11-18 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 47 | Civil | RFI-ELE-CVL-F-C300-GLT-0047 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of handing over foundation for D-18214 at DEMIN Water Tank to Mechanical | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-17 | 2025-11-18 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 48 | Civil | RFI-ELE-CVL-F-C300-GLT-0048 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of installation of perimeter precast U drain at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-13 | 2025-12-15 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 49 | Civil | RFI-ELE-CVL-F-C300-GLT-0049 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of installation of perimeter precast U drain (South) at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-03 | 2026-01-05 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 50 | Civil | RFI-ELE-CVL-F-C300-GLT-0050 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of installation of precast manhole MS3 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-03 | 2026-01-05 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 51 | Civil | RFI-ELE-CVL-F-C300-GLT-0051 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of installation of precast manhole MS4 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-09 | 2026-01-10 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 52 | Civil | RFI-ELE-CVL-F-C300-GLT-0052 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of GRE Pipe opening grout for MA5 - Gully Trap (GT-1) at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-12 | 2026-01-13 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 52 | Civil | RFI-ELE-CVL-F-C300-GLT-0053 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of anchor bolt grouting for TK 16230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-12 | 2026-01-13 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 52 | Civil | RFI-ELE-CVL-F-C300-GLT-0054 | External | ELECO | Civil Work | N/A | General Test | General Test | Inspection of foundation grouting for TK -18201B at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-24 | 2026-01-26 | 5.00 PM | H | W | N/A | R | Hanis | C300 | Accepted

## 04.RFI_SVW
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-30
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-CVL-F-C300-SVW-0001 | External | ELECO | Civil Work | N/A | Earth work | Survey | Inspection for setting out survey work at sub-station C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-05-30 | 2024-05-31 | 9:00 | H | W | N/A | R | Hanis | C300 | Accepted | -
| 2 | Civil | RFI-ELE-CVL-F-C300-SVW-0002 | External | ELECO | Civil Work | N/A | Earth work | Survey | Inspection for temporary benchmark for Sub-station C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-06-19 | 2024-06-20 | 9:00 | H | W | N/A | R | Hanis | C300 | Accepted | -
| 3 | Civil | RFI-ELE-CVL-F-C300-SVW-0003 | External | ELECO | Civil Work | N/A | Earth work | Survey | Inspection for survey work prior to pile cutting activity for Sub-station C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-16 | 2024-08-17 | 9:00 | H | W | N/A | R | Hanis | C300 | Accepted | -
| 4 | Civil | RFI-ELE-CVL-F-C300-SVW-0004 | External | ELECO | Civil Work | N/A | Earth work | Survey | Inspection for survey work prior to pile cutting activity for Sub-station C-2106 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-17 | 2024-09-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 5 | Civil | RFI-ELE-CVL-F-C300-SVW-0005 | External | ELECO | Civil Work | N/A | Earth work | Survey | Inspection for survey work prior to pile cutting activity for MAn Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-24 | 2024-10-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 6 | Civil | RFI-ELE-CVL-F-C300-SVW-0006 | External | ELECO | Civil Work | N/A | Earth work | Survey | Inspection for survey work prior to pile cutting activity for Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-23 | 2024-11-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
-
-
-
-
-
-
-
-

## 05.RFI_EXC
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-30
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-CVL-F-C300-EXC-0001 | External | Eleco | Civil Work | N/A | Earth Work | Excavation | Inspection for excavation work at Substation C-2105 building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-07-22 | 2024-07-23 | 9:00 | H | W | N/A | R | Hanis | C300 | Accepted | -
| 2 | Civil | RFI-ELE-CVL-F-C300-EXC-0002 | External | Eleco | Civil Work | N/A | Earth Work | Excavation | Inspection for excavation work prior to foundation installation for Substation C-2105 building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-16 | 2024-08-17 | 9:00 | H | W | N/A | R | Hanis | C300 | Accepted | -
| 3 | Civil | RFI-ELE-CVL-F-C300-EXC-0003 | External | Eleco | Civil Work | N/A | Earth Work | Excavation | Inspection for excavation work prior to foundation installation for Substation C-2105 building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-17 | 2024-09-18 | 9.00AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 4 | Civil | RFI-ELE-CVL-F-C300-EXC-0004 | External | Eleco | Civil Work | N/A | Earth Work | Excavation | Inspection for excavation work prior to foundation installation for Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-24 | 2024-10-25 | 9.00AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 5 | Civil | RFI-ELE-CVL-F-C300-EXC-0005 | External | Eleco | Civil Work | N/A | Earth Work | Excavation | Inspection for excavation work prior to foundation installation for Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-06 | 2025-01-07 | 9.00AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 6 | Civil | RFI-ELE-CVL-F-C300-EXC-0006 | External | Eleco | Civil Work | N/A | Earth Work | Excavation | Inspection for excavation work prior to foundation installation for Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-24 | 2025-09-25 | 9.00AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 7 | Civil | RFI-ELE-CVL-F-C300-EXC-0007 | External | Eleco | Civil Work | N/A | Earth Work | Excavation | Inspection for excavation work prior to foundation installation for Chilled Water Package | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-24 | 2025-09-25 | 9.00AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 8 | Civil | RFI-ELE-CVL-F-C300-EXC-0008 | External | Eleco | Civil Work | N/A | Earth Work | Excavation | Inspection for excavation work prior to GRE laying around C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-24 | 2025-09-25 | 9.00AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 8 | Civil | RFI-ELE-CVL-F-C300-EXC-0008 | External | Eleco | Civil Work | N/A | Earth Work | Excavation | Inspection for excavation work prior to Manholes around C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-24 | 2025-09-25 | 9.00AM | H | W | N/A | R | Hanis | C300 | Accepted | -
-
-
-
-
-

## 06.RFI_PRC
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-30
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-CVL-F-C300-PRC-0001 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pile plug installation for Sub-station C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-17 | 2024-08-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 2 | Civil | RFI-ELE-CVL-F-C300-PRC-0002 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap's leancon for Sub-station C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-18 | 2024-08-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 3 | Civil | RFI-ELE-CVL-F-C300-PRC-0003 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap's leancon for Sub-station C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-23 | 2024-08-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 4 | Civil | RFI-ELE-CVL-F-C300-PRC-0004 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pile plug installation for Sub-station C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-23 | 2024-08-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 5 | Civil | RFI-ELE-CVL-F-C300-PRC-0005 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-26 | 2024-08-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 6 | Civil | RFI-ELE-CVL-F-C300-PRC-0006 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-29 | 2024-08-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 7 | Civil | RFI-ELE-CVL-F-C300-PRC-0007 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-04 | 2024-09-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 8 | Civil | RFI-ELE-CVL-F-C300-PRC-0008 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of stump for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-04 | 2024-09-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 9 | Civil | RFI-ELE-CVL-F-C300-PRC-0009 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-06 | 2024-09-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 10 | Civil | RFI-ELE-CVL-F-C300-PRC-0010 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pile plug installation for Sub-station C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-21 | 2024-09-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 11 | Civil | RFI-ELE-CVL-F-C300-PRC-0011 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap's leancon for Sub-station C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-21 | 2024-09-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 12 | Civil | RFI-ELE-CVL-F-C300-PRC-0012 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-24 | 2024-09-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 13 | Civil | RFI-ELE-CVL-F-C300-PRC-0013 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of broken pile rectification for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-24 | 2024-09-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 14 | Civil | RFI-ELE-CVL-F-C300-PRC-0014 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-26 | 2024-09-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 15 | Civil | RFI-ELE-CVL-F-C300-PRC-0015 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of stump for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-30 | 2024-10-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 16 | Civil | RFI-ELE-CVL-F-C300-PRC-0016 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of groundbeam leancon Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-04 | 2024-10-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 17 | Civil | RFI-ELE-CVL-F-C300-PRC-0017 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of groundbeam Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-19 | 2024-10-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 18 | Civil | RFI-ELE-CVL-F-C300-PRC-0018 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of groundbeam Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-22 | 2024-10-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 19 | Civil | RFI-ELE-CVL-F-C300-PRC-0019 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pileplug installation MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-12 | 2024-11-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 20 | Civil | RFI-ELE-CVL-F-C300-PRC-0020 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation leancon MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-12 | 2024-11-13 | 9.00 AM | H | w | N/A | R | Hanis | C300 | Accepted | PNDG ATTCH
| 21 | Civil | RFI-ELE-CVL-F-C300-PRC-0021 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pileplug installation MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-14 | 2024-11-15 | 9.00 AM | H | w | N/A | R | Hanis | C300 | Accepted
| 22 | Civil | RFI-ELE-CVL-F-C300-PRC-0022 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation leancon MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-14 | 2024-11-15 | 9.00 AM | H | w | N/A | R | Hanis | C300 | Accepted
| 23 | Civil | RFI-ELE-CVL-F-C300-PRC-0023 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of groundslab leancon Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-15 | 2024-11-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | PNDG ATTCH
| 24 | Civil | RFI-ELE-CVL-F-C300-PRC-0024 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation PC16 MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-16 | 2024-11-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 25 | Civil | RFI-ELE-CVL-F-C300-PRC-0025 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pileplug installation MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-18 | 2024-11-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 26 | Civil | RFI-ELE-CVL-F-C300-PRC-0026 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation leancon MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-18 | 2024-11-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | PNDG ATTCH
| 27 | Civil | RFI-ELE-CVL-F-C300-PRC-0027 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-23 | 2024-11-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 28 | Civil | RFI-ELE-CVL-F-C300-PRC-0028 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pileplug installation MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-23 | 2024-11-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 29 | Civil | RFI-ELE-CVL-F-C300-PRC-0029 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation leancon MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-23 | 2024-11-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 30 | Civil | RFI-ELE-CVL-F-C300-PRC-0030 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pileplug installation for Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-23 | 2024-11-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 31 | Civil | RFI-ELE-CVL-F-C300-PRC-0031 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation leancon for Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-23 | 2024-11-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 32 | Civil | RFI-ELE-CVL-F-C300-PRC-0032 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-29 | 2024-11-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 33 | Civil | RFI-ELE-CVL-F-C300-PRC-0033 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation PC16 top MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-29 | 2024-12-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 34 | Civil | RFI-ELE-CVL-F-C300-PRC-0034 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for groundslab Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-29 | 2024-12-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 35 | Civil | RFI-ELE-CVL-F-C300-PRC-0035 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for groundbeam Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-04 | 2024-12-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 36 | Civil | RFI-ELE-CVL-F-C300-PRC-0036 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean concrete at AHU-01A and B and HVAC control panel Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-07 | 2024-12-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 37 | Civil | RFI-ELE-CVL-F-C300-PRC-0037 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean concrete at PC4c and PC4 Man refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-07 | 2024-12-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 38 | Civil | RFI-ELE-CVL-F-C300-PRC-0038 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for column G/level to 1st level GL A-D/2-3 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-09 | 2024-12-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 39 | Civil | RFI-ELE-CVL-F-C300-PRC-0039 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Pilecap Man Refiner Foundation PC4c and PC4d | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-10 | 2024-12-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 40 | Civil | RFI-ELE-CVL-F-C300-PRC-0040 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pileplug Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-10 | 2024-12-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 41 | Civil | RFI-ELE-CVL-F-C300-PRC-0041 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Pilecap Man Refiner Foundation PC4c topside, PC4d topside, PC8 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-12 | 2024-12-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 42 | Civil | RFI-ELE-CVL-F-C300-PRC-0042 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for EDG Foundation at Substation C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-13 | 2024-12-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 43 | Civil | RFI-ELE-CVL-F-C300-PRC-0043 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for column G/level to 1st level GL A-D/4-5a Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-13 | 2024-12-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 44 | Civil | RFI-ELE-CVL-F-C300-PRC-0044 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for column G/level to 1st level GL A-D/1x, GL C-D/1, GL A/5-7, GL B/7 and GL B1/5 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-17 | 2024-12-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 45 | Civil | RFI-ELE-CVL-F-C300-PRC-0045 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean concrete at PC6a, PC2b, 3 nos of PC2 and PC8a | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-17 | 2024-12-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 46 | Civil | RFI-ELE-CVL-F-C300-PRC-0046 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for PilePlug at PC6a, PC2b, 3 nos of PC2 and PC8a | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-17 | 2024-12-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 47 | Civil | RFI-ELE-CVL-F-C300-PRC-0047 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for column G/level to 1st level GL B1-D / 6-8, GL C1/5A and GL D/5 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-19 | 2024-12-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 48 | Civil | RFI-ELE-CVL-F-C300-PRC-0048 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean concrete at PC2b, PC2 and PC9 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-19 | 2024-12-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 49 | Civil | RFI-ELE-CVL-F-C300-PRC-0049 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for PilePlug at PC2b, PC2 and PC9 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-19 | 2024-12-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 50 | Civil | RFI-ELE-CVL-F-C300-PRC-0050 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Pilecap Man Refiner Foundation PC6a, PC8a, PC2 (2 unit) and PC2b | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-20 | 2024-12-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 51 | Civil | RFI-ELE-CVL-F-C300-PRC-0051 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Pileplug Man Refiner Foundation PC9, PC2b, PC6b, PC2 and PC2a | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-20 | 2024-12-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 52 | Civil | RFI-ELE-CVL-F-C300-PRC-0052 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Leancon Man Refiner Foundation PC6b, PC2 and PC2a | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-20 | 2024-12-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 53 | Civil | RFI-ELE-CVL-F-C300-PRC-0053 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Pilecap Transformer MCC-A and MCC-B foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-20 | 2024-12-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 54 | Civil | RFI-ELE-CVL-F-C300-PRC-0054 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Pilecap PC9, PC2b and PC2 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-21 | 2024-12-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 55 | Civil | RFI-ELE-CVL-F-C300-PRC-0055 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for 2nd Cast PC8a at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-23 | 2024-12-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 56 | Civil | RFI-ELE-CVL-F-C300-PRC-0056 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for leancon Man Refiner Foundation PC4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-23 | 2024-12-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 57 | Civil | RFI-ELE-CVL-F-C300-PRC-0057 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pedestal C1 PC 11, GL A/3, for Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-23 | 2024-12-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 58 | Civil | RFI-ELE-CVL-F-C300-PRC-0058 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap PC4 and PC6b at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 59 | Civil | RFI-ELE-CVL-F-C300-PRC-0059 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for leancon PC2, PC2a, PC2b/C1 and PC24 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 60 | Civil | RFI-ELE-CVL-F-C300-PRC-0060 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pileplug PC2, PC2a, PC2b/C1 and PC24 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 61 | Civil | RFI-ELE-CVL-F-C300-PRC-0061 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Pedestal C1 for PC11, PC8, PC6a and PC2b | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 62 | Civil | RFI-ELE-CVL-F-C300-PRC-0062 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for leancon for TK-18203 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 63 | Civil | RFI-ELE-CVL-F-C300-PRC-0063 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pileplug for TK-18203 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 64 | Civil | RFI-ELE-CVL-F-C300-PRC-0064 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pedestal for pilecap PC6c, PC6, PC5, PC12, PC8a, PC9, PC2 and PC2a | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-26 | 2024-12-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 65 | Civil | RFI-ELE-CVL-F-C300-PRC-0065 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pedestal for pilecap PC11, PC2 (2 nos), PC1 and PC6b | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-27 | 2024-12-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 66 | Civil | RFI-ELE-CVL-F-C300-PRC-0066 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap PC2,PC2a, PC2b at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-27 | 2024-12-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 67 | Civil | RFI-ELE-CVL-F-C300-PRC-0067 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for leancon pilecap PC2a at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-27 | 2024-12-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 68 | Civil | RFI-ELE-CVL-F-C300-PRC-0068 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pileplug pilecap PC2a at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-27 | 2024-12-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 69 | Civil | RFI-ELE-CVL-F-C300-PRC-0069 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap PC5/C1 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-28 | 2024-12-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 70 | Civil | RFI-ELE-CVL-F-C300-PRC-0070 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pedestal for pilecap PC2/PS, PC2a/PS, PC2b/PS at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-28 | 2024-12-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 71 | Civil | RFI-ELE-CVL-F-C300-PRC-0071 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean con for pilecap PC 8b and PC4/C1 (2 nos) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-28 | 2024-12-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 72 | Civil | RFI-ELE-CVL-F-C300-PRC-0072 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pileplug for pilecap PC 8b and PC4/C1 (2 nos) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-28 | 2024-12-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 73 | Civil | RFI-ELE-CVL-F-C300-PRC-0073 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pedestal for pilecap PC5 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-30 | 2024-12-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 74 | Civil | RFI-ELE-CVL-F-C300-PRC-0074 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for leancon for pilecap PC6d/C1 , PC12/C1 and PC8b | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-31 | 2025-01-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 75 | Civil | RFI-ELE-CVL-F-C300-PRC-0075 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap PC4/C1 2 nos at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-31 | 2025-01-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 76 | Civil | RFI-ELE-CVL-F-C300-PRC-0076 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection pedestal PC2a/C1 GL d/7 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-01 | 2025-01-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 77 | Civil | RFI-ELE-CVL-F-C300-PRC-0077 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection pilecap PC24 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-02 | 2025-01-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 78 | Civil | RFI-ELE-CVL-F-C300-PRC-0078 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection pedestal PC2b/C1 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-02 | 2025-01-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 79 | Civil | RFI-ELE-CVL-F-C300-PRC-0079 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection leancon for PC6d/C1 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-02 | 2025-01-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 80 | Civil | RFI-ELE-CVL-F-C300-PRC-0080 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection pileplug for PC6d/C1 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-02 | 2025-01-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 81 | Civil | RFI-ELE-CVL-F-C300-PRC-0081 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection pilecap for PC5, PC12/C1 GL E/5, and PC8b at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-03 | 2025-01-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 82 | Civil | RFI-ELE-CVL-F-C300-PRC-0082 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection pilecap for AHU-01 A and 01B, HVAC Control Panel Foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-03 | 2025-01-03 | 6.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 83 | Civil | RFI-ELE-CVL-F-C300-PRC-0083 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap PC8b,PC12/C1,PC6d/C1 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-05 | 2025-01-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 84 | Civil | RFI-ELE-CVL-F-C300-PRC-0084 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pedestal PC4/C1 (2nos) Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-05 | 2025-01-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 85 | Civil | RFI-ELE-CVL-F-C300-PRC-0085 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection leancon for pilecap GL A-A2 - 27' -29' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-06 | 2025-01-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 86 | Civil | RFI-ELE-CVL-F-C300-PRC-0086 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal PC12, PC 6d, PC8b and PC24 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-07 | 2025-01-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 87 | Civil | RFI-ELE-CVL-F-C300-PRC-0087 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of foundation TK 18203 Demin Water Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-08 | 2025-01-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 88 | Civil | RFI-ELE-CVL-F-C300-PRC-0088 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal PC24 (saddle) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-09 | 2025-01-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 89 | Civil | RFI-ELE-CVL-F-C300-PRC-0089 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation leancon Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-10 | 2025-01-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 90 | Civil | RFI-ELE-CVL-F-C300-PRC-0090 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation leancon Briquetting Building-PC22,PC6 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-15 | 2025-01-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 91 | Civil | RFI-ELE-CVL-F-C300-PRC-0091 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation pileplug for PC22, PC6, PC5a and PC5 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-16 | 2025-01-16 | 4.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 92 | Civil | RFI-ELE-CVL-F-C300-PRC-0092 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for slab and beam 1st floor for Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-16 | 2025-01-17 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 93 | Civil | RFI-ELE-CVL-F-C300-PRC-0093 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap GL A-A2 - 27' -29' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-16 | 2025-01-17 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 94 | Civil | RFI-ELE-CVL-F-C300-PRC-0094 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal PC24 (free saddle) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-17 | 2025-01-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 95 | Civil | RFI-ELE-CVL-F-C300-PRC-0095 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of column GL A-D/1X at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-22 | 2025-01-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 96 | Civil | RFI-ELE-CVL-F-C300-PRC-0096 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap GL A1' -A2'/ 28' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-22 | 2025-01-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 97 | Civil | RFI-ELE-CVL-F-C300-PRC-0097 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal GL A1' -A2'/ 29' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-22 | 2025-01-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 98 | Civil | RFI-ELE-CVL-F-C300-PRC-0098 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap PC6 and PC5a at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-23 | 2025-01-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 99 | Civil | RFI-ELE-CVL-F-C300-PRC-0099 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon for pilecap D-2806 at Esstar Vision Compound | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-25 | 2025-01-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 100 | Civil | RFI-ELE-CVL-F-C300-PRC-0100 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap D-2806 at Esstar Vision Compound | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-25 | 2025-01-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 101 | Civil | RFI-ELE-CVL-F-C300-PRC-0101 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap GL A-C/1-4 for Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-27 | 2025-01-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 102 | Civil | RFI-ELE-CVL-F-C300-PRC-0102 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pileplug PC6/C1 (3nos),PC6a/C1 (2nos) and PC6c/C1 for Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-27 | 2025-01-27 | 6.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 103 | Civil | RFI-ELE-CVL-F-C300-PRC-0103 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of column GL A-D/4-8 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-31 | 2025-02-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 104 | Civil | RFI-ELE-CVL-F-C300-PRC-0104 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon for pilecap PC6/C1 and PC8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-31 | 2025-02-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 105 | Civil | RFI-ELE-CVL-F-C300-PRC-0105 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap PC6/C1, PC6c/C1 and PC6a/C1 GL A-B/3-4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-01 | 2025-02-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 106 | Civil | RFI-ELE-CVL-F-C300-PRC-0106 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of stump column at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-04 | 2025-02-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 107 | Civil | RFI-ELE-CVL-F-C300-PRC-0107 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pileplug at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-04 | 2025-02-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 108 | Civil | RFI-ELE-CVL-F-C300-PRC-0108 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap GL A1' -A2'/ 27-29 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 109 | Civil | RFI-ELE-CVL-F-C300-PRC-0109 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal GL A1' -A2'/27- 29' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 110 | Civil | RFI-ELE-CVL-F-C300-PRC-0110 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of column 1st-RL GL B-D/2-3 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 111 | Civil | RFI-ELE-CVL-F-C300-PRC-0111 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of stump column at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Cancelled
| 112 | Civil | RFI-ELE-CVL-F-C300-PRC-0112 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pileplug at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 113 | Civil | RFI-ELE-CVL-F-C300-PRC-0113 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of stump column at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-06 | 2024-02-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 114 | Civil | RFI-ELE-CVL-F-C300-PRC-0114 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-06 | 2024-02-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 115 | Civil | RFI-ELE-CVL-F-C300-PRC-0115 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-07 | 2024-02-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 116 | Civil | RFI-ELE-CVL-F-C300-PRC-0116 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon for pilecap at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-07 | 2024-02-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 117 | Civil | RFI-ELE-CVL-F-C300-PRC-0117 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pileplug at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-07 | 2024-02-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 118 | Civil | RFI-ELE-CVL-F-C300-PRC-0118 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of raft foundation Battery Room at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-07 | 2024-02-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 119 | Civil | RFI-ELE-CVL-F-C300-PRC-0119 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of column 1st-RL at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-08 | 2024-02-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 120 | Civil | RFI-ELE-CVL-F-C300-PRC-0120 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pileplug at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-11 | 2024-02-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 121 | Civil | RFI-ELE-CVL-F-C300-PRC-0121 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon for pilecap at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-11 | 2024-02-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 122 | Civil | RFI-ELE-CVL-F-C300-PRC-0122 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-11 | 2024-02-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 123 | Civil | RFI-ELE-CVL-F-C300-PRC-0123 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of stump column at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-11 | 2024-02-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 124 | Civil | RFI-ELE-CVL-F-C300-PRC-0124 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap GL A1' -A2'/ 27-29 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-11 | 2024-02-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 125 | Civil | RFI-ELE-CVL-F-C300-PRC-0125 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal GL A1' -A2'/27- 29' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-13 | 2024-02-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 126 | Civil | RFI-ELE-CVL-F-C300-PRC-0126 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of column 1st-RL at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-11 | 2024-02-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 127 | Civil | RFI-ELE-CVL-F-C300-PRC-0127 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap PC3/C2 GL C/9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 128 | Civil | RFI-ELE-CVL-F-C300-PRC-0128 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon PC7a/C1 and PC6b/C1 GL B/5-6 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 129 | Civil | RFI-ELE-CVL-F-C300-PRC-0129 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pileplug PC7a/C1 and PC6b/C1 GL B/5-6 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 130 | Civil | RFI-ELE-CVL-F-C300-PRC-0130 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon Groundbeam GL A/1-2, A-C/1 and C/1-4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 131 | Civil | RFI-ELE-CVL-F-C300-PRC-0131 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal PC4/C2 GL C/8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 132 | Civil | RFI-ELE-CVL-F-C300-PRC-0132 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap Z-19208A Weighing Machines and Silo Foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-19 | 2025-02-19 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 133 | Civil | RFI-ELE-CVL-F-C300-PRC-0133 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap PC6b and PC6d GL B/6-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-19 | 2025-02-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 134 | Civil | RFI-ELE-CVL-F-C300-PRC-0134 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap PC7a/C1 GL B/5 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-20 | 2025-02-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 135 | Civil | RFI-ELE-CVL-F-C300-PRC-0135 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon PC3/C2 GL C/10 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-20 | 2025-02-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 136 | Civil | RFI-ELE-CVL-F-C300-PRC-0136 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pileplug PC3/C2 GL C/10 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-20 | 2025-02-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 137 | Civil | RFI-ELE-CVL-F-C300-PRC-0137 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal PC3/C2 GL C/9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-20 | 2025-02-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 138 | Civil | RFI-ELE-CVL-F-C300-PRC-0138 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of roof slab and beam at GL A-D/4-8 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-22 | 2025-02-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 139 | Civil | RFI-ELE-CVL-F-C300-PRC-0139 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of roof beam at GL A-D/1x-1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-22 | 2025-02-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 140 | Civil | RFI-ELE-CVL-F-C300-PRC-0140 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of ground beam Gl A-C/ 1-5 for Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-25 | 2025-02-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 141 | Civil | RFI-ELE-CVL-F-C300-PRC-0141 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap PC3/C2 GL C/10 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-25 | 2025-02-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 142 | Civil | RFI-ELE-CVL-F-C300-PRC-0142 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean con for PC4/C2 (2 nos) GL C/11-12, Z-19208B, Z-19240 Equipment foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-25 | 2025-02-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 143 | Civil | RFI-ELE-CVL-F-C300-PRC-0143 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pileplug for PC4/C2 (2 nos) GL C/11-12, Z-19208B, Z-19240 Equipment foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-25 | 2025-02-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 144 | Civil | RFI-ELE-CVL-F-C300-PRC-0144 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of foundation pilecap Z-19208B & D-19220 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-27 | 2025-02-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 145 | Civil | RFI-ELE-CVL-F-C300-PRC-0145 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap for PC4/C2 (2 nos) GL C/11-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-27 | 2025-02-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 146 | Civil | RFI-ELE-CVL-F-C300-PRC-0146 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap for PC4/C2 GL A/12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-28 | 2025-03-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 147 | Civil | RFI-ELE-CVL-F-C300-PRC-0147 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean con for PC6/C1 and PC7/C1 GL A/5-6, and Z-19208C at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-28 | 2025-03-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 148 | Civil | RFI-ELE-CVL-F-C300-PRC-0148 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilepug for PC6/C1 and PC7/C1 GL A/5-6, and Z-19208C at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-28 | 2025-03-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 149 | Civil | RFI-ELE-CVL-F-C300-PRC-0149 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of roof slab GL A-D/1-4 for Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-03 | 2025-03-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 150 | Civil | RFI-ELE-CVL-F-C300-PRC-0150 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pile cap PC6/C1 GL A/4-5 and Z-19208C at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-04 | 2025-03-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 151 | Civil | RFI-ELE-CVL-F-C300-PRC-0151 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of groundbeam GL C/4-9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-04 | 2025-03-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 152 | Civil | RFI-ELE-CVL-F-C300-PRC-0152 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean con PC3/C2 (2nos) GL A/9-10 and PC4/C2 (2nos) GL A/11 and B/12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-04 | 2025-03-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 153 | Civil | RFI-ELE-CVL-F-C300-PRC-0153 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pileplug PC3/C2 (2nos) GL A/9-10 and PC4/C2 (2nos) GL A/11 and B/12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-04 | 2025-03-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 154 | Civil | RFI-ELE-CVL-F-C300-PRC-0154 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal PC5a, PC6a, PC6, PC7a, PC6b, and PC6d GL B/2-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-04 | 2025-03-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 155 | Civil | RFI-ELE-CVL-F-C300-PRC-0155 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean con P-18201A and P-18201B Pump Foundation at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-05 | 2025-03-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 156 | Civil | RFI-ELE-CVL-F-C300-PRC-0156 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap PC4/C2 (2 nos), PC3/C2 (2 nos) GL A/8-11 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 157 | Civil | RFI-ELE-CVL-F-C300-PRC-0157 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of Pedestal 2nd cast PC5/C1 GL B/1, PC6/C1 (3 nos), PC6a/C1 (2 nos), PC7/C1 (2 nos) and PC4/C2 GL A/1-8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 158 | Civil | RFI-ELE-CVL-F-C300-PRC-0158 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of groundbeam GL A/1-4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 159 | Civil | RFI-ELE-CVL-F-C300-PRC-0159 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal PC3/C2 and PC4/C2 (2nos) GL C/10-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 160 | Civil | RFI-ELE-CVL-F-C300-PRC-0160 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap PC4/C2 GL B/12, PC7/C1 GL A/6 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 161 | Civil | RFI-ELE-CVL-F-C300-PRC-0161 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon PC4/C2 GL A/8, PC3/C2 GL A/9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 162 | Civil | RFI-ELE-CVL-F-C300-PRC-0162 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pileplug PC4/C2 GL A/8, PC3/C2 GL A/9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 163 | Civil | RFI-ELE-CVL-F-C300-PRC-0163 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Pump Foundation P-18201A and P-18201B at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-07 | 2025-03-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 164 | Civil | RFI-ELE-CVL-F-C300-PRC-0164 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean concrete and pile plug Stretch Hood Device and ground beam GL A 4-6 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 165 | Civil | RFI-ELE-CVL-F-C300-PRC-0165 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap foundation Stretch Hood Device at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 166 | Civil | RFI-ELE-CVL-F-C300-PRC-0166 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap foundation D-19220 Foundation Melt Tank at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 167 | Civil | RFI-ELE-CVL-F-C300-PRC-0167 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of groundbeam GL A/4-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 168 | Civil | RFI-ELE-CVL-F-C300-PRC-0168 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of 2nd cast pedestal PC6/C1 (2nos) and PC6a/C1 GL A/1-4 Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 169 | Civil | RFI-ELE-CVL-F-C300-PRC-0169 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal PC4/C2 (4nos) and PC3/C2 (3nos) GL A-B/8-12 Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 170 | Civil | RFI-ELE-CVL-F-C300-PRC-0170 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of cast fascia GL A-D/ 4-8 at roof floor Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 171 | Civil | RFI-ELE-CVL-F-C300-PRC-0171 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of Lean concrete for ground beam GL A-C/8-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 172 | Civil | RFI-ELE-CVL-F-C300-PRC-0172 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of Lean concrete for PC7/C1 GL A/7 and foundation Stretch Hood Device GL A/8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 173 | Civil | RFI-ELE-CVL-F-C300-PRC-0173 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal for PC6a/C1 and PC6/C1 GL A/4-5 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 174 | Civil | RFI-ELE-CVL-F-C300-PRC-0174 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of groundbeam for GL A-C/8 -12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-13 | 2025-03-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 175 | Civil | RFI-ELE-CVL-F-C300-PRC-0175 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap for foundation Stretch Hood Device GL A/8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-13 | 2025-03-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 176 | Civil | RFI-ELE-CVL-F-C300-PRC-0176 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal for PC3/C2 (2 nos) and PC4/C2 (3 nos) GL B-C/9-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-14 | 2025-03-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 177 | Civil | RFI-ELE-CVL-F-C300-PRC-0177 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pedestal foundation D-19220 Foundation Melt Tank at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-14 | 2025-03-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 178 | Civil | RFI-ELE-CVL-F-C300-PRC-0178 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of Lean concrete for PC7/C1 GL A/7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-14 | 2025-03-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 179 | Civil | RFI-ELE-CVL-F-C300-PRC-0179 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pileplug for PC7/C1 GL A/7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-14 | 2025-03-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 180 | Civil | RFI-ELE-CVL-F-C300-PRC-0180 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of cast fascia GL A-D/ 4at roof floor Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-15 | 2025-03-17 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 181 | Civil | RFI-ELE-CVL-F-C300-PRC-0181 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal for PC3/C2 (2 nos) and PC4/C2 (3 nos) GL A-B/9-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-15 | 2025-03-17 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 182 | Civil | RFI-ELE-CVL-F-C300-PRC-0182 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap for PC7/C1 GL A/7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-17 | 2025-03-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 183 | Civil | RFI-ELE-CVL-F-C300-PRC-0183 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal for PC7/C1 GL A/7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-18 | 2025-03-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 184 | Civil | RFI-ELE-CVL-F-C300-PRC-0184 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon groundbeam for GL A/6-8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-18 | 2025-03-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 185 | Civil | RFI-ELE-CVL-F-C300-PRC-0185 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of groundbeam for GL A/6-8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-20 | 2025-03-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 186 | Civil | RFI-ELE-CVL-F-C300-PRC-0186 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean concrete at P-16214 and P-16247 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-22 | 2025-03-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 187 | Civil | RFI-ELE-CVL-F-C300-PRC-0187 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean concrete at P-18203A (2 nos) and P-16224 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-24 | 2025-03-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 188 | Civil | RFI-ELE-CVL-F-C300-PRC-0188 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of foundation afor P-18203A (2 nos), P-16214, P-16247 and P-16224 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-26 | 2025-03-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 189 | Civil | RFI-ELE-CVL-F-C300-PRC-0189 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean concrete for groundslab GL A-C/10-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-10 | 2025-04-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 190 | Civil | RFI-ELE-CVL-F-C300-PRC-0190 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean concrete for Pump foundation at Esstar Vission Compound | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-10 | 2025-04-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 191 | Civil | RFI-ELE-CVL-F-C300-PRC-0191 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of foudation for Pump foundation at Esstar Vission Compound | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-16 | 2025-04-17 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 192 | Civil | RFI-ELE-CVL-F-C300-PRC-0192 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean concrete GL B-C/1-7 for groundslab Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-16 | 2025-04-17 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 193 | Civil | RFI-ELE-CVL-F-C300-PRC-0193 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean concrete ACCU Foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-16 | 2025-04-17 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 194 | Civil | RFI-ELE-CVL-F-C300-PRC-0194 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of groundslab GL A-C/10-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-17 | 2025-04-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 195 | Civil | RFI-ELE-CVL-F-C300-PRC-0195 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of ACCU Foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-18 | 2025-04-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 196 | Civil | RFI-ELE-CVL-F-C300-PRC-0196 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of F9 Foundation at Man Refiner GL A-B/9 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-22 | 2025-04-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 197 | Civil | RFI-ELE-CVL-F-C300-PRC-0197 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon for non suspended slab HVAC Room Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-29 | 2025-04-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 198 | Civil | RFI-ELE-CVL-F-C300-PRC-0198 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon groundslab GL A-C/7-9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-03 | 2025-05-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 199 | Civil | RFI-ELE-CVL-F-C300-PRC-0199 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of ground slab GL A-C/7-9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-12 | 2025-05-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 200 | Civil | RFI-ELE-CVL-F-C300-PRC-0200 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean con ground slab and manholes at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-26 | 2025-05-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 201 | Civil | RFI-ELE-CVL-F-C300-PRC-0201 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean con CCW sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-26 | 2025-05-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 202 | Civil | RFI-ELE-CVL-F-C300-PRC-0202 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean con substation staircase landing | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-26 | 2025-05-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 203 | Civil | RFI-ELE-CVL-F-C300-PRC-0203 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of base sump pit CB4 and CB5 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-28 | 2025-05-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 204 | Civil | RFI-ELE-CVL-F-C300-PRC-0204 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of base foundation for North Staircase at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-28 | 2025-05-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 205 | Civil | RFI-ELE-CVL-F-C300-PRC-0205 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of base CCW S-18244 sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-29 | 2025-05-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 206 | Civil | RFI-ELE-CVL-F-C300-PRC-0206 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean con South side staircase bottom foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-30 | 2025-05-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 207 | Civil | RFI-ELE-CVL-F-C300-PRC-0207 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean con for base manholes MA3 and MA4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-30 | 2025-05-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Cancelled
| 208 | Civil | RFI-ELE-CVL-F-C300-PRC-0208 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for North Staircase bottom plinth at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-03 | 2025-06-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 209 | Civil | RFI-ELE-CVL-F-C300-PRC-0209 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of sump pit CB4 and CB5 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-04 | 2025-06-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 210 | Civil | RFI-ELE-CVL-F-C300-PRC-0210 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of South side staircase bottom foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-04 | 2025-06-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 211 | Civil | RFI-ELE-CVL-F-C300-PRC-0211 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon groundslab GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-04 | 2025-06-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Cancelled
| 212 | Civil | RFI-ELE-CVL-F-C300-PRC-0212 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of CCW S-18244 sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-05 | 2025-06-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 213 | Civil | RFI-ELE-CVL-F-C300-PRC-0213 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for South Staircase bottom plinth at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-05 | 2025-06-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 214 | Civil | RFI-ELE-CVL-F-C300-PRC-0214 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for North Staircase Fligth at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-06 | 2025-06-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 215 | Civil | RFI-ELE-CVL-F-C300-PRC-0215 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean con for base manholes MA3 and MA4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-06 | 2025-06-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 216 | Civil | RFI-ELE-CVL-F-C300-PRC-0216 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean con for trench for Transfomer at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-10 | 2025-06-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 217 | Civil | RFI-ELE-CVL-F-C300-PRC-0217 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for South Staircase Fligth at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-10 | 2025-06-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 218 | Civil | RFI-ELE-CVL-F-C300-PRC-0218 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean con for P-16211 A and B at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-10 | 2025-06-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 219 | Civil | RFI-ELE-CVL-F-C300-PRC-0219 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of GRE Pipe portion for Battery Room Slab at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-10 | 2025-06-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 220 | Civil | RFI-ELE-CVL-F-C300-PRC-0220 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of trench for Transfomer at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-11 | 2025-06-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 221 | Civil | RFI-ELE-CVL-F-C300-PRC-0221 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pump foundation P-16211 A and B at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-11 | 2025-06-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 222 | Civil | RFI-ELE-CVL-F-C300-PRC-0222 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon groundslab GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-11 | 2025-06-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 223 | Civil | RFI-ELE-CVL-F-C300-PRC-0223 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon for East IER Room RC Step Type 1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-16 | 2025-06-17 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 224 | Civil | RFI-ELE-CVL-F-C300-PRC-0224 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of trench for Transfomer A and B at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-16 | 2025-06-17 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 225 | Civil | RFI-ELE-CVL-F-C300-PRC-0225 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of foundation for East IER Room RC Step Type 1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-17 | 2025-06-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 226 | Civil | RFI-ELE-CVL-F-C300-PRC-0226 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal for F9 Foundation (2 nos) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-17 | 2025-06-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 227 | Civil | RFI-ELE-CVL-F-C300-PRC-0227 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of wall CCW S-18244 sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-20 | 2025-06-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 228 | Civil | RFI-ELE-CVL-F-C300-PRC-0228 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of East IER Room RC Step Type 1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-24 | 2025-06-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 229 | Civil | RFI-ELE-CVL-F-C300-PRC-0229 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon for North IER Room RC Step Type 2 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-24 | 2025-06-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 230 | Civil | RFI-ELE-CVL-F-C300-PRC-0230 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean con for trench for EDG at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-24 | 2025-06-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 231 | Civil | RFI-ELE-CVL-F-C300-PRC-0231 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon groundslab GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-24 | 2025-06-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 232 | Civil | RFI-ELE-CVL-F-C300-PRC-0232 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of wall and top CCW S-18244 sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-25 | 2025-06-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 233 | Civil | RFI-ELE-CVL-F-C300-PRC-0233 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of precast cable support block at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-25 | 2025-06-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 234 | Civil | RFI-ELE-CVL-F-C300-PRC-0234 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of Foundation for North IER Room RC Step Type 2 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-26 | 2025-06-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 235 | Civil | RFI-ELE-CVL-F-C300-PRC-0235 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of base for trench for EDG at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-26 | 2025-06-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 236 | Civil | RFI-ELE-CVL-F-C300-PRC-0236 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of wall for trench for EDG at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 237 | Civil | RFI-ELE-CVL-F-C300-PRC-0237 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of flight for North IER Room RC Step Type 2 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 238 | Civil | RFI-ELE-CVL-F-C300-PRC-0238 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon groundslab GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-01 | 2025-07-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 239 | Civil | RFI-ELE-CVL-F-C300-PRC-0239 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of groundslab GL A-C/1-4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-04 | 2025-07-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 240 | Civil | RFI-ELE-CVL-F-C300-PRC-0240 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon for cable tray support foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-08 | 2025-07-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 241 | Civil | RFI-ELE-CVL-F-C300-PRC-0241 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for cable tray support foundation F1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-10 | 2025-07-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 242 | Civil | RFI-ELE-CVL-F-C300-PRC-0242 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean con for Z-18213A foundation for Chilled Water Package | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-10 | 2025-07-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 243 | Civil | RFI-ELE-CVL-F-C300-PRC-0243 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pileplug for Z-18213A foundation for Chilled Water Package | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-10 | 2025-07-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 244 | Civil | RFI-ELE-CVL-F-C300-PRC-0244 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of groundslab GL A-C/4-8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-11 | 2025-07-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 245 | Civil | RFI-ELE-CVL-F-C300-PRC-0245 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean con for Z-18213A foundation for Chilled Water Package | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-14 | 2025-07-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 246 | Civil | RFI-ELE-CVL-F-C300-PRC-0246 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for cable tray support foundation pedestal F1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-14 | 2025-07-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 247 | Civil | RFI-ELE-CVL-F-C300-PRC-0247 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean con PC 3 (E-18206) Foundation at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-14 | 2025-07-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 248 | Civil | RFI-ELE-CVL-F-C300-PRC-0248 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pileplug PC 3 (E-18206) Foundation at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-14 | 2025-07-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 249 | Civil | RFI-ELE-CVL-F-C300-PRC-0249 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Z-18213A foundation for Chilled Water Package | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-16 | 2025-07-17 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 250 | Civil | RFI-ELE-CVL-F-C300-PRC-0250 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for PC 3 (E-18206) Foundation at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-17 | 2025-07-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 251 | Civil | RFI-ELE-CVL-F-C300-PRC-0251 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of roofslab GL A-C/1-3 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-18 | 2025-07-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 252 | Civil | RFI-ELE-CVL-F-C300-PRC-0252 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of 1st Floor GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-28 | 2025-07-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 253 | Civil | RFI-ELE-CVL-F-C300-PRC-0253 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of 2nd Floor GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-29 | 2025-07-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 254 | Civil | RFI-ELE-CVL-F-C300-PRC-0254 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of roofslab kerb GL A-C/1-3 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-29 | 2025-07-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 255 | Civil | RFI-ELE-CVL-F-C300-PRC-0255 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean concrete for TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-29 | 2025-07-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 256 | Civil | RFI-ELE-CVL-F-C300-PRC-0256 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pileplug for TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-29 | 2025-07-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 257 | Civil | RFI-ELE-CVL-F-C300-PRC-0257 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap for TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-02 | 2025-08-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 258 | Civil | RFI-ELE-CVL-F-C300-PRC-0258 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon for P-16232 (P7) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-02 | 2025-08-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 259 | Civil | RFI-ELE-CVL-F-C300-PRC-0259 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of 1st Mezzanine Floor GL A-B/3-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 260 | Civil | RFI-ELE-CVL-F-C300-PRC-0260 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean con for foundation T 19230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-06 | 2025-08-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 261 | Civil | RFI-ELE-CVL-F-C300-PRC-0261 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pileplug for foundation T 19230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-06 | 2025-08-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 262 | Civil | RFI-ELE-CVL-F-C300-PRC-0262 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal for TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-07 | 2025-08-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 263 | Civil | RFI-ELE-CVL-F-C300-PRC-0263 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation T 19230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-08 | 2025-08-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 264 | Civil | RFI-ELE-CVL-F-C300-PRC-0264 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pedestal T 19230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-11 | 2025-08-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 265 | Civil | RFI-ELE-CVL-F-C300-PRC-0265 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation melt tank pump P19221A/B at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-12 | 2025-08-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 266 | Civil | RFI-ELE-CVL-F-C300-PRC-0266 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of 2nd Floor pump foundation and kerb GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-15 | 2025-08-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 267 | Civil | RFI-ELE-CVL-F-C300-PRC-0267 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of 1st Mezzanine Floor GL A-B/3-7 pump foundation and kerb at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-16 | 2025-08-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 268 | Civil | RFI-ELE-CVL-F-C300-PRC-0268 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean concrete for new pump P19231 A/B and P19232 A/B at Scubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-16 | 2025-08-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 269 | Civil | RFI-ELE-CVL-F-C300-PRC-0269 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean concrete for D16227 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-16 | 2025-08-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 270 | Civil | RFI-ELE-CVL-F-C300-PRC-0270 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of foundation for new pump P19231 A/B and P19232 A/B at Scubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-19 | 2025-08-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 271 | Civil | RFI-ELE-CVL-F-C300-PRC-0271 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of foundation for D16227 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-19 | 2025-08-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 272 | Civil | RFI-ELE-CVL-F-C300-PRC-0272 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean con for compound slab TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 273 | Civil | RFI-ELE-CVL-F-C300-PRC-0273 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal for D16227 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-21 | 2025-08-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 274 | Civil | RFI-ELE-CVL-F-C300-PRC-0274 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of foundation for new pump P19231 B at Scubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-28 | 2025-08-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 275 | Civil | RFI-ELE-CVL-F-C300-PRC-0275 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of compound slab TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-30 | 2025-09-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 276 | Civil | RFI-ELE-CVL-F-C300-PRC-0276 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of cable tray support foundation near Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-30 | 2025-09-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 277 | Civil | RFI-ELE-CVL-F-C300-PRC-0277 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pump foundation for P-18204A/B at Demineralise Water Pump Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-06 | 2025-09-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 278 | Civil | RFI-ELE-CVL-F-C300-PRC-0278 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of cable tray support foundation near Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-06 | 2025-09-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 279 | Civil | RFI-ELE-CVL-F-C300-PRC-0279 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of foundation for P-16232 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-06 | 2025-09-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 280 | Civil | RFI-ELE-CVL-F-C300-PRC-0280 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of 1st Mezzanine Floor GL A-B/3-7 pump foundation and kerb at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-10 | 2025-09-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 281 | Civil | RFI-ELE-CVL-F-C300-PRC-0281 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon for MC10 Manhole | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-12 | 2025-09-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 282 | Civil | RFI-ELE-CVL-F-C300-PRC-0282 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for leancon at F5 and F6 at SP 10 Platform | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-12 | 2025-09-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 283 | Civil | RFI-ELE-CVL-F-C300-PRC-0283 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for stair foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-12 | 2025-09-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 284 | Civil | RFI-ELE-CVL-F-C300-PRC-0284 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation at F5 and F6 at SP 10 Platform | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-17 | 2025-09-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 285 | Civil | RFI-ELE-CVL-F-C300-PRC-0285 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for stair foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-17 | 2025-09-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 286 | Civil | RFI-ELE-CVL-F-C300-PRC-0286 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of 1st Mezzanine Floor GL A-B/3-7 pump foundation and kerb at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-19 | 2025-09-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 287 | Civil | RFI-ELE-CVL-F-C300-PRC-0287 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of 1st Floor Z-19206 A/B/C Fines Sifter at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-19 | 2025-09-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 288 | Civil | RFI-ELE-CVL-F-C300-PRC-0288 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of 2nd Floor slab GL A-B/6-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-19 | 2025-09-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 289 | Civil | RFI-ELE-CVL-F-C300-PRC-0289 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon for 2 nos F2, 1 nos F3 and 4 nos F5 foundation at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-19 | 2025-09-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 290 | Civil | RFI-ELE-CVL-F-C300-PRC-0290 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of Pileplug for 2 nos F2, 1 nos F3 and 4 nos F5 foundation at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-19 | 2025-09-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 291 | Civil | RFI-ELE-CVL-F-C300-PRC-0291 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of foundation chimney S-19232 at Roof Slab Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-19 | 2025-09-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 292 | Civil | RFI-ELE-CVL-F-C300-PRC-0292 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pilecap for 2 nos F2, 1 nos F3, 1 nos F7 and 4 nos F5 foundation at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-20 | 2025-09-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 293 | Civil | RFI-ELE-CVL-F-C300-PRC-0293 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pedestal at F5 and F6 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-22 | 2025-09-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 294 | Civil | RFI-ELE-CVL-F-C300-PRC-0294 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of 2nd Floor kerb GL A-B/6-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-22 | 2025-09-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 295 | Civil | RFI-ELE-CVL-F-C300-PRC-0295 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-22 | 2025-09-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 296 | Civil | RFI-ELE-CVL-F-C300-PRC-0296 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon for MA5, MA6 and MA7 Manholes around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-22 | 2025-09-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 297 | Civil | RFI-ELE-CVL-F-C300-PRC-0297 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pedestal 2 nos F5, 2 nos F1 and 2 nos F2 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-23 | 2025-09-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 298 | Civil | RFI-ELE-CVL-F-C300-PRC-0298 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for leancon 1 nos F7 and 1 nos F3 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-23 | 2025-09-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 299 | Civil | RFI-ELE-CVL-F-C300-PRC-0299 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for leancon apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-23 | 2025-09-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 300 | Civil | RFI-ELE-CVL-F-C300-PRC-0300 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-23 | 2025-09-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 301 | Civil | RFI-ELE-CVL-F-C300-PRC-0301 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-24 | 2025-09-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 302 | Civil | RFI-ELE-CVL-F-C300-PRC-0302 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap 1 nos F7 and 1 nos F3 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-24 | 2025-09-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 303 | Civil | RFI-ELE-CVL-F-C300-PRC-0303 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap 1 nos F1 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-24 | 2025-09-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 304 | Civil | RFI-ELE-CVL-F-C300-PRC-0304 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 305 | Civil | RFI-ELE-CVL-F-C300-PRC-0305 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pedestal 1 nos F7 and 1 nos F3 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 306 | Civil | RFI-ELE-CVL-F-C300-PRC-0306 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean con for D 18220 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-26 | 2025-09-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 307 | Civil | RFI-ELE-CVL-F-C300-PRC-0307 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pileplug for D 18220 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-26 | 2025-09-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 308 | Civil | RFI-ELE-CVL-F-C300-PRC-0308 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-26 | 2025-09-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 309 | Civil | RFI-ELE-CVL-F-C300-PRC-0309 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for precast manholes MA5, MA6, MA7 and MA8 for C300 at M-One Precast Yard | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-26 | 2025-09-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 310 | Civil | RFI-ELE-CVL-F-C300-PRC-0310 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pilecap for D 18220 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-27 | 2025-09-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 311 | Civil | RFI-ELE-CVL-F-C300-PRC-0311 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-27 | 2025-09-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 312 | Civil | RFI-ELE-CVL-F-C300-PRC-0312 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pedestal for D 18220 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-29 | 2025-09-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 313 | Civil | RFI-ELE-CVL-F-C300-PRC-0313 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for leancon for YM 18250 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-29 | 2025-09-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 314 | Civil | RFI-ELE-CVL-F-C300-PRC-0314 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of foundation for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-29 | 2025-09-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 315 | Civil | RFI-ELE-CVL-F-C300-PRC-0315 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of base MA5, MA6, MA7 and MC10 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-30 | 2025-09-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 316 | Civil | RFI-ELE-CVL-F-C300-PRC-0316 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation for YM 18250 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-30 | 2025-10-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 317 | Civil | RFI-ELE-CVL-F-C300-PRC-0317 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of wall MA5, MA6, MA7 and MC10 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-01 | 2025-10-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 318 | Civil | RFI-ELE-CVL-F-C300-PRC-0318 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of foundation for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-02 | 2025-10-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 319 | Civil | RFI-ELE-CVL-F-C300-PRC-0319 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-02 | 2025-10-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 320 | Civil | RFI-ELE-CVL-F-C300-PRC-0320 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean con for MC1 and MC6 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-06 | 2025-10-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 321 | Civil | RFI-ELE-CVL-F-C300-PRC-0321 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for leancon apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-07 | 2025-10-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 322 | Civil | RFI-ELE-CVL-F-C300-PRC-0322 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of top MA5, MA6, MA7 and MC10 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-07 | 2025-10-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 323 | Civil | RFI-ELE-CVL-F-C300-PRC-0323 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-08 | 2025-10-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 324 | Civil | RFI-ELE-CVL-F-C300-PRC-0324 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean con foundation for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-08 | 2025-10-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 325 | Civil | RFI-ELE-CVL-F-C300-PRC-0325 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for apron slab and ramp around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-09 | 2025-10-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 326 | Civil | RFI-ELE-CVL-F-C300-PRC-0326 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for apron slab around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-10 | 2025-10-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 327 | Civil | RFI-ELE-CVL-F-C300-PRC-0327 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of foundation for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-10 | 2025-10-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 328 | Civil | RFI-ELE-CVL-F-C300-PRC-0328 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for apron slab around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-11 | 2025-10-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 329 | Civil | RFI-ELE-CVL-F-C300-PRC-0329 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of foundation for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-11 | 2025-10-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 330 | Civil | RFI-ELE-CVL-F-C300-PRC-0330 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for apron slab around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-13 | 2025-10-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 331 | Civil | RFI-ELE-CVL-F-C300-PRC-0331 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon for slab at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-13 | 2025-10-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 332 | Civil | RFI-ELE-CVL-F-C300-PRC-0332 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon for cable C360 support foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-13 | 2025-10-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 333 | Civil | RFI-ELE-CVL-F-C300-PRC-0333 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of concrete for F1 Service Platform foundation at Demin Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-13 | 2025-10-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 334 | Civil | RFI-ELE-CVL-F-C300-PRC-0334 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon for MC7 Manholes | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-13 | 2025-10-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 335 | Civil | RFI-ELE-CVL-F-C300-PRC-0335 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of pedestal for F1 Service Platform foundation at Demin Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-14 | 2025-10-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 336 | Civil | RFI-ELE-CVL-F-C300-PRC-0336 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of foundation for cable C360 support foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-14 | 2025-10-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 337 | Civil | RFI-ELE-CVL-F-C300-PRC-0337 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of bund wall for TK16230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-17 | 2025-10-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 338 | Civil | RFI-ELE-CVL-F-C300-PRC-0338 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for apron slab and ramp around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-17 | 2025-10-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 339 | Civil | RFI-ELE-CVL-F-C300-PRC-0339 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for stair landing foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-17 | 2025-10-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 340 | Civil | RFI-ELE-CVL-F-C300-PRC-0340 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of base MC2, MC7 and wall MC1 and MC6 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-18 | 2025-10-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 341 | Civil | RFI-ELE-CVL-F-C300-PRC-0341 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of gully trap GT-1 at Substation C2015 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-18 | 2025-10-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 342 | Civil | RFI-ELE-CVL-F-C300-PRC-0342 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean con for Manholes MC4 and MC8 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-20 | 2025-10-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 343 | Civil | RFI-ELE-CVL-F-C300-PRC-0343 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for apron slab and ramp around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-20 | 2025-10-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 344 | Civil | RFI-ELE-CVL-F-C300-PRC-0344 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for precast manholes MA5, MA6, MA7 and MA8 for C300 at M-One Precast Yard | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-21 | 2025-10-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 345 | Civil | RFI-ELE-CVL-F-C300-PRC-0345 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of slab at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-24 | 2025-10-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 346 | Civil | RFI-ELE-CVL-F-C300-PRC-0346 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of kerb at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-03 | 2025-11-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 347 | Civil | RFI-ELE-CVL-F-C300-PRC-0347 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for apron slab and ramp around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-03 | 2025-11-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 348 | Civil | RFI-ELE-CVL-F-C300-PRC-0348 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pipe support foundation and D-18214 at Demin Water Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-10 | 2025-11-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 349 | Civil | RFI-ELE-CVL-F-C300-PRC-0349 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for RC step Type 3 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-10 | 2025-11-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 350 | Civil | RFI-ELE-CVL-F-C300-PRC-0350 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for leancon MC5 at Manholes C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-13 | 2025-11-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 351 | Civil | RFI-ELE-CVL-F-C300-PRC-0351 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for leancon rigid paving at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-14 | 2025-11-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 352 | Civil | RFI-ELE-CVL-F-C300-PRC-0352 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pipe support foundation at Demin Water Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-14 | 2025-11-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 353 | Civil | RFI-ELE-CVL-F-C300-PRC-0353 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for base for MC4 and MC5, wall for MC2 and MC7 at Manholes C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-14 | 2025-11-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 354 | Civil | RFI-ELE-CVL-F-C300-PRC-0354 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for rigid paving at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-19 | 2025-11-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 355 | Civil | RFI-ELE-CVL-F-C300-PRC-0355 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Wall for MC4 and MC5 Manholes C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-20 | 2025-11-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 356 | Civil | RFI-ELE-CVL-F-C300-PRC-0356 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for kerb paving at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-21 | 2025-11-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 357 | Civil | RFI-ELE-CVL-F-C300-PRC-0357 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection Service Platform SP-07 Foundation at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-26 | 2025-11-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 358 | Civil | RFI-ELE-CVL-F-C300-PRC-0358 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of lean concrete for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-29 | 2025-11-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 359 | Civil | RFI-ELE-CVL-F-C300-PRC-0359 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-29 | 2025-12-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 360 | Civil | RFI-ELE-CVL-F-C300-PRC-0360 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for slab opening at 1st Floor Briquetting Building (SI-085) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-01 | 2025-12-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 361 | Civil | RFI-ELE-CVL-F-C300-PRC-0361 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-03 | 2025-12-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 362 | Civil | RFI-ELE-CVL-F-C300-PRC-0362 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Manhole MC8 base at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-05 | 2025-12-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 363 | Civil | RFI-ELE-CVL-F-C300-PRC-0363 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean con pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-08 | 2025-12-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 364 | Civil | RFI-ELE-CVL-F-C300-PRC-0364 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-09 | 2025-12-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 365 | Civil | RFI-ELE-CVL-F-C300-PRC-0365 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Manhole MC8 wall at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-09 | 2025-12-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 366 | Civil | RFI-ELE-CVL-F-C300-PRC-0366 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean con pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-11 | 2025-12-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 367 | Civil | RFI-ELE-CVL-F-C300-PRC-0367 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-16 | 2025-12-17 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 368 | Civil | RFI-ELE-CVL-F-C300-PRC-0368 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean con pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-19 | 2025-12-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 369 | Civil | RFI-ELE-CVL-F-C300-PRC-0369 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-23 | 2025-12-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 370 | Civil | RFI-ELE-CVL-F-C300-PRC-0370 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-27 | 2025-12-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 371 | Civil | RFI-ELE-CVL-F-C300-PRC-0371 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean con for TK16230 stairs foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-27 | 2025-12-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 372 | Civil | RFI-ELE-CVL-F-C300-PRC-0372 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for foundation for TK16230 stairs foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-27 | 2025-12-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 373 | Civil | RFI-ELE-CVL-F-C300-PRC-0373 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon for apron slab GL A/ 5-10 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-27 | 2025-12-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 374 | Civil | RFI-ELE-CVL-F-C300-PRC-0374 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for apron slab GL A/ 5-10 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-30 | 2025-12-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 375 | Civil | RFI-ELE-CVL-F-C300-PRC-0375 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pavement kerb at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-30 | 2025-12-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 376 | Civil | RFI-ELE-CVL-F-C300-PRC-0376 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean concrete for manholes MA8 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-03 | 2026-01-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 377 | Civil | RFI-ELE-CVL-F-C300-PRC-0377 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon for apron slab at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-06 | 2026-01-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 378 | Civil | RFI-ELE-CVL-F-C300-PRC-0378 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for apron slab at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-09 | 2026-01-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 379 | Civil | RFI-ELE-CVL-F-C300-PRC-0379 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for stairs TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-12 | 2026-01-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 380 | Civil | RFI-ELE-CVL-F-C300-PRC-0380 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection of leancon for apron slab at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-12 | 2026-01-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 381 | Civil | RFI-ELE-CVL-F-C300-PRC-0381 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for base concrete for manholes MA8 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-12 | 2026-01-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 382 | Civil | RFI-ELE-CVL-F-C300-PRC-0382 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for air vent support for MC4, MC5, MC6, MC7, MA6 and MA7 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-12 | 2026-01-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 383 | Civil | RFI-ELE-CVL-F-C300-PRC-0383 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Wall and Top concrete for manholes MA8 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-19 | 2026-01-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 384 | Civil | RFI-ELE-CVL-F-C300-PRC-0384 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Stairs foundation for Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-19 | 2026-01-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 385 | Civil | RFI-ELE-CVL-F-C300-PRC-0385 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for manhole cover MC1, MC4, MC5, MC6 and MC7 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-19 | 2026-01-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 386 | Civil | RFI-ELE-CVL-F-C300-PRC-0386 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean concrete for ramp at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-19 | 2026-01-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 387 | Civil | RFI-ELE-CVL-F-C300-PRC-0387 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for concrete for apron at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-19 | 1900-01-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 388 | Civil | RFI-ELE-CVL-F-C300-PRC-0388 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for concrete heavy duty paving near Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-19 | 1900-01-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 389 | Civil | RFI-ELE-CVL-F-C300-PRC-0389 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Stairs foundation for Demin Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-22 | 2026-01-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 390 | Civil | RFI-ELE-CVL-F-C300-PRC-0390 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-22 | 2026-01-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 391 | Civil | RFI-ELE-CVL-F-C300-PRC-0391 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for ramp at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-24 | 2026-01-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 392 | Civil | RFI-ELE-CVL-F-C300-PRC-0392 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for airvent pipe support for MC2, MC10 and MC8 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-24 | 2026-01-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 393 | Civil | RFI-ELE-CVL-F-C300-PRC-0393 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for leancon ramp at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-26 | 2026-01-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 394 | Civil | RFI-ELE-CVL-F-C300-PRC-0394 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for leancon pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-26 | 2026-01-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 395 | Civil | RFI-ELE-CVL-F-C300-PRC-0395 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for Heavy Duty Pavement at Man Refiner (South) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-27 | 2026-01-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 396 | Civil | RFI-ELE-CVL-F-C300-PRC-0396 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for manhole cover MC1, MC2, MC4, MC5, MC8 and MA8 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-28 | 2026-01-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 397 | Civil | RFI-ELE-CVL-F-C300-PRC-0397 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for airvent pipe support MA5. MA6 and MA7 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-30 | 2026-01-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 398 | Civil | RFI-ELE-CVL-F-C300-PRC-0398 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for rigid pavement and PL07 pipe support at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-30 | 2026-01-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 399 | Civil | RFI-ELE-CVL-F-C300-PRC-0399 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for slab around MC10 at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-30 | 2026-01-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 400 | Civil | RFI-ELE-CVL-F-C300-PRC-0400 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for lean con for ramp at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-30 | 2026-01-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 401 | Civil | RFI-ELE-CVL-F-C300-PRC-0401 | External | Eleco | Civil Work | N/A | RC Work | Pre-pour concrete | Inspection for ramp at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-30 | 2026-01-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing

## 07.RFI_CON
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-30
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-CVL-F-C300-CON-0001 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pile plug installation for Sub-station C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-17 | 2024-08-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 2 | Civil | RFI-ELE-CVL-F-C300-CON-0002 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap's leancon for Sub-station C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-18 | 2024-08-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 3 | Civil | RFI-ELE-CVL-F-C300-CON-0003 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap's leancon for Sub-station C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-23 | 2024-08-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 4 | Civil | RFI-ELE-CVL-F-C300-CON-0004 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pile plug installation for Sub-station C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-23 | 2024-08-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 5 | Civil | RFI-ELE-CVL-F-C300-CON-0005 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-26 | 2024-08-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 6 | Civil | RFI-ELE-CVL-F-C300-CON-0006 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-29 | 2024-08-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 7 | Civil | RFI-ELE-CVL-F-C300-CON-0007 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-04 | 2024-09-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 8 | Civil | RFI-ELE-CVL-F-C300-CON-0008 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of stump for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-04 | 2024-09-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 9 | Civil | RFI-ELE-CVL-F-C300-CON-0009 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-06 | 2024-09-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 10 | Civil | RFI-ELE-CVL-F-C300-CON-0010 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pile plug installation for Sub-station C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-21 | 2024-09-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 11 | Civil | RFI-ELE-CVL-F-C300-CON-0011 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap's leancon for Sub-station C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-21 | 2024-09-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 12 | Civil | RFI-ELE-CVL-F-C300-CON-0012 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-24 | 2024-09-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 13 | Civil | RFI-ELE-CVL-F-C300-CON-0013 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of broken pile rectification for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-24 | 2024-09-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 14 | Civil | RFI-ELE-CVL-F-C300-CON-0014 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-26 | 2024-09-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 15 | Civil | RFI-ELE-CVL-F-C300-CON-0015 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of stump for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-30 | 2024-10-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 16 | Civil | RFI-ELE-CVL-F-C300-CON-0016 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of groundbeam leancon Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-04 | 2024-10-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 17 | Civil | RFI-ELE-CVL-F-C300-CON-0017 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of groundbeam Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-19 | 2024-10-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 18 | Civil | RFI-ELE-CVL-F-C300-CON-0018 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of groundbeam Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-22 | 2024-10-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 19 | Civil | RFI-ELE-CVL-F-C300-CON-0019 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pileplug installation MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-12 | 2024-11-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 20 | Civil | RFI-ELE-CVL-F-C300-CON-0020 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation leancon MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-12 | 2024-11-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 21 | Civil | RFI-ELE-CVL-F-C300-CON-0021 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pileplug installation MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-14 | 2024-11-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 22 | Civil | RFI-ELE-CVL-F-C300-CON-0022 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation leancon MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-14 | 2024-11-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 23 | Civil | RFI-ELE-CVL-F-C300-CON-0023 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of groundslab leancon Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-15 | 2024-11-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 24 | Civil | RFI-ELE-CVL-F-C300-CON-0024 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation PC16 MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-16 | 2024-11-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 25 | Civil | RFI-ELE-CVL-F-C300-CON-0025 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pileplug installation MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-18 | 2024-11-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 26 | Civil | RFI-ELE-CVL-F-C300-CON-0026 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation leancon MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-18 | 2024-11-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 27 | Civil | RFI-ELE-CVL-F-C300-CON-0027 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-23 | 2024-11-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 28 | Civil | RFI-ELE-CVL-F-C300-CON-0028 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pileplug installation MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-23 | 2024-11-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 29 | Civil | RFI-ELE-CVL-F-C300-CON-0029 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation leancon MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-23 | 2024-11-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 30 | Civil | RFI-ELE-CVL-F-C300-CON-0030 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pileplug installation for Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-23 | 2024-11-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 31 | Civil | RFI-ELE-CVL-F-C300-CON-0031 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation leancon for Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-23 | 2024-11-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 32 | Civil | RFI-ELE-CVL-F-C300-CON-0032 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation PC16 top MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-29 | 2024-11-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 33 | Civil | RFI-ELE-CVL-F-C300-CON-0033 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-29 | 2024-12-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 34 | Civil | RFI-ELE-CVL-F-C300-CON-0034 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for groundslab Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-29 | 2024-12-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 35 | Civil | RFI-ELE-CVL-F-C300-CON-0035 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for groundbeam Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-04 | 2024-12-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 36 | Civil | RFI-ELE-CVL-F-C300-CON-0036 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean concrete at AHU-01A and B and HVAC control panel Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-07 | 2024-12-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 37 | Civil | RFI-ELE-CVL-F-C300-CON-0037 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean concrete at PC4c and PC4 Man refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-07 | 2024-12-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 38 | Civil | RFI-ELE-CVL-F-C300-CON-0038 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for column G/level to 1st level GL A-D/2-3 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-09 | 2024-12-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 39 | Civil | RFI-ELE-CVL-F-C300-CON-0039 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for Pilecap Man Refiner Foundation PC4c and PC4d | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-10 | 2024-12-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 40 | Civil | RFI-ELE-CVL-F-C300-CON-0040 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pileplug Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-10 | 2024-12-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 41 | Civil | RFI-ELE-CVL-F-C300-CON-0041 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for Pilecap Man Refiner Foundation PC4c topside, PC4d topside, PC8 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-12 | 2024-12-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 42 | Civil | RFI-ELE-CVL-F-C300-CON-0042 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for EDG Foundation at Substation C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-13 | 2024-12-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 43 | Civil | RFI-ELE-CVL-F-C300-CON-0043 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for column G/level to 1st level GL A-D/4-5a Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-13 | 2024-12-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 44 | Civil | RFI-ELE-CVL-F-C300-CON-0044 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for column G/level to 1st level GL A-D/1x, GL C-D/1, GL A/5-7, GL B/7 and GL B1/5 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-17 | 2024-12-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 45 | Civil | RFI-ELE-CVL-F-C300-CON-0045 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean concrete at PC6a, PC2b, 3 nos of PC2 and PC8a | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-17 | 2024-12-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 46 | Civil | RFI-ELE-CVL-F-C300-CON-0046 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for PilePlug at PC6a, PC2b, 3 nos of PC2 and PC8a | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-17 | 2024-12-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 47 | Civil | RFI-ELE-CVL-F-C300-CON-0047 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for column G/level to 1st level GL B1-D / 6-8, GL C1/5A and GL D/5 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-19 | 2024-12-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 48 | Civil | RFI-ELE-CVL-F-C300-CON-0048 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean concrete at PC2b, PC2 and PC9 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-19 | 2024-12-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 49 | Civil | RFI-ELE-CVL-F-C300-CON-0049 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for PilePlug at PC2b, PC2 and PC9 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-19 | 2024-12-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 50 | Civil | RFI-ELE-CVL-F-C300-CON-0050 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for Pilecap Man Refiner Foundation PC6a, PC8a, PC2 (2 unit) and PC2b | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-20 | 2024-12-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 51 | Civil | RFI-ELE-CVL-F-C300-CON-0051 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for Pileplug Man Refiner Foundation PC9, PC2b, PC6b, PC2 and PC2a | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-20 | 2024-12-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 52 | Civil | RFI-ELE-CVL-F-C300-CON-0052 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for Leancon Man Refiner Foundation PC6b, PC2 and PC2a | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-20 | 2024-12-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 53 | Civil | RFI-ELE-CVL-F-C300-CON-0053 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for Pilecap Transformer MCC-A and MCC-B foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-20 | 2024-12-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 54 | Civil | RFI-ELE-CVL-F-C300-CON-0054 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for Pilecap PC9, PC2b and PC2 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-21 | 2024-12-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 55 | Civil | RFI-ELE-CVL-F-C300-CON-0055 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for 2nd Cast PC8a at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-23 | 2024-12-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 56 | Civil | RFI-ELE-CVL-F-C300-CON-0056 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for leancon Man Refiner Foundation PC4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-23 | 2024-12-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 57 | Civil | RFI-ELE-CVL-F-C300-CON-0057 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pedestal C1 PC 11, GL A/3, for Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-23 | 2024-12-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 58 | Civil | RFI-ELE-CVL-F-C300-CON-0058 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap PC4 and PC6b at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 59 | Civil | RFI-ELE-CVL-F-C300-CON-0059 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for leancon PC2, PC2a, PC2b/C1 and PC24 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 60 | Civil | RFI-ELE-CVL-F-C300-CON-0060 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pileplug PC2, PC2a, PC2b/C1 and PC24 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 61 | Civil | RFI-ELE-CVL-F-C300-CON-0061 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for Pedestal C1 for PC11, PC8, PC6a and PC2b | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 62 | Civil | RFI-ELE-CVL-F-C300-CON-0062 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for leancon for TK-18203 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 63 | Civil | RFI-ELE-CVL-F-C300-CON-0063 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pileplug for TK-18203 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 64 | Civil | RFI-ELE-CVL-F-C300-CON-0064 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pedestal for pilecap PC6c, PC6, PC5, PC12, PC8a, PC9, PC2 and PC2a | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-26 | 2024-12-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 65 | Civil | RFI-ELE-CVL-F-C300-CON-0065 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pedestal for pilecap PC11, PC2 (2 nos), PC1 and PC6b | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-27 | 2024-12-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 66 | Civil | RFI-ELE-CVL-F-C300-CON-0066 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap PC2,PC2a, PC2b at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-27 | 2024-12-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 67 | Civil | RFI-ELE-CVL-F-C300-CON-0067 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for leancon pilecap PC2a at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-27 | 2024-12-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 68 | Civil | RFI-ELE-CVL-F-C300-CON-0068 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pileplug pilecap PC2a at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-27 | 2024-12-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 69 | Civil | RFI-ELE-CVL-F-C300-CON-0069 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap PC5/C1 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-28 | 2024-12-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 70 | Civil | RFI-ELE-CVL-F-C300-CON-0070 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pedestal for pilecap PC2/PS, PC2a/PS, PC2b/PS at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-28 | 2024-12-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 71 | Civil | RFI-ELE-CVL-F-C300-CON-0071 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean con for pilecap PC 8b and PC4/C1 (2 nos) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-28 | 2024-12-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 72 | Civil | RFI-ELE-CVL-F-C300-CON-0072 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pileplug for pilecap PC 8b and PC4/C1 (2 nos) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-28 | 2024-12-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 73 | Civil | RFI-ELE-CVL-F-C300-CON-0073 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pedestal for pilecap PC5 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-30 | 2024-12-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 74 | Civil | RFI-ELE-CVL-F-C300-CON-0074 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for leancon for pilecap PC6d/C1 , PC12/C1 and PC8b | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-31 | 2025-01-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 75 | Civil | RFI-ELE-CVL-F-C300-CON-0075 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap PC4/C1 2 nos at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-31 | 2025-01-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 76 | Civil | RFI-ELE-CVL-F-C300-CON-0076 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection pedestal PC2a/C1 GL d/7 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-01 | 2025-01-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 77 | Civil | RFI-ELE-CVL-F-C300-CON-0077 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection pilecap PC24 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-02 | 2025-01-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 78 | Civil | RFI-ELE-CVL-F-C300-CON-0078 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection pedestal PC2b/C1 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-02 | 2025-01-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 79 | Civil | RFI-ELE-CVL-F-C300-CON-0079 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection leancon for PC6d/C1 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-02 | 2025-01-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 80 | Civil | RFI-ELE-CVL-F-C300-CON-0080 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection pileplug for PC6d/C1 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-02 | 2025-01-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 81 | Civil | RFI-ELE-CVL-F-C300-CON-0081 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection pilecap for PC5, PC12/C1 GL E/5, and PC8b at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-03 | 2025-01-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 82 | Civil | RFI-ELE-CVL-F-C300-CON-0082 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection pilecap for AHU-01 A and 01B, HVAC Control Panel Foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-03 | 2025-01-03 | 18:00 | H | W | N/A | R | Hanis | C300 | Accepted
| 83 | Civil | RFI-ELE-CVL-F-C300-CON-0083 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap PC8a,PC12/C1,PC6d/C1 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-05 | 2025-01-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 84 | Civil | RFI-ELE-CVL-F-C300-CON-0084 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pedestal PC4/C1 (2nos) Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-05 | 2025-01-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 85 | Civil | RFI-ELE-CVL-F-C300-CON-0085 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection leancon for pilecap GL A-A2 - 27' -29' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-06 | 2025-01-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 86 | Civil | RFI-ELE-CVL-F-C300-CON-0086 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal PC12, PC 6d, PC8b and PC24 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-07 | 2025-01-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 87 | Civil | RFI-ELE-CVL-F-C300-CON-0087 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of foundation TK 18203 Demin Water Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-08 | 2025-01-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 88 | Civil | RFI-ELE-CVL-F-C300-CON-0088 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal PC24 (saddle) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-09 | 2025-01-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 89 | Civil | RFI-ELE-CVL-F-C300-CON-0089 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation leancon Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-10 | 2025-01-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 90 | Civil | RFI-ELE-CVL-F-C300-CON-0090 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation leancon Briquetting Building-PC22,PC6 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-15 | 2025-01-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 91 | Civil | RFI-ELE-CVL-F-C300-CON-0091 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation pileplug for PC22, PC6, PC5a and PC5 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-16 | 2025-01-16 | 4.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 92 | Civil | RFI-ELE-CVL-F-C300-CON-0092 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for slab and beam 1st floor for Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-16 | 2025-01-17 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 93 | Civil | RFI-ELE-CVL-F-C300-CON-0093 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap GL A-A2 - 27' -29' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-16 | 2025-01-17 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 94 | Civil | RFI-ELE-CVL-F-C300-CON-0094 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal PC24 (free saddle) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-17 | 2025-01-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 95 | Civil | RFI-ELE-CVL-F-C300-CON-0095 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of column GL A-D/1X at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-22 | 2025-01-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 96 | Civil | RFI-ELE-CVL-F-C300-CON-0096 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap GL A1' -A2'/ 28' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-22 | 2025-01-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 97 | Civil | RFI-ELE-CVL-F-C300-CON-0097 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal GL A1' -A2'/ 29' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-22 | 2025-01-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 98 | Civil | RFI-ELE-CVL-F-C300-CON-0098 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap PC6 and PC5a at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-23 | 2025-01-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 99 | Civil | RFI-ELE-CVL-F-C300-CON-0099 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon for pilecap D-2806 at Esstar Vision Compound | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-25 | 2025-01-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 100 | Civil | RFI-ELE-CVL-F-C300-CON-0100 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap D-2806 at Esstar Vision Compound | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-25 | 2025-01-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 101 | Civil | RFI-ELE-CVL-F-C300-CON-0101 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap GL A-C/1-4 for Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-27 | 2025-01-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 102 | Civil | RFI-ELE-CVL-F-C300-CON-0102 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pileplug PC6/C1 (3nos),PC6a/C1 (2nos) and PC6c/C1 for Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-27 | 2025-01-27 | 6.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 103 | Civil | RFI-ELE-CVL-F-C300-CON-0103 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of column GL A-D/4-8 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-31 | 2025-02-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 104 | Civil | RFI-ELE-CVL-F-C300-CON-0104 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon for pilecap PC6/C1 and PC8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-31 | 2025-02-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 105 | Civil | RFI-ELE-CVL-F-C300-CON-0105 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap PC6/C1, PC6c/C1 and PC6a/C1 GL A-B/3-4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-01 | 2025-02-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 106 | Civil | RFI-ELE-CVL-F-C300-CON-0106 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of stump column at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-04 | 2025-02-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 107 | Civil | RFI-ELE-CVL-F-C300-CON-0107 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pileplug at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-04 | 2025-02-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 108 | Civil | RFI-ELE-CVL-F-C300-CON-0108 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap GL A1' -A2'/ 27-29 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 109 | Civil | RFI-ELE-CVL-F-C300-CON-0109 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal GL A1' -A2'/27- 29' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 110 | Civil | RFI-ELE-CVL-F-C300-CON-0110 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of column 1st-RL GL B-D/2-3 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 111 | Civil | RFI-ELE-CVL-F-C300-CON-0111 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of stump column at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Cancelled
| 112 | Civil | RFI-ELE-CVL-F-C300-CON-0112 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pileplug at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 113 | Civil | RFI-ELE-CVL-F-C300-CON-0113 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of stump column at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-06 | 2024-02-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 114 | Civil | RFI-ELE-CVL-F-C300-CON-0114 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-06 | 2024-02-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 115 | Civil | RFI-ELE-CVL-F-C300-CON-0115 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-07 | 2024-02-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 116 | Civil | RFI-ELE-CVL-F-C300-CON-0116 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon for pilecap at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-07 | 2024-02-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 117 | Civil | RFI-ELE-CVL-F-C300-CON-0117 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pileplug at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-07 | 2024-02-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 118 | Civil | RFI-ELE-CVL-F-C300-CON-0118 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of raft foundation Battery Room at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-07 | 2024-02-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 119 | Civil | RFI-ELE-CVL-F-C300-CON-0119 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of column 1st-RL at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0004 | B | 2024-02-08 | 2024-02-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 120 | Civil | RFI-ELE-CVL-F-C300-CON-0120 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pileplug at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-11 | 2024-02-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 121 | Civil | RFI-ELE-CVL-F-C300-CON-0121 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon for pilecap at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-11 | 2024-02-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 122 | Civil | RFI-ELE-CVL-F-C300-CON-0122 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-11 | 2024-02-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 123 | Civil | RFI-ELE-CVL-F-C300-CON-0123 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of stump column at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-11 | 2024-02-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 124 | Civil | RFI-ELE-CVL-F-C300-CON-0124 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap GL A1' -A2'/ 27-29 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-11 | 2024-02-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 125 | Civil | RFI-ELE-CVL-F-C300-CON-0125 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal GL A1' -A2'/27- 29' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-13 | 2024-02-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 126 | Civil | RFI-ELE-CVL-F-C300-CON-0126 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of column 1st-RL at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-11 | 2024-02-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 127 | Civil | RFI-ELE-CVL-F-C300-CON-0127 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap PC3/C2 GL C/9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 128 | Civil | RFI-ELE-CVL-F-C300-CON-0128 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon PC7a/C1 and PC6b/C1 GL B/5-6 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 129 | Civil | RFI-ELE-CVL-F-C300-CON-0129 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of Pileplug PC7a/C1 and PC6b/C1 GL B/5-6 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 130 | Civil | RFI-ELE-CVL-F-C300-CON-0130 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon Groundbeam GL A/1-2, A-C/1 and C/1-4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 131 | Civil | RFI-ELE-CVL-F-C300-CON-0131 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal PC4/C2 GL C/8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 132 | Civil | RFI-ELE-CVL-F-C300-CON-0132 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap Z-19208A Weighing Machines and Silo Foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-19 | 2025-02-19 | 11.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 133 | Civil | RFI-ELE-CVL-F-C300-CON-0133 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap PC6b and PC6d GL B/6-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-19 | 2025-02-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 134 | Civil | RFI-ELE-CVL-F-C300-CON-0134 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap PC7a/C1 GL B/5 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-20 | 2025-02-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 135 | Civil | RFI-ELE-CVL-F-C300-CON-0135 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon PC3/C2 GL C/10 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-20 | 2025-02-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 136 | Civil | RFI-ELE-CVL-F-C300-CON-0136 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pileplug PC3/C2 GL C/10 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-20 | 2025-02-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 137 | Civil | RFI-ELE-CVL-F-C300-CON-0137 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal PC3/C2 GL C/9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-20 | 2025-02-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 138 | Civil | RFI-ELE-CVL-F-C300-CON-0138 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of roof slab and beam at GL A-D/4-8 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-22 | 2025-02-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 139 | Civil | RFI-ELE-CVL-F-C300-CON-0139 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of roof beam at GL A-D/1x-1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-22 | 2025-02-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 140 | Civil | RFI-ELE-CVL-F-C300-CON-0140 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of ground beam Gl A-C/ 1-5 for Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-25 | 2025-02-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 141 | Civil | RFI-ELE-CVL-F-C300-CON-0141 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap PC3/C2 GL C/10 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-25 | 2025-02-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 142 | Civil | RFI-ELE-CVL-F-C300-CON-0142 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean con for PC4/C2 (2 nos) GL C/11-12, Z-19208B, Z-19240 Equipment foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-25 | 2025-02-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 143 | Civil | RFI-ELE-CVL-F-C300-CON-0143 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pileplug for PC4/C2 (2 nos) GL C/11-12, Z-19208B, Z-19240 Equipment foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-25 | 2025-02-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 144 | Civil | RFI-ELE-CVL-F-C300-CON-0144 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of foundation pilecap Z-19208B & D-19220 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-27 | 2025-02-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 145 | Civil | RFI-ELE-CVL-F-C300-CON-0145 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap for PC4/C2 (2 nos) GL C/11-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-27 | 2025-02-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 146 | Civil | RFI-ELE-CVL-F-C300-CON-0146 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap for PC4/C2 GL A/12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-28 | 2025-03-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 147 | Civil | RFI-ELE-CVL-F-C300-CON-0147 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean con for PC6/C1 and PC7/C1 GL A/5-6, and Z-19208C at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-28 | 2025-03-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 148 | Civil | RFI-ELE-CVL-F-C300-CON-0148 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilepug for PC6/C1 and PC7/C1 GL A/5-6, and Z-19208C at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-28 | 2025-03-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 149 | Civil | RFI-ELE-CVL-F-C300-CON-0149 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of roof slab GL A-D/1-4 for Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-03 | 2025-03-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 150 | Civil | RFI-ELE-CVL-F-C300-CON-0150 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pile cap PC6/C1 GL A/4-5 and Z-19208C at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-04 | 2025-03-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 151 | Civil | RFI-ELE-CVL-F-C300-CON-0151 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of groundbeam GL C/4-9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-04 | 2025-03-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 152 | Civil | RFI-ELE-CVL-F-C300-CON-0152 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean con PC3/C2 (2nos) GL A/9-10 and PC4/C2 (2nos) GL A/11 and B/12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-04 | 2025-03-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 153 | Civil | RFI-ELE-CVL-F-C300-CON-0153 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pileplug PC3/C2 (2nos) GL A/9-10 and PC4/C2 (2nos) GL A/11 and B/12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-04 | 2025-03-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 154 | Civil | RFI-ELE-CVL-F-C300-CON-0154 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal PC5a, PC6a, PC6, PC7a, PC6b, and PC6d GL B/2-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-04 | 2025-03-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 155 | Civil | RFI-ELE-CVL-F-C300-CON-0155 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean con P-18201A and P-18201B Pump Foundation at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-05 | 2025-03-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 156 | Civil | RFI-ELE-CVL-F-C300-CON-0156 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap PC4/C2 (2 nos), PC3/C2 (2 nos) GL A/8-11 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 157 | Civil | RFI-ELE-CVL-F-C300-CON-0157 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of Pedestal 2nd cast PC5/C1 GL B/1, PC6/C1 (3 nos), PC6a/C1 (2 nos), PC7/C1 (2 nos) and PC4/C2 GL A/1-8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 158 | Civil | RFI-ELE-CVL-F-C300-CON-0158 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of groundbeam GL A/1-4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 159 | Civil | RFI-ELE-CVL-F-C300-CON-0159 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal PC3/C2 and PC4/C2 (2nos) GL C/10-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 160 | Civil | RFI-ELE-CVL-F-C300-CON-0160 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap PC4/C2 GL B/12, PC7/C1 GL A/6 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 161 | Civil | RFI-ELE-CVL-F-C300-CON-0161 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon PC4/C2 GL A/8, PC3/C2 GL A/9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 162 | Civil | RFI-ELE-CVL-F-C300-CON-0162 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pileplug PC4/C2 GL A/8, PC3/C2 GL A/9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 163 | Civil | RFI-ELE-CVL-F-C300-CON-0163 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for Pump Foundation P-18201A and P-18201B at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-07 | 2025-03-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 164 | Civil | RFI-ELE-CVL-F-C300-CON-0164 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean concrete and pile plug Stretch Hood Device and ground beam GL A 4-6 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 165 | Civil | RFI-ELE-CVL-F-C300-CON-0165 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap foundation Stretch Hood Device at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 166 | Civil | RFI-ELE-CVL-F-C300-CON-0166 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap foundation D-19220 Foundation Melt Tank at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 167 | Civil | RFI-ELE-CVL-F-C300-CON-0167 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of groundbeam GL A/4-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 168 | Civil | RFI-ELE-CVL-F-C300-CON-0168 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of 2nd cast pedestal PC6/C1 (2nos) and PC6a/C1 GL A/1-4 Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 169 | Civil | RFI-ELE-CVL-F-C300-CON-0169 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal PC4/C2 (4nos) and PC3/C2 (3nos) GL A-B/8-12 Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 170 | Civil | RFI-ELE-CVL-F-C300-CON-0170 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of cast fascia GL A-D/ 4-8 at roof floor Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 171 | Civil | RFI-ELE-CVL-F-C300-CON-0171 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of Lean concrete for ground beam GL A-C/8-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 172 | Civil | RFI-ELE-CVL-F-C300-CON-0172 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of Lean concrete for PC7/C1 GL A/7 and foundation Stretch Hood Device GL A/8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 173 | Civil | RFI-ELE-CVL-F-C300-CON-0173 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal for PC6a/C1 and PC6/C1 GL A/4-5 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 174 | Civil | RFI-ELE-CVL-F-C300-CON-0174 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of groundbeam for GL A-C/8 -12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-13 | 2025-03-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 175 | Civil | RFI-ELE-CVL-F-C300-CON-0175 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap for foundation Stretch Hood Device GL A/8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-13 | 2025-03-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 176 | Civil | RFI-ELE-CVL-F-C300-CON-0176 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal for PC3/C2 (2 nos) and PC4/C2 (3 nos) GL B-C/9-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-14 | 2025-03-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 177 | Civil | RFI-ELE-CVL-F-C300-CON-0177 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pedestal foundation D-19220 Foundation Melt Tank at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-14 | 2025-03-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 178 | Civil | RFI-ELE-CVL-F-C300-CON-0178 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of Lean concrete for PC7/C1 GL A/7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-14 | 2025-03-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 179 | Civil | RFI-ELE-CVL-F-C300-CON-0179 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pileplug for PC7/C1 GL A/7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-14 | 2025-03-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 180 | Civil | RFI-ELE-CVL-F-C300-CON-0180 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of cast fascia GL A-D/ 4at roof floor Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-15 | 2025-03-17 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 181 | Civil | RFI-ELE-CVL-F-C300-CON-0181 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal for PC3/C2 (2 nos) and PC4/C2 (3 nos) GL A-B/9-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-15 | 2025-03-17 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 182 | Civil | RFI-ELE-CVL-F-C300-CON-0182 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap for PC7/C1 GL A/7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-17 | 2025-03-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 183 | Civil | RFI-ELE-CVL-F-C300-CON-0183 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal for PC7/C1 GL A/7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-18 | 2025-03-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 184 | Civil | RFI-ELE-CVL-F-C300-CON-0184 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon groundbeam for GL A/6-8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-18 | 2025-03-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 185 | Civil | RFI-ELE-CVL-F-C300-CON-0185 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of groundbeam for GL A/6-8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-20 | 2025-03-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 186 | Civil | RFI-ELE-CVL-F-C300-CON-0186 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean concrete at P-16214 and P-16247 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-22 | 2025-03-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 187 | Civil | RFI-ELE-CVL-F-C300-CON-0187 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean concrete at P-18203A (2 nos) and P-16224 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-24 | 2025-03-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 188 | Civil | RFI-ELE-CVL-F-C300-CON-0188 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of foundation afor P-18203A (2 nos), P-16214, P-16247 and P-16224 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-26 | 2025-03-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 189 | Civil | RFI-ELE-CVL-F-C300-CON-0189 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean concrete for groundslab GL A-C/10-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-10 | 2025-04-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 190 | Civil | RFI-ELE-CVL-F-C300-CON-0190 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean concrete for Pump foundation at Esstar Vission Compound | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-10 | 2025-04-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 191 | Civil | RFI-ELE-CVL-F-C300-CON-0191 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of foudation for Pump foundation at Esstar Vission Compound | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-16 | 2025-04-17 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 192 | Civil | RFI-ELE-CVL-F-C300-CON-0192 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean concrete GL B-C/1-7 for groundslab Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-16 | 2025-04-17 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 193 | Civil | RFI-ELE-CVL-F-C300-CON-0193 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean concrete ACCU Foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-16 | 2025-04-17 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 194 | Civil | RFI-ELE-CVL-F-C300-CON-0194 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of groundslab GL A-C/10-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-17 | 2025-04-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 195 | Civil | RFI-ELE-CVL-F-C300-CON-0195 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of ACCU Foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-18 | 2025-04-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 196 | Civil | RFI-ELE-CVL-F-C300-CON-0196 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of F9 Foundation at Man Refiner GL A-B/9 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-22 | 2025-04-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 197 | Civil | RFI-ELE-CVL-F-C300-CON-0197 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon for non suspended slab HVAC Room Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-29 | 2025-04-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 198 | Civil | RFI-ELE-CVL-F-C300-CON-0198 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon groundslab GL A-C/7-9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-03 | 2025-05-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 199 | Civil | RFI-ELE-CVL-F-C300-CON-0199 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of ground slab GL A-C/7-9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-12 | 2025-05-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 200 | Civil | RFI-ELE-CVL-F-C300-CON-0200 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean con ground slab and manholes at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-26 | 2025-05-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 201 | Civil | RFI-ELE-CVL-F-C300-CON-0201 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean con CCW sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-26 | 2025-05-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 202 | Civil | RFI-ELE-CVL-F-C300-CON-0202 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean con substation staircase landing | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-26 | 2025-05-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 203 | Civil | RFI-ELE-CVL-F-C300-CON-0203 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of base sump pit CB4 and CB5 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-28 | 2025-05-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 204 | Civil | RFI-ELE-CVL-F-C300-CON-0204 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of base foundation for North Staircase at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-28 | 2025-05-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 205 | Civil | RFI-ELE-CVL-F-C300-CON-0205 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of base CCW S-18244 sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-29 | 2025-05-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 206 | Civil | RFI-ELE-CVL-F-C300-CON-0206 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean con South side staircase bottom foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-30 | 2025-05-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 207 | Civil | RFI-ELE-CVL-F-C300-CON-0207 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean con for base manholes MA3 and MA4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-30 | 2025-05-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 208 | Civil | RFI-ELE-CVL-F-C300-CON-0208 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for North Staircase bottom plinth at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-03 | 2025-06-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 209 | Civil | RFI-ELE-CVL-F-C300-CON-0209 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of sump pit CB4 and CB5 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-04 | 2025-06-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 210 | Civil | RFI-ELE-CVL-F-C300-CON-0210 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of South side staircase bottom foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-04 | 2025-06-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 211 | Civil | RFI-ELE-CVL-F-C300-CON-0211 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon groundslab GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-04 | 2025-06-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 212 | Civil | RFI-ELE-CVL-F-C300-CON-0212 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of CCW S-18244 sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-05 | 2025-06-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 213 | Civil | RFI-ELE-CVL-F-C300-CON-0213 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for South Staircase bottom plinth at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-05 | 2025-06-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 214 | Civil | RFI-ELE-CVL-F-C300-CON-0214 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for North Staircase Fligth at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-06 | 2025-06-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 215 | Civil | RFI-ELE-CVL-F-C300-CON-0215 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean con for base manholes MA3 and MA4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-06 | 2025-06-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 216 | Civil | RFI-ELE-CVL-F-C300-CON-0216 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean con for trench for Transfomer at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-10 | 2025-06-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 217 | Civil | RFI-ELE-CVL-F-C300-CON-0217 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for South Staircase Fligth at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-10 | 2025-06-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 218 | Civil | RFI-ELE-CVL-F-C300-CON-0218 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean con for P-16211 A and B at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-10 | 2025-06-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 219 | Civil | RFI-ELE-CVL-F-C300-CON-0219 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of GRE Pipe portion for Battery Room Slab at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-10 | 2025-06-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 220 | Civil | RFI-ELE-CVL-F-C300-CON-0220 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of trench for Transfomer at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-11 | 2025-06-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 221 | Civil | RFI-ELE-CVL-F-C300-CON-0221 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pump foundation P-16211 A and B at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-11 | 2025-06-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 222 | Civil | RFI-ELE-CVL-F-C300-CON-0222 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon groundslab GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-11 | 2025-06-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 223 | Civil | RFI-ELE-CVL-F-C300-CON-0223 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon for East IER Room RC Step Type 1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-16 | 2025-06-17 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 224 | Civil | RFI-ELE-CVL-F-C300-CON-0224 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of trench for Transfomer A and B at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-16 | 2025-06-17 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 225 | Civil | RFI-ELE-CVL-F-C300-CON-0225 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of foundation for East IER Room RC Step Type 1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-17 | 2025-06-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 226 | Civil | RFI-ELE-CVL-F-C300-CON-0226 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal for F9 Foundation (2 nos) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-17 | 2025-06-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 227 | Civil | RFI-ELE-CVL-F-C300-CON-0227 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of wall CCW S-18244 sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-20 | 2025-06-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 228 | Civil | RFI-ELE-CVL-F-C300-CON-0228 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of East IER Room RC Step Type 1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-24 | 2025-06-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 229 | Civil | RFI-ELE-CVL-F-C300-CON-0229 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon for North IER Room RC Step Type 2 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-24 | 2025-06-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 230 | Civil | RFI-ELE-CVL-F-C300-CON-0230 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean con for trench for EDG at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-24 | 2025-06-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 231 | Civil | RFI-ELE-CVL-F-C300-CON-0231 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon groundslab GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-24 | 2025-06-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 232 | Civil | RFI-ELE-CVL-F-C300-CON-0232 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of wall and top CCW S-18244 sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-25 | 2025-06-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 233 | Civil | RFI-ELE-CVL-F-C300-CON-0233 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of precast cable support block at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-25 | 2025-06-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 234 | Civil | RFI-ELE-CVL-F-C300-CON-0234 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of Foundation for North IER Room RC Step Type 2 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-26 | 2025-06-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 235 | Civil | RFI-ELE-CVL-F-C300-CON-0235 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of base for trench for EDG at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-26 | 2025-06-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 236 | Civil | RFI-ELE-CVL-F-C300-CON-0236 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of wall for trench for EDG at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 237 | Civil | RFI-ELE-CVL-F-C300-CON-0237 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of flight for North IER Room RC Step Type 2 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 238 | Civil | RFI-ELE-CVL-F-C300-CON-0238 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon groundslab GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-01 | 2025-07-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 239 | Civil | RFI-ELE-CVL-F-C300-CON-0239 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of groundslab GL A-C/1-4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-04 | 2025-07-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 240 | Civil | RFI-ELE-CVL-F-C300-CON-0240 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon for cable tray support foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-08 | 2025-07-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 241 | Civil | RFI-ELE-CVL-F-C300-CON-0241 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for cable tray support foundation F1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-10 | 2025-07-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 242 | Civil | RFI-ELE-CVL-F-C300-CON-0242 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean con for Z-18213A foundation for Chilled Water Package | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-10 | 2025-07-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 243 | Civil | RFI-ELE-CVL-F-C300-CON-0243 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pileplug for Z-18213A foundation for Chilled Water Package | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-10 | 2025-07-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 244 | Civil | RFI-ELE-CVL-F-C300-CON-0244 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of groundslab GL A-C/4-8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-11 | 2025-07-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 245 | Civil | RFI-ELE-CVL-F-C300-CON-0245 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean con for Z-18213A foundation for Chilled Water Package | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-14 | 2025-07-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 246 | Civil | RFI-ELE-CVL-F-C300-CON-0246 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for cable tray support foundation pedestal F1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-14 | 2025-07-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 247 | Civil | RFI-ELE-CVL-F-C300-CON-0247 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean con PC 3 (E-18206) Foundation at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-14 | 2025-07-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 248 | Civil | RFI-ELE-CVL-F-C300-CON-0248 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pileplug PC 3 (E-18206) Foundation at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-14 | 2025-07-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 249 | Civil | RFI-ELE-CVL-F-C300-CON-0249 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for Z-18213A foundation for Chilled Water Package | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-16 | 2025-07-17 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 250 | Civil | RFI-ELE-CVL-F-C300-CON-0250 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for PC 3 (E-18206) Foundation at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-17 | 2025-07-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 251 | Civil | RFI-ELE-CVL-F-C300-CON-0251 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of roofslab GL A-C/1-3 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-18 | 2025-07-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 252 | Civil | RFI-ELE-CVL-F-C300-CON-0252 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of 1st Floor GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-28 | 2025-07-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 253 | Civil | RFI-ELE-CVL-F-C300-CON-0253 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of 2nd Floor GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-29 | 2025-07-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 254 | Civil | RFI-ELE-CVL-F-C300-CON-0254 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of roofslab kerb GL A-C/1-3 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-29 | 2025-07-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 255 | Civil | RFI-ELE-CVL-F-C300-CON-0255 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean concrete for TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-29 | 2025-07-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 256 | Civil | RFI-ELE-CVL-F-C300-CON-0256 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pileplug for TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-29 | 2025-07-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 257 | Civil | RFI-ELE-CVL-F-C300-CON-0257 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap for TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-02 | 2025-08-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 258 | Civil | RFI-ELE-CVL-F-C300-CON-0258 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon for P-16232 (P7) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-02 | 2025-08-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 259 | Civil | RFI-ELE-CVL-F-C300-CON-0259 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of 1st Mezzanine Floor GL A-B/3-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 260 | Civil | RFI-ELE-CVL-F-C300-CON-0260 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean con for foundation T 19230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-06 | 2025-08-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 261 | Civil | RFI-ELE-CVL-F-C300-CON-0261 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pileplug for foundation T 19230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-06 | 2025-08-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 262 | Civil | RFI-ELE-CVL-F-C300-CON-0262 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal for TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-07 | 2025-08-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 263 | Civil | RFI-ELE-CVL-F-C300-CON-0263 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation T 19230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-08 | 2025-08-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 264 | Civil | RFI-ELE-CVL-F-C300-CON-0264 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pedestal T 19230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-11 | 2025-08-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 265 | Civil | RFI-ELE-CVL-F-C300-CON-0265 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation melt tank pump P19221A/B at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-12 | 2025-08-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 266 | Civil | RFI-ELE-CVL-F-C300-CON-0266 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of 2nd Floor pump foundation and kerb GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-15 | 2025-08-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 267 | Civil | RFI-ELE-CVL-F-C300-CON-0267 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of 1st Mezzanine Floor GL A-B/3-7 pump foundation and kerb at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-16 | 2025-08-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 268 | Civil | RFI-ELE-CVL-F-C300-CON-0268 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean concrete for new pump P19231 A/B and P19232 A/B at Scubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-16 | 2025-08-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 269 | Civil | RFI-ELE-CVL-F-C300-CON-0269 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean concrete for D16227 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-16 | 2025-08-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 270 | Civil | RFI-ELE-CVL-F-C300-CON-0270 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of foundation for new pump P19231 A/B and P19232 A/B at Scubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-19 | 2025-08-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 271 | Civil | RFI-ELE-CVL-F-C300-CON-0271 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of foundation for D16227 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-19 | 2025-08-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 272 | Civil | RFI-ELE-CVL-F-C300-CON-0272 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean con for compound slab TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 273 | Civil | RFI-ELE-CVL-F-C300-CON-0273 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal for D16227 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-21 | 2025-08-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 274 | Civil | RFI-ELE-CVL-F-C300-CON-0274 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of foundation for new pump P19231 B at Scubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-28 | 2025-08-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 275 | Civil | RFI-ELE-CVL-F-C300-CON-0275 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of compound slab TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-30 | 2025-09-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 276 | Civil | RFI-ELE-CVL-F-C300-CON-0276 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of cable tray support foundation near Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-30 | 2025-09-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 277 | Civil | RFI-ELE-CVL-F-C300-CON-0277 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pump foundation for P-18204A/B at Demineralise Water Pump Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-06 | 2025-09-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 278 | Civil | RFI-ELE-CVL-F-C300-CON-0278 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of cable tray support foundation near Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-06 | 2025-09-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 279 | Civil | RFI-ELE-CVL-F-C300-CON-0279 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of foundation for P-16232 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-06 | 2025-09-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 280 | Civil | RFI-ELE-CVL-F-C300-CON-0280 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of 1st Mezzanine Floor GL A-B/3-7 pump foundation and kerb at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-10 | 2025-09-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 281 | Civil | RFI-ELE-CVL-F-C300-CON-0281 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon for MC10 Manhole | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-12 | 2025-09-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 282 | Civil | RFI-ELE-CVL-F-C300-CON-0282 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for leancon at F5 and F6 at SP 10 Platform | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-12 | 2025-09-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 283 | Civil | RFI-ELE-CVL-F-C300-CON-0283 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for stair foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-12 | 2025-09-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 284 | Civil | RFI-ELE-CVL-F-C300-CON-0284 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation at F5 and F6 at SP 10 Platform | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-17 | 2025-09-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 285 | Civil | RFI-ELE-CVL-F-C300-CON-0285 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for stair foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-17 | 2025-09-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 286 | Civil | RFI-ELE-CVL-F-C300-CON-0286 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of 1st Mezzanine Floor GL A-B/3-7 pump foundation and kerb at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-19 | 2025-09-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 287 | Civil | RFI-ELE-CVL-F-C300-CON-0287 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of 1st Floor Z-19206 A/B/C Fines Sifter at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-19 | 2025-09-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 288 | Civil | RFI-ELE-CVL-F-C300-CON-0288 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of 2nd Floor slab GL A-B/6-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-19 | 2025-09-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 289 | Civil | RFI-ELE-CVL-F-C300-CON-0289 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon for 2 nos F2, 1 nos F3 and 4 nos F5 foundation at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-19 | 2025-09-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 290 | Civil | RFI-ELE-CVL-F-C300-CON-0290 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of Pileplug for 2 nos F2, 1 nos F3 and 4 nos F5 foundation at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-19 | 2025-09-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 291 | Civil | RFI-ELE-CVL-F-C300-CON-0291 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of foundation chimney S-19232 at Roof Slab Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-19 | 2025-09-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 292 | Civil | RFI-ELE-CVL-F-C300-CON-0292 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pilecap for 2 nos F2, 1 nos F3, 1 nos F7 and 4 nos F5 foundation at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-20 | 2025-09-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 293 | Civil | RFI-ELE-CVL-F-C300-CON-0293 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pedestal at F5 and F6 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-22 | 2025-09-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 294 | Civil | RFI-ELE-CVL-F-C300-CON-0294 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of 2nd Floor kerb GL A-B/6-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-22 | 2025-09-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 295 | Civil | RFI-ELE-CVL-F-C300-CON-0295 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-22 | 2025-09-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 296 | Civil | RFI-ELE-CVL-F-C300-CON-0296 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon for MA5, MA6 and MA7 Manholes around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-22 | 2025-09-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 297 | Civil | RFI-ELE-CVL-F-C300-CON-0297 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pedestal 2 nos F5, 2 nos F1 and 2 nos F2 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-23 | 2025-09-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 298 | Civil | RFI-ELE-CVL-F-C300-CON-0298 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for leancon 1 nos F7 and 1 nos F3 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-23 | 2025-09-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 299 | Civil | RFI-ELE-CVL-F-C300-CON-0299 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for leancon apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-23 | 2025-09-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 300 | Civil | RFI-ELE-CVL-F-C300-CON-0300 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-23 | 2025-09-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 301 | Civil | RFI-ELE-CVL-F-C300-CON-0301 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-24 | 2025-09-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 302 | Civil | RFI-ELE-CVL-F-C300-CON-0302 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap 1 nos F7 and 1 nos F3 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-24 | 2025-09-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 303 | Civil | RFI-ELE-CVL-F-C300-CON-0303 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap 1 nos F1 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-24 | 2025-09-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 304 | Civil | RFI-ELE-CVL-F-C300-CON-0304 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 305 | Civil | RFI-ELE-CVL-F-C300-CON-0305 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pedestal 1 nos F7 and 1 nos F3 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 306 | Civil | RFI-ELE-CVL-F-C300-CON-0306 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean con for D 18220 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-26 | 2025-09-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 307 | Civil | RFI-ELE-CVL-F-C300-CON-0307 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pileplug for D 18220 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-26 | 2025-09-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 308 | Civil | RFI-ELE-CVL-F-C300-CON-0308 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-26 | 2025-09-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 309 | Civil | RFI-ELE-CVL-F-C300-CON-0309 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for precast manholes MA5, MA6, MA7 and MA8 for C300 at M-One Precast Yard | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-26 | 2025-09-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 310 | Civil | RFI-ELE-CVL-F-C300-CON-0310 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pilecap for D 18220 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-27 | 2025-09-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 311 | Civil | RFI-ELE-CVL-F-C300-CON-0311 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-27 | 2025-09-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 312 | Civil | RFI-ELE-CVL-F-C300-CON-0312 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pedestal for D 18220 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-29 | 2025-09-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 313 | Civil | RFI-ELE-CVL-F-C300-CON-0313 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for leancon for YM 18250 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-29 | 2025-09-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 314 | Civil | RFI-ELE-CVL-F-C300-CON-0314 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of foundation for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-29 | 2025-09-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 315 | Civil | RFI-ELE-CVL-F-C300-CON-0315 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of base MA5, MA6, MA7 and MC10 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-30 | 2025-09-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 316 | Civil | RFI-ELE-CVL-F-C300-CON-0316 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation for YM 18250 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-30 | 2025-10-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 317 | Civil | RFI-ELE-CVL-F-C300-CON-0317 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of wall MA5, MA6, MA7 and MC10 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-01 | 2025-10-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 318 | Civil | RFI-ELE-CVL-F-C300-CON-0318 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of foundation for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-02 | 2025-10-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 319 | Civil | RFI-ELE-CVL-F-C300-CON-0319 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-02 | 2025-10-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 320 | Civil | RFI-ELE-CVL-F-C300-CON-0320 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean con for MC1 and MC6 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-06 | 2025-10-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 321 | Civil | RFI-ELE-CVL-F-C300-CON-0321 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for leancon apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-07 | 2025-10-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 322 | Civil | RFI-ELE-CVL-F-C300-CON-0322 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of top MA5, MA6, MA7 and MC10 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-07 | 2025-10-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 323 | Civil | RFI-ELE-CVL-F-C300-CON-0323 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-08 | 2025-10-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 324 | Civil | RFI-ELE-CVL-F-C300-CON-0324 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean con foundation for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-08 | 2025-10-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 325 | Civil | RFI-ELE-CVL-F-C300-CON-0325 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for apron slab and ramp around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-09 | 2025-10-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 326 | Civil | RFI-ELE-CVL-F-C300-CON-0326 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for apron slab around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-10 | 2025-10-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 327 | Civil | RFI-ELE-CVL-F-C300-CON-0327 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of foundation for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-10 | 2025-10-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 328 | Civil | RFI-ELE-CVL-F-C300-CON-0328 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for apron slab around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-11 | 2025-10-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 329 | Civil | RFI-ELE-CVL-F-C300-CON-0329 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of foundation for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-11 | 2025-10-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 330 | Civil | RFI-ELE-CVL-F-C300-CON-0330 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for apron slab around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-13 | 2025-10-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 331 | Civil | RFI-ELE-CVL-F-C300-CON-0331 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon for slab at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-13 | 2025-10-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 332 | Civil | RFI-ELE-CVL-F-C300-CON-0332 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon for cable C360 support foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-13 | 2025-10-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 333 | Civil | RFI-ELE-CVL-F-C300-CON-0333 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of concrete for F1 Service Platform foundation at Demin Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-13 | 2025-10-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 334 | Civil | RFI-ELE-CVL-F-C300-CON-0334 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon for MC7 Manholes | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-13 | 2025-10-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 335 | Civil | RFI-ELE-CVL-F-C300-CON-0335 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of pedestal for F1 Service Platform foundation at Demin Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-14 | 2025-10-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 336 | Civil | RFI-ELE-CVL-F-C300-CON-0336 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of foundation for cable C360 support foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-14 | 2025-10-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 337 | Civil | RFI-ELE-CVL-F-C300-CON-0337 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of bund wall for TK16230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-17 | 2025-10-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 338 | Civil | RFI-ELE-CVL-F-C300-CON-0338 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for apron slab and ramp around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-17 | 2025-10-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 339 | Civil | RFI-ELE-CVL-F-C300-CON-0339 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for stair landing foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-17 | 2025-10-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 340 | Civil | RFI-ELE-CVL-F-C300-CON-0340 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of base MC2, MC7 and wall MC1 and MC6 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-18 | 2025-10-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 341 | Civil | RFI-ELE-CVL-F-C300-CON-0341 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of gully trap GT-1 at Substation C2015 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-18 | 2025-10-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 342 | Civil | RFI-ELE-CVL-F-C300-CON-0342 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean con for Manholes MC4 and MC8 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-20 | 2025-10-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 343 | Civil | RFI-ELE-CVL-F-C300-CON-0343 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for apron slab and ramp around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-20 | 2025-10-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 344 | Civil | RFI-ELE-CVL-F-C300-CON-0344 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for precast manholes MA5, MA6, MA7 and MA8 for C300 at M-One Precast Yard | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-21 | 2025-10-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 345 | Civil | RFI-ELE-CVL-F-C300-CON-0345 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of slab at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-24 | 2025-10-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 346 | Civil | RFI-ELE-CVL-F-C300-CON-0346 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of kerb at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-03 | 2025-11-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 347 | Civil | RFI-ELE-CVL-F-C300-CON-0347 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for apron slab and ramp around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-03 | 2025-11-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 348 | Civil | RFI-ELE-CVL-F-C300-CON-0348 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pipe support foundation and D-18214 at Demin Water Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-10 | 2025-11-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 349 | Civil | RFI-ELE-CVL-F-C300-CON-0349 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for RC step Type 3 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-10 | 2025-11-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 350 | Civil | RFI-ELE-CVL-F-C300-CON-0350 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for leancon MC5 at Manholes C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-13 | 2025-11-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 351 | Civil | RFI-ELE-CVL-F-C300-CON-0351 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for leancon rigid paving at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-14 | 2025-11-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 352 | Civil | RFI-ELE-CVL-F-C300-CON-0352 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pipe support foundation at Demin Water Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-14 | 2025-11-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 353 | Civil | RFI-ELE-CVL-F-C300-CON-0353 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for base for MC4 and MC5, wall for MC2 and MC7 at Manholes C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-14 | 2025-11-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 354 | Civil | RFI-ELE-CVL-F-C300-CON-0354 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for rigid paving at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-19 | 2025-11-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 355 | Civil | RFI-ELE-CVL-F-C300-CON-0355 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for Wall for MC4 and MC5 Manholes C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-20 | 2025-11-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 356 | Civil | RFI-ELE-CVL-F-C300-CON-0356 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for kerb paving at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-21 | 2025-11-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 357 | Civil | RFI-ELE-CVL-F-C300-CON-0357 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection Service Platform SP-07 Foundation at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-26 | 2025-11-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 358 | Civil | RFI-ELE-CVL-F-C300-CON-0358 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of lean concrete for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-29 | 2025-11-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 359 | Civil | RFI-ELE-CVL-F-C300-CON-0359 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-29 | 2025-12-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 360 | Civil | RFI-ELE-CVL-F-C300-CON-0360 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for slab opening at 1st Floor Briquetting Building (SI-085) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-01 | 2025-12-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 361 | Civil | RFI-ELE-CVL-F-C300-CON-0361 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-03 | 2025-12-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 362 | Civil | RFI-ELE-CVL-F-C300-CON-0362 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for Manhole MC8 base at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-05 | 2025-12-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 363 | Civil | RFI-ELE-CVL-F-C300-CON-0363 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean con pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-08 | 2025-12-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 364 | Civil | RFI-ELE-CVL-F-C300-CON-0364 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-09 | 2025-12-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 365 | Civil | RFI-ELE-CVL-F-C300-CON-0365 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for Manhole MC8 wall at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-09 | 2025-12-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 366 | Civil | RFI-ELE-CVL-F-C300-CON-0366 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean con pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-11 | 2025-12-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 367 | Civil | RFI-ELE-CVL-F-C300-CON-0367 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-16 | 2025-12-17 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 368 | Civil | RFI-ELE-CVL-F-C300-CON-0368 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean con pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-19 | 2025-12-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 369 | Civil | RFI-ELE-CVL-F-C300-CON-0369 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-23 | 2025-12-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 370 | Civil | RFI-ELE-CVL-F-C300-CON-0370 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-27 | 2025-12-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 371 | Civil | RFI-ELE-CVL-F-C300-CON-0371 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean con for TK16230 stairs foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-27 | 2025-12-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 372 | Civil | RFI-ELE-CVL-F-C300-CON-0372 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for foundation for TK16230 stairs foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-27 | 2025-12-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 373 | Civil | RFI-ELE-CVL-F-C300-CON-0373 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon for apron slab GL A/ 5-10 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-27 | 2025-12-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 374 | Civil | RFI-ELE-CVL-F-C300-CON-0374 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for apron slab GL A/ 5-10 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-30 | 2025-12-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 375 | Civil | RFI-ELE-CVL-F-C300-CON-0375 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pavement kerb at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-30 | 2025-12-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 376 | Civil | RFI-ELE-CVL-F-C300-CON-0376 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean concrete for manholes MA8 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-03 | 2026-01-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 377 | Civil | RFI-ELE-CVL-F-C300-CON-0377 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon for apron slab at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-06 | 2026-01-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 378 | Civil | RFI-ELE-CVL-F-C300-CON-0378 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for apron slab at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-09 | 2026-01-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 379 | Civil | RFI-ELE-CVL-F-C300-CON-0379 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for stairs TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-12 | 2026-01-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 380 | Civil | RFI-ELE-CVL-F-C300-CON-0380 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection of leancon for apron slab at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-12 | 2026-01-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 381 | Civil | RFI-ELE-CVL-F-C300-CON-0381 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for base concrete for manholes MA8 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-12 | 2026-01-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 382 | Civil | RFI-ELE-CVL-F-C300-CON-0382 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for air vent support for MC4, MC5, MC6, MC7, MA6 and MA7 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-12 | 2026-01-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 383 | Civil | RFI-ELE-CVL-F-C300-CON-0383 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for Wall and Top concrete for manholes MA8 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-19 | 2026-01-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 384 | Civil | RFI-ELE-CVL-F-C300-CON-0384 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for Stairs foundation for Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-19 | 2026-01-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 385 | Civil | RFI-ELE-CVL-F-C300-CON-0385 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for manhole cover MC1, MC4, MC5, MC6 and MC7 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-19 | 2026-01-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 386 | Civil | RFI-ELE-CVL-F-C300-CON-0386 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean concrete for ramp at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-19 | 2026-01-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 387 | Civil | RFI-ELE-CVL-F-C300-CON-0387 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for concrete for apron at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-19 | 1900-01-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 388 | Civil | RFI-ELE-CVL-F-C300-CON-0388 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for concrete heavy duty paving near Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-19 | 1900-01-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 389 | Civil | RFI-ELE-CVL-F-C300-CON-0389 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for Stairs foundation for Demin Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-22 | 2026-01-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 390 | Civil | RFI-ELE-CVL-F-C300-CON-0390 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-22 | 2026-01-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 391 | Civil | RFI-ELE-CVL-F-C300-CON-0391 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for ramp at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-24 | 2026-01-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 392 | Civil | RFI-ELE-CVL-F-C300-CON-0392 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for airvent pipe support for MC2, MC10 and MC8 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-24 | 2026-01-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 393 | Civil | RFI-ELE-CVL-F-C300-CON-0393 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for leancon ramp at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-26 | 2026-01-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 394 | Civil | RFI-ELE-CVL-F-C300-CON-0394 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for leancon pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-26 | 2026-01-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 395 | Civil | RFI-ELE-CVL-F-C300-CON-0395 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for Heavy Duty Pavement at Man Refiner (South) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-27 | 2026-01-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 396 | Civil | RFI-ELE-CVL-F-C300-CON-0396 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for manhole cover MC1, MC2, MC4, MC5, MC8 and MA8 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-28 | 2026-01-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 397 | Civil | RFI-ELE-CVL-F-C300-CON-0397 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for airvent pipe support MA5. MA6 and MA7 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-30 | 2026-01-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 398 | Civil | RFI-ELE-CVL-F-C300-CON-0398 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for rigid pavement and PL07 pipe support at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-30 | 2026-01-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 399 | Civil | RFI-ELE-CVL-F-C300-CON-0399 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for slab around MC10 at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-30 | 2026-01-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 400 | Civil | RFI-ELE-CVL-F-C300-CON-0400 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for lean con for ramp at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-30 | 2026-01-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 401 | Civil | RFI-ELE-CVL-F-C300-CON-0401 | External | Eleco | Civil Work | N/A | RC Work | Pour concrete | Inspection for ramp at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-30 | 2026-01-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing

## 08.RFI_PSC
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-30
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-CVL-F-C300-PSC-0001 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pile plug installation for Sub-station C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-17 | 2024-08-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 2 | Civil | RFI-ELE-CVL-F-C300-PSC-0002 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap's leancon for Sub-station C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-18 | 2024-08-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 3 | Civil | RFI-ELE-CVL-F-C300-PSC-0003 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap's leancon for Sub-station C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-23 | 2024-08-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 4 | Civil | RFI-ELE-CVL-F-C300-PSC-0004 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pile plug installation for Sub-station C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-23 | 2024-08-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 5 | Civil | RFI-ELE-CVL-F-C300-PSC-0005 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-26 | 2024-08-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 6 | Civil | RFI-ELE-CVL-F-C300-PSC-0006 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-08-29 | 2024-09-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 7 | Civil | RFI-ELE-CVL-F-C300-PSC-0007 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-05-04 | 2024-09-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 8 | Civil | RFI-ELE-CVL-F-C300-PSC-0008 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of stump for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-05-04 | 2024-09-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 9 | Civil | RFI-ELE-CVL-F-C300-PSC-0009 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-05-06 | 2024-09-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 10 | Civil | RFI-ELE-CVL-F-C300-PSC-0010 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pile plug installation for Sub-station C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-21 | 2024-09-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 11 | Civil | RFI-ELE-CVL-F-C300-PSC-0011 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap's leancon for Sub-station C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-21 | 2024-09-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 12 | Civil | RFI-ELE-CVL-F-C300-PSC-0012 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-24 | 2024-09-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 13 | Civil | RFI-ELE-CVL-F-C300-PSC-0013 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of broken pile rectification for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-24 | 2024-09-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 14 | Civil | RFI-ELE-CVL-F-C300-PSC-0014 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-26 | 2024-09-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 15 | Civil | RFI-ELE-CVL-F-C300-PSC-0015 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of stump for C-2105 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-30 | 2024-10-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 16 | Civil | RFI-ELE-CVL-F-C300-PSC-0016 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of groundbeam leancon Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-04 | 2024-10-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 17 | Civil | RFI-ELE-CVL-F-C300-PSC-0017 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of groundbeam Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-19 | 2024-10-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 18 | Civil | RFI-ELE-CVL-F-C300-PSC-0018 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of groundbeam Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-22 | 2024-10-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 19 | Civil | RFI-ELE-CVL-F-C300-PSC-0019 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pileplug installation MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-12 | 2024-11-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 20 | Civil | RFI-ELE-CVL-F-C300-PSC-0020 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation leancon MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-12 | 2024-11-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 21 | Civil | RFI-ELE-CVL-F-C300-PSC-0021 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pileplug installation MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-14 | 2024-11-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 22 | Civil | RFI-ELE-CVL-F-C300-PSC-0022 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation leancon MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-14 | 2024-11-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 23 | Civil | RFI-ELE-CVL-F-C300-PSC-0023 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of groundslab leancon Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-15 | 2024-11-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 24 | Civil | RFI-ELE-CVL-F-C300-PSC-0024 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation PC16 MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-16 | 2024-11-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 25 | Civil | RFI-ELE-CVL-F-C300-PSC-0025 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pileplug installation MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-18 | 2024-11-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 26 | Civil | RFI-ELE-CVL-F-C300-PSC-0026 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation leancon MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-18 | 2024-11-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 27 | Civil | RFI-ELE-CVL-F-C300-PSC-0027 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-23 | 2024-11-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 28 | Civil | RFI-ELE-CVL-F-C300-PSC-0028 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pileplug installation MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-23 | 2024-11-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 29 | Civil | RFI-ELE-CVL-F-C300-PSC-0029 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation leancon MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-23 | 2024-11-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 30 | Civil | RFI-ELE-CVL-F-C300-PSC-0030 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pileplug installation for Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-23 | 2024-11-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 31 | Civil | RFI-ELE-CVL-F-C300-PSC-0031 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation leancon for Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-23 | 2024-11-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 32 | Civil | RFI-ELE-CVL-F-C300-PSC-0032 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation PC16 top MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-29 | 2024-11-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 33 | Civil | RFI-ELE-CVL-F-C300-PSC-0033 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-29 | 2024-12-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 34 | Civil | RFI-ELE-CVL-F-C300-PSC-0034 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for groundslab Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-29 | 2024-12-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 35 | Civil | RFI-ELE-CVL-F-C300-PSC-0035 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for groundbeam Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-04 | 2024-12-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 36 | Civil | RFI-ELE-CVL-F-C300-PSC-0036 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean concrete at AHU-01A and B and HVAC control panel Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-07 | 2024-12-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 37 | Civil | RFI-ELE-CVL-F-C300-PSC-0037 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean concrete at PC4c and PC4 foundation Man refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-07 | 2024-12-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 38 | Civil | RFI-ELE-CVL-F-C300-PSC-0038 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for column G/level to 1st level GL A-D/2-3 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-09 | 2024-12-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 39 | Civil | RFI-ELE-CVL-F-C300-PSC-0039 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Pilecap Man Refiner Foundation PC4c and PC4d | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-10 | 2024-12-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 40 | Civil | RFI-ELE-CVL-F-C300-PSC-0040 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pileplug Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-10 | 2024-12-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 41 | Civil | RFI-ELE-CVL-F-C300-PSC-0041 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Pilecap Man Refiner Foundation PC4c topside, PC4d topside, PC8 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-12 | 2024-12-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 42 | Civil | RFI-ELE-CVL-F-C300-PSC-0042 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for EDG Foundation at Substation C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-13 | 2024-12-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 43 | Civil | RFI-ELE-CVL-F-C300-PSC-0043 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for column G/level to 1st level GL A-D/4-5a Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-13 | 2024-12-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 44 | Civil | RFI-ELE-CVL-F-C300-PSC-0044 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for column G/level to 1st level GL A-D/1x, GL C-D/1, GL A/5-7, GL B/7 and GL B1/5 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-17 | 2024-12-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 45 | Civil | RFI-ELE-CVL-F-C300-PSC-0045 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean concrete at PC6a, PC2b, 3 nos of PC2 and PC8a | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-17 | 2024-12-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 46 | Civil | RFI-ELE-CVL-F-C300-PSC-0046 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for PilePlug at PC6a, PC2b, 3 nos of PC2 and PC8a | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-17 | 2024-12-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 47 | Civil | RFI-ELE-CVL-F-C300-PSC-0047 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for column G/level to 1st level GL B1-D / 6-8, GL C1/5A and GL D/5 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-19 | 2024-12-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 48 | Civil | RFI-ELE-CVL-F-C300-PSC-0048 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean concrete at PC2b, PC2 and PC9 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-19 | 2024-12-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 49 | Civil | RFI-ELE-CVL-F-C300-PSC-0049 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for PilePlug at PC2b, PC2 and PC9 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-19 | 2024-12-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 50 | Civil | RFI-ELE-CVL-F-C300-PSC-0050 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Pilecap Man Refiner Foundation PC6a, PC8a, PC2 (2 unit) and PC2b | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-20 | 2024-12-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 51 | Civil | RFI-ELE-CVL-F-C300-PSC-0051 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Pileplug Man Refiner Foundation PC9, PC2b, PC6b, PC2 and PC2a | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-20 | 2024-12-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 52 | Civil | RFI-ELE-CVL-F-C300-PSC-0052 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Leancon Man Refiner Foundation PC6b, PC2 and PC2a | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-20 | 2024-12-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 53 | Civil | RFI-ELE-CVL-F-C300-PSC-0053 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Pilecap Transformer MCC-A and MCC-B foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-20 | 2024-12-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 54 | Civil | RFI-ELE-CVL-F-C300-PSC-0054 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Pilecap PC9, PC2b and PC2 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-21 | 2024-12-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 55 | Civil | RFI-ELE-CVL-F-C300-PSC-0055 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for 2nd Cast PC8a at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-23 | 2024-12-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 56 | Civil | RFI-ELE-CVL-F-C300-PSC-0056 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for leancon Man Refiner Foundation PC4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-23 | 2024-12-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 57 | Civil | RFI-ELE-CVL-F-C300-PSC-0057 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pedestal C1 PC 11, GL A/3, for Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-23 | 2024-12-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 58 | Civil | RFI-ELE-CVL-F-C300-PSC-0058 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap PC4 and PC6b at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 59 | Civil | RFI-ELE-CVL-F-C300-PSC-0059 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for leancon PC2, PC2a, PC2b/C1 and PC24 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 60 | Civil | RFI-ELE-CVL-F-C300-PSC-0060 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pileplug PC2, PC2a, PC2b/C1 and PC24 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 61 | Civil | RFI-ELE-CVL-F-C300-PSC-0061 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Pedestal C1 for PC11, PC8, PC6a and PC2b | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 62 | Civil | RFI-ELE-CVL-F-C300-PSC-0062 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for leancon for TK-18203 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 63 | Civil | RFI-ELE-CVL-F-C300-PSC-0063 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pileplug for TK-18203 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 64 | Civil | RFI-ELE-CVL-F-C300-PSC-0064 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pedestal for pilecap PC6c, PC6, PC5, PC12, PC8a, PC9, PC2 and PC2a | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-26 | 2024-12-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 65 | Civil | RFI-ELE-CVL-F-C300-PSC-0065 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pedestal for pilecap PC11, PC2 (2 nos), PC1 and PC6b | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-27 | 2024-12-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 66 | Civil | RFI-ELE-CVL-F-C300-PSC-0066 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap PC2,PC2a, PC2b at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-27 | 2024-12-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 67 | Civil | RFI-ELE-CVL-F-C300-PSC-0067 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for leancon pilecap PC2a at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-27 | 2024-12-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 68 | Civil | RFI-ELE-CVL-F-C300-PSC-0068 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pileplug pilecap PC2a at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-27 | 2024-12-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 69 | Civil | RFI-ELE-CVL-F-C300-PSC-0069 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap PC5/C1 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-28 | 2024-12-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 70 | Civil | RFI-ELE-CVL-F-C300-PSC-0070 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pedestal for pilecap PC2/PS, PC2a/PS, PC2b/PS at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-28 | 2024-12-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 71 | Civil | RFI-ELE-CVL-F-C300-PSC-0071 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean con for pilecap PC 8b and PC4/C1 (2 nos) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-28 | 2024-12-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 72 | Civil | RFI-ELE-CVL-F-C300-PSC-0072 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pileplug for pilecap PC 8b and PC4/C1 (2 nos) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-28 | 2024-12-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 73 | Civil | RFI-ELE-CVL-F-C300-PSC-0073 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pedestal for pilecap PC5 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-30 | 2025-01-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 74 | Civil | RFI-ELE-CVL-F-C300-PSC-0074 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for leancon for pilecap PC6d/C1 , PC12/C1 and PC8b | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-31 | 2025-01-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 75 | Civil | RFI-ELE-CVL-F-C300-PSC-0075 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap PC4/C1 2 nos at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-31 | 2025-01-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 76 | Civil | RFI-ELE-CVL-F-C300-PSC-0076 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection pedestal PC2a/C1 GL d/7 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-01 | 2025-01-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 77 | Civil | RFI-ELE-CVL-F-C300-PSC-0077 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection pilecap PC24 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-02 | 2025-01-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 78 | Civil | RFI-ELE-CVL-F-C300-PSC-0078 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection pedestal PC2b/C1 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-02 | 2025-01-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 79 | Civil | RFI-ELE-CVL-F-C300-PSC-0079 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection leancon for PC6d/C1 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-02 | 2025-01-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 80 | Civil | RFI-ELE-CVL-F-C300-PSC-0080 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection pileplug for PC6d/C1 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-02 | 2025-01-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 81 | Civil | RFI-ELE-CVL-F-C300-PSC-0081 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection pilecap for PC5, PC12/C1 GL E/5, and PC8b at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-03 | 2025-01-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 82 | Civil | RFI-ELE-CVL-F-C300-PSC-0082 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection pilecap for AHU-01 A and 01B, HVAC Control Panel Foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-03 | 2025-01-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 83 | Civil | RFI-ELE-CVL-F-C300-PSC-0083 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap PC8a,PC12/C1,PC6d/C1 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-05 | 2025-01-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 84 | Civil | RFI-ELE-CVL-F-C300-PSC-0084 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pedestal PC4/C1 (2nos) Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-05 | 2025-01-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 85 | Civil | RFI-ELE-CVL-F-C300-PSC-0085 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection leancon for pilecap GL A-A2 - 27' -29' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-06 | 2025-01-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 86 | Civil | RFI-ELE-CVL-F-C300-PSC-0086 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal PC12, PC 6d, PC8b and PC24 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-07 | 2025-01-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 87 | Civil | RFI-ELE-CVL-F-C300-PSC-0087 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of foundation TK 18203 Demin Water Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-08 | 2025-01-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 88 | Civil | RFI-ELE-CVL-F-C300-PSC-0088 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal PC24 (saddle) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-09 | 2025-01-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 89 | Civil | RFI-ELE-CVL-F-C300-PSC-0089 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation leancon Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-10 | 2025-01-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 90 | Civil | RFI-ELE-CVL-F-C300-PSC-0090 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation leancon Briquetting Building-PC22,PC6 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-15 | 2025-01-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 91 | Civil | RFI-ELE-CVL-F-C300-PSC-0091 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation pileplug for PC22, PC6, PC5a and PC5 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-16 | 2025-01-17 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 92 | Civil | RFI-ELE-CVL-F-C300-PSC-0092 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for slab and beam 1st floor for Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-16 | 2025-01-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 93 | Civil | RFI-ELE-CVL-F-C300-PSC-0093 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap GL A-A2 - 27' -29' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-16 | 2025-01-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 94 | Civil | RFI-ELE-CVL-F-C300-PSC-0094 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal PC24 (free saddle) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-17 | 2025-01-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 95 | Civil | RFI-ELE-CVL-F-C300-PSC-0095 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of column GL A-D/1X at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-22 | 2025-01-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 96 | Civil | RFI-ELE-CVL-F-C300-PSC-0096 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap GL A1' -A2'/ 28' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-22 | 2025-01-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 97 | Civil | RFI-ELE-CVL-F-C300-PSC-0097 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal GL A1' -A2'/ 29' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-22 | 2025-01-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 98 | Civil | RFI-ELE-CVL-F-C300-PSC-0098 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap PC6 and PC5a at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-23 | 2025-01-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 99 | Civil | RFI-ELE-CVL-F-C300-PSC-0099 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon for pilecap D-2806 at Esstar Vision Compound | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-25 | 2025-01-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 100 | Civil | RFI-ELE-CVL-F-C300-PSC-0100 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap D-2806 at Esstar Vision Compound | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-25 | 2025-01-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 101 | Civil | RFI-ELE-CVL-F-C300-PSC-0101 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap GL A-C/1-4 for Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-27 | 2025-01-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 102 | Civil | RFI-ELE-CVL-F-C300-PSC-0102 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pileplug PC6/C1 (3nos),PC6a/C1 (2nos) and PC6c/C1 for Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-27 | 2025-01-28 | 6.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 103 | Civil | RFI-ELE-CVL-F-C300-PSC-0103 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of column GL A-D/4-8 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-31 | 2025-02-02 | 6.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 104 | Civil | RFI-ELE-CVL-F-C300-PSC-0104 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon for pilecap PC6/C1 and PC8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-31 | 2025-02-02 | 6.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 105 | Civil | RFI-ELE-CVL-F-C300-PSC-0105 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap PC6/C1, PC6c/C1 and PC6a/C1 GL A-B/3-4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-01 | 2025-02-04 | 6.00 PM | H | W | N/A | R | Hanis | C300 | Accepted
| 106 | Civil | RFI-ELE-CVL-F-C300-PSC-0106 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of stump column at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-04 | 2025-02-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 107 | Civil | RFI-ELE-CVL-F-C300-PSC-0107 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pileplug at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-04 | 2025-02-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 108 | Civil | RFI-ELE-CVL-F-C300-PSC-0108 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap GL A1' -A2'/ 27-29 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 109 | Civil | RFI-ELE-CVL-F-C300-PSC-0109 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal GL A1' -A2'/27- 29' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 110 | Civil | RFI-ELE-CVL-F-C300-PSC-0110 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of column 1st-RL GL B-D/2-3 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 111 | Civil | RFI-ELE-CVL-F-C300-PSC-0111 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of stump column at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Cancelled
| 112 | Civil | RFI-ELE-CVL-F-C300-PSC-0112 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pileplug at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 113 | Civil | RFI-ELE-CVL-F-C300-PSC-0113 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of stump column at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-06 | 2024-02-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 114 | Civil | RFI-ELE-CVL-F-C300-PSC-0114 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-06 | 2024-02-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 115 | Civil | RFI-ELE-CVL-F-C300-PSC-0115 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-07 | 2025-02-09 | 9:00 | H | W | N/A | R | Hanis | C300 | Accepted
| 116 | Civil | RFI-ELE-CVL-F-C300-PSC-0116 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon for pilecap at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-07 | 2025-02-09 | 9:00 | H | W | N/A | R | Hanis | C300 | Accepted
| 117 | Civil | RFI-ELE-CVL-F-C300-PSC-0117 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pileplug at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-07 | 2025-02-09 | 9:00 | H | W | N/A | R | Hanis | C300 | Accepted
| 118 | Civil | RFI-ELE-CVL-F-C300-PSC-0118 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of raft foundation Battery Room at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-07 | 2025-02-09 | 9:00 | H | W | N/A | R | Hanis | C300 | Accepted
| 119 | Civil | RFI-ELE-CVL-F-C300-PSC-0119 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of column 1st-RL at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0004 | B | 2024-02-08 | 2024-02-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 120 | Civil | RFI-ELE-CVL-F-C300-PSC-0120 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pileplug at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-11 | 2024-02-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 121 | Civil | RFI-ELE-CVL-F-C300-PSC-0121 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon for pilecap at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-11 | 2024-02-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 122 | Civil | RFI-ELE-CVL-F-C300-PSC-0122 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-11 | 2024-02-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 123 | Civil | RFI-ELE-CVL-F-C300-PSC-0123 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of stump column at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-11 | 2024-02-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 124 | Civil | RFI-ELE-CVL-F-C300-PSC-0124 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap GL A1' -A2'/ 27-29 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-11 | 2024-02-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 125 | Civil | RFI-ELE-CVL-F-C300-PSC-0125 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal GL A1' -A2'/27- 29' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-13 | 2024-02-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 126 | Civil | RFI-ELE-CVL-F-C300-PSC-0126 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of column 1st-RL at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-11 | 2024-02-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 127 | Civil | RFI-ELE-CVL-F-C300-PSC-0127 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap PC3/C2 GL C/9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 128 | Civil | RFI-ELE-CVL-F-C300-PSC-0128 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon PC7a/C1 and PC6b/C1 GL B/5-6 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 129 | Civil | RFI-ELE-CVL-F-C300-PSC-0129 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of Pileplug PC7a/C1 and PC6b/C1 GL B/5-6 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 130 | Civil | RFI-ELE-CVL-F-C300-PSC-0130 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon Groundbeam GL A/1-2, A-C/1 and C/1-4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 131 | Civil | RFI-ELE-CVL-F-C300-PSC-0131 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal PC4/C2 GL C/8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 132 | Civil | RFI-ELE-CVL-F-C300-PSC-0132 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap Z-19208A Weighing Machines and Silo Foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-19 | 2025-01-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 133 | Civil | RFI-ELE-CVL-F-C300-PSC-0133 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap PC6b and PC6d GL B/6-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-19 | 2025-02-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 134 | Civil | RFI-ELE-CVL-F-C300-PSC-0134 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap PC7a/C1 GL B/5 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-20 | 2025-02-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 135 | Civil | RFI-ELE-CVL-F-C300-PSC-0135 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon PC3/C2 GL C/10 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-20 | 2025-02-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 136 | Civil | RFI-ELE-CVL-F-C300-PSC-0136 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pileplug PC3/C2 GL C/10 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-20 | 2025-02-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 137 | Civil | RFI-ELE-CVL-F-C300-PSC-0137 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal PC3/C2 GL C/9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-20 | 2025-02-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 138 | Civil | RFI-ELE-CVL-F-C300-PSC-0138 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of roof slab and beam at GL A-D/4-8 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-22 | 2025-02-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 139 | Civil | RFI-ELE-CVL-F-C300-PSC-0139 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of roof beam at GL A-D/1x-1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-22 | 2025-02-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 140 | Civil | RFI-ELE-CVL-F-C300-PSC-0140 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of ground beam Gl A-C/ 1-5 for Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-25 | 2025-02-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 141 | Civil | RFI-ELE-CVL-F-C300-PSC-0141 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap PC3/C2 GL C/10 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-25 | 2025-02-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 142 | Civil | RFI-ELE-CVL-F-C300-PSC-0142 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean con for PC4/C2 (2 nos) GL C/11-12, Z-19208B, Z-19240 Equipment foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-25 | 2025-02-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 143 | Civil | RFI-ELE-CVL-F-C300-PSC-0143 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pileplug for PC4/C2 (2 nos) GL C/11-12, Z-19208B, Z-19240 Equipment foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-25 | 2025-02-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 144 | Civil | RFI-ELE-CVL-F-C300-PSC-0144 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of foundation pilecap Z-19208B & D-19220 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-27 | 2025-02-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 145 | Civil | RFI-ELE-CVL-F-C300-PSC-0145 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap for PC4/C2 (2 nos) GL C/11-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-27 | 2025-03-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 146 | Civil | RFI-ELE-CVL-F-C300-PSC-0146 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap for PC4/C2 GL A/12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-28 | 2025-03-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 147 | Civil | RFI-ELE-CVL-F-C300-PSC-0147 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean con for PC6/C1 and PC7/C1 GL A/5-6, and Z-19208C at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-28 | 2025-03-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 148 | Civil | RFI-ELE-CVL-F-C300-PSC-0148 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilepug for PC6/C1 and PC7/C1 GL A/5-6, and Z-19208C at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-28 | 2025-03-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 149 | Civil | RFI-ELE-CVL-F-C300-PSC-0149 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of roof slab GL A-D/1-4 for Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-03 | 2025-03-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 150 | Civil | RFI-ELE-CVL-F-C300-PSC-0150 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pile cap PC6/C1 GL A/4-5 and Z-19208C at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-04 | 2025-03-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 151 | Civil | RFI-ELE-CVL-F-C300-PSC-0151 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of groundbeam GL C/4-9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-04 | 2025-03-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 152 | Civil | RFI-ELE-CVL-F-C300-PSC-0152 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean con PC3/C2 (2nos) GL A/9-10 and PC4/C2 (2nos) GL A/11 and B/12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-04 | 2025-03-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 153 | Civil | RFI-ELE-CVL-F-C300-PSC-0153 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pileplug PC3/C2 (2nos) GL A/9-10 and PC4/C2 (2nos) GL A/11 and B/12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-04 | 2025-03-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 154 | Civil | RFI-ELE-CVL-F-C300-PSC-0154 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal PC5a, PC6a, PC6, PC7a, PC6b, and PC6d GL B/2-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-04 | 2025-03-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 155 | Civil | RFI-ELE-CVL-F-C300-PSC-0155 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean con P-18201A and P-18201B Pump Foundation at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-05 | 2025-03-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 156 | Civil | RFI-ELE-CVL-F-C300-PSC-0156 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap PC4/C2 (2 nos), PC3/C2 (2 nos) GL A/8-11 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 157 | Civil | RFI-ELE-CVL-F-C300-PSC-0157 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of Pedestal 2nd cast PC5/C1 GL B/1, PC6/C1 (3 nos), PC6a/C1 (2 nos), PC7/C1 (2 nos) and PC4/C2 GL A/1-8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 158 | Civil | RFI-ELE-CVL-F-C300-PSC-0158 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of groundbeam GL A/1-4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 159 | Civil | RFI-ELE-CVL-F-C300-PSC-0159 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal PC3/C2 and PC4/C2 (2nos) GL C/10-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 160 | Civil | RFI-ELE-CVL-F-C300-PSC-0160 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap PC4/C2 GL B/12, PC7/C1 GL A/6 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 161 | Civil | RFI-ELE-CVL-F-C300-PSC-0161 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon PC4/C2 GL A/8, PC3/C2 GL A/9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 162 | Civil | RFI-ELE-CVL-F-C300-PSC-0162 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pileplug PC4/C2 GL A/8, PC3/C2 GL A/9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 163 | Civil | RFI-ELE-CVL-F-C300-PSC-0163 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Pump Foundation P-18201A and P-18201B at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-07 | 2025-03-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 164 | Civil | RFI-ELE-CVL-F-C300-PSC-0164 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean concrete and pile plug Stretch Hood Device and ground beam GL A 4-6 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 165 | Civil | RFI-ELE-CVL-F-C300-PSC-0165 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap foundation Stretch Hood Device at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 166 | Civil | RFI-ELE-CVL-F-C300-PSC-0166 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap foundation D-19220 Foundation Melt Tank at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 167 | Civil | RFI-ELE-CVL-F-C300-PSC-0167 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of groundbeam GL A/4-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 168 | Civil | RFI-ELE-CVL-F-C300-PSC-0168 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of 2nd cast pedestal PC6/C1 (2nos) and PC6a/C1 GL A/1-4 Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 169 | Civil | RFI-ELE-CVL-F-C300-PSC-0169 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal PC4/C2 (4nos) and PC3/C2 (3nos) GL A-B/8-12 Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 170 | Civil | RFI-ELE-CVL-F-C300-PSC-0170 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of cast fascia GL A-D/ 4-8 at roof floor Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 171 | Civil | RFI-ELE-CVL-F-C300-PSC-0171 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of Lean concrete for ground beam GL A-C/8-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 172 | Civil | RFI-ELE-CVL-F-C300-PSC-0172 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of Lean concrete for PC7/C1 GL A/7 and foundation Stretch Hood Device GL A/8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 173 | Civil | RFI-ELE-CVL-F-C300-PSC-0173 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal for PC6a/C1 and PC6/C1 GL A/4-5 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 174 | Civil | RFI-ELE-CVL-F-C300-PSC-0174 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of groundbeam for GL A-C/8 -12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-13 | 2025-03-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 175 | Civil | RFI-ELE-CVL-F-C300-PSC-0175 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap for foundation Stretch Hood Device GL A/8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-13 | 2025-03-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 176 | Civil | RFI-ELE-CVL-F-C300-PSC-0176 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal for PC3/C2 (2 nos) and PC4/C2 (3 nos) GL B-C/9-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-14 | 2025-03-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 177 | Civil | RFI-ELE-CVL-F-C300-PSC-0177 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pedestal foundation D-19220 Foundation Melt Tank at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-14 | 2025-03-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 178 | Civil | RFI-ELE-CVL-F-C300-PSC-0178 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of Lean concrete for PC7/C1 GL A/7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-14 | 2025-03-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 179 | Civil | RFI-ELE-CVL-F-C300-PSC-0179 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pileplug for PC7/C1 GL A/7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-14 | 2025-03-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 180 | Civil | RFI-ELE-CVL-F-C300-PSC-0180 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of cast fascia GL A-D/ 4at roof floor Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-15 | 2025-03-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 181 | Civil | RFI-ELE-CVL-F-C300-PSC-0181 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal for PC3/C2 (2 nos) and PC4/C2 (3 nos) GL A-B/9-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-15 | 2025-03-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 182 | Civil | RFI-ELE-CVL-F-C300-PSC-0182 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap for PC7/C1 GL A/7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-17 | 2025-03-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 183 | Civil | RFI-ELE-CVL-F-C300-PSC-0183 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal for PC7/C1 GL A/7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-18 | 2025-03-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 184 | Civil | RFI-ELE-CVL-F-C300-PSC-0184 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon groundbeam for GL A/6-8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-18 | 2025-03-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 185 | Civil | RFI-ELE-CVL-F-C300-PSC-0185 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of groundbeam for GL A/6-8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-20 | 2025-03-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 186 | Civil | RFI-ELE-CVL-F-C300-PSC-0186 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean concrete at P-16214 and P-16247 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-22 | 2025-03-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 187 | Civil | RFI-ELE-CVL-F-C300-PSC-0187 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean concrete at P-18203A (2 nos) and P-16224 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-24 | 2025-03-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 188 | Civil | RFI-ELE-CVL-F-C300-PSC-0188 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of foundation afor P-18203A (2 nos), P-16214, P-16247 and P-16224 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-26 | 2025-03-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 189 | Civil | RFI-ELE-CVL-F-C300-PSC-0189 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean concrete for groundslab GL A-C/10-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-10 | 2025-04-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 190 | Civil | RFI-ELE-CVL-F-C300-PSC-0190 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean concrete for Pump foundation at Esstar Vission Compound | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-10 | 2025-04-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 191 | Civil | RFI-ELE-CVL-F-C300-PSC-0191 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of foudation for Pump foundation at Esstar Vission Compound | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-16 | 2025-04-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 192 | Civil | RFI-ELE-CVL-F-C300-PSC-0192 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean concrete GL B-C/1-7 for groundslab Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-16 | 2025-04-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 193 | Civil | RFI-ELE-CVL-F-C300-PSC-0193 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean concrete ACCU Foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-16 | 2025-04-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 194 | Civil | RFI-ELE-CVL-F-C300-PSC-0194 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of groundslab GL A-C/10-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-17 | 2025-04-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 195 | Civil | RFI-ELE-CVL-F-C300-PSC-0195 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of ACCU Foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-18 | 2025-04-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 196 | Civil | RFI-ELE-CVL-F-C300-PSC-0196 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of F9 Foundation at Man Refiner GL A-B/9 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-22 | 2025-04-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 197 | Civil | RFI-ELE-CVL-F-C300-PSC-0197 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon for non suspended slab HVAC Room Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-29 | 2025-05-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 198 | Civil | RFI-ELE-CVL-F-C300-PSC-0198 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon groundslab GL A-C/7-9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-03 | 2025-05-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 199 | Civil | RFI-ELE-CVL-F-C300-PSC-0199 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of ground slab GL A-C/7-9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-12 | 2025-05-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 200 | Civil | RFI-ELE-CVL-F-C300-PSC-0200 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean con ground slab and manholes at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-26 | 2025-05-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 201 | Civil | RFI-ELE-CVL-F-C300-PSC-0201 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean con CCW sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-26 | 2025-05-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 202 | Civil | RFI-ELE-CVL-F-C300-PSC-0202 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean con substation staircase landing | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-26 | 2025-05-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 203 | Civil | RFI-ELE-CVL-F-C300-PSC-0203 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of base sump pit CB4 and CB5 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-28 | 2025-05-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 204 | Civil | RFI-ELE-CVL-F-C300-PSC-0204 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of base foundation for North Staircase at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-28 | 2025-05-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 205 | Civil | RFI-ELE-CVL-F-C300-PSC-0205 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of base CCW S-18244 sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-29 | 2025-05-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 206 | Civil | RFI-ELE-CVL-F-C300-PSC-0206 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean con South side staircase bottom foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-30 | 2025-06-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 207 | Civil | RFI-ELE-CVL-F-C300-PSC-0207 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean con for base manholes MA3 and MA4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-30 | 2025-06-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 208 | Civil | RFI-ELE-CVL-F-C300-PSC-0208 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for North Staircase bottom plinth at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-03 | 2025-06-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 209 | Civil | RFI-ELE-CVL-F-C300-PSC-0209 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of sump pit CB4 and CB5 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-04 | 2025-06-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 210 | Civil | RFI-ELE-CVL-F-C300-PSC-0210 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of South side staircase bottom foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-04 | 2025-06-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 211 | Civil | RFI-ELE-CVL-F-C300-PSC-0211 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon groundslab GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-04 | 2025-06-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 212 | Civil | RFI-ELE-CVL-F-C300-PSC-0212 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of CCW S-18244 sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-05 | 2025-06-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 213 | Civil | RFI-ELE-CVL-F-C300-PSC-0213 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for South Staircase bottom plinth at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-05 | 2025-06-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 214 | Civil | RFI-ELE-CVL-F-C300-PSC-0214 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for North Staircase Fligth at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-06 | 2025-06-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 215 | Civil | RFI-ELE-CVL-F-C300-PSC-0215 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean con for base manholes MA3 and MA4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-06 | 2025-06-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 216 | Civil | RFI-ELE-CVL-F-C300-PSC-0216 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean con for trench for Transfomer at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-10 | 2025-06-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 217 | Civil | RFI-ELE-CVL-F-C300-PSC-0217 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for South Staircase Fligth at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-10 | 2025-06-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 218 | Civil | RFI-ELE-CVL-F-C300-PSC-0218 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean con for P-16211 A and B at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-10 | 2025-06-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 219 | Civil | RFI-ELE-CVL-F-C300-PSC-0219 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of GRE Pipe portion for Battery Room Slab at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-10 | 2025-06-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 220 | Civil | RFI-ELE-CVL-F-C300-PSC-0220 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of trench for Transfomer at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-11 | 2025-06-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 221 | Civil | RFI-ELE-CVL-F-C300-PSC-0221 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pump foundation P-16211 A and B at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-11 | 2025-06-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 222 | Civil | RFI-ELE-CVL-F-C300-PSC-0222 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon groundslab GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-11 | 2025-06-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 223 | Civil | RFI-ELE-CVL-F-C300-PSC-0223 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon for East IER Room RC Step Type 1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-16 | 2025-06-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 224 | Civil | RFI-ELE-CVL-F-C300-PSC-0224 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of trench for Transfomer A and B at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-16 | 2025-06-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 225 | Civil | RFI-ELE-CVL-F-C300-PSC-0225 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of foundation for East IER Room RC Step Type 1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-17 | 2025-06-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 226 | Civil | RFI-ELE-CVL-F-C300-PSC-0226 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal for F9 Foundation (2 nos) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-17 | 2025-06-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 227 | Civil | RFI-ELE-CVL-F-C300-PSC-0227 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of wall CCW S-18244 sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-20 | 2025-06-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 228 | Civil | RFI-ELE-CVL-F-C300-PSC-0228 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of East IER Room RC Step Type 1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-24 | 2025-06-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 229 | Civil | RFI-ELE-CVL-F-C300-PSC-0229 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon for North IER Room RC Step Type 2 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-24 | 2025-06-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 230 | Civil | RFI-ELE-CVL-F-C300-PSC-0230 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean con for trench for EDG at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-24 | 2025-06-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 231 | Civil | RFI-ELE-CVL-F-C300-PSC-0231 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon groundslab GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-24 | 2025-06-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 232 | Civil | RFI-ELE-CVL-F-C300-PSC-0232 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of wall and top CCW S-18244 sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-25 | 2025-06-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 233 | Civil | RFI-ELE-CVL-F-C300-PSC-0233 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of precast cable support block at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-25 | 2025-06-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 234 | Civil | RFI-ELE-CVL-F-C300-PSC-0234 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of Foundation for North IER Room RC Step Type 2 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-26 | 2025-06-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 235 | Civil | RFI-ELE-CVL-F-C300-PSC-0235 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of base for trench for EDG at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-26 | 2025-06-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 236 | Civil | RFI-ELE-CVL-F-C300-PSC-0236 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of wall for trench for EDG at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 237 | Civil | RFI-ELE-CVL-F-C300-PSC-0237 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of flight for North IER Room RC Step Type 2 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 238 | Civil | RFI-ELE-CVL-F-C300-PSC-0238 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon groundslab GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-01 | 2025-07-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 239 | Civil | RFI-ELE-CVL-F-C300-PSC-0239 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of groundslab GL A-C/1-4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-04 | 2025-07-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 240 | Civil | RFI-ELE-CVL-F-C300-PSC-0240 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon for cable tray support foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-08 | 2025-07-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 241 | Civil | RFI-ELE-CVL-F-C300-PSC-0241 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for cable tray support foundation F1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-10 | 2025-07-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 242 | Civil | RFI-ELE-CVL-F-C300-PSC-0242 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean con for Z-18213A foundation for Chilled Water Package | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-10 | 2025-07-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 243 | Civil | RFI-ELE-CVL-F-C300-PSC-0243 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pileplug for Z-18213A foundation for Chilled Water Package | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-10 | 2025-07-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 244 | Civil | RFI-ELE-CVL-F-C300-PSC-0244 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of groundslab GL A-C/4-8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-11 | 2025-07-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 245 | Civil | RFI-ELE-CVL-F-C300-PSC-0245 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean con for Z-18213A foundation for Chilled Water Package | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-14 | 2025-07-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 246 | Civil | RFI-ELE-CVL-F-C300-PSC-0246 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for cable tray support foundation pedestal F1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-14 | 2025-07-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 247 | Civil | RFI-ELE-CVL-F-C300-PSC-0247 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean con PC 3 (E-18206) Foundation at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-14 | 2025-07-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 248 | Civil | RFI-ELE-CVL-F-C300-PSC-0248 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pileplug PC 3 (E-18206) Foundation at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-14 | 2025-07-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 249 | Civil | RFI-ELE-CVL-F-C300-PSC-0249 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Z-18213A foundation for Chilled Water Package | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-16 | 2025-07-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 250 | Civil | RFI-ELE-CVL-F-C300-PSC-0250 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for PC 3 (E-18206) Foundation at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-17 | 2025-07-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 251 | Civil | RFI-ELE-CVL-F-C300-PSC-0251 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of roofslab GL A-C/1-3 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-18 | 2025-07-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 252 | Civil | RFI-ELE-CVL-F-C300-PSC-0252 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of 1st Floor GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-28 | 2025-07-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 253 | Civil | RFI-ELE-CVL-F-C300-PSC-0253 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of 2nd Floor GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-29 | 2025-07-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 254 | Civil | RFI-ELE-CVL-F-C300-PSC-0254 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of roofslab kerb GL A-C/1-3 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-29 | 2025-07-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 255 | Civil | RFI-ELE-CVL-F-C300-PSC-0255 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean concrete for TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-29 | 2025-07-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 256 | Civil | RFI-ELE-CVL-F-C300-PSC-0256 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pileplug for TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-29 | 2025-07-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 257 | Civil | RFI-ELE-CVL-F-C300-PSC-0257 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap for TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-02 | 2025-08-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 258 | Civil | RFI-ELE-CVL-F-C300-PSC-0258 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon for P-16232 (P7) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-02 | 2025-08-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 259 | Civil | RFI-ELE-CVL-F-C300-PSC-0259 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of 1st Mezzanine Floor GL A-B/3-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 260 | Civil | RFI-ELE-CVL-F-C300-PSC-0260 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean con for foundation T 19230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-06 | 2025-08-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 261 | Civil | RFI-ELE-CVL-F-C300-PSC-0261 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pileplug for foundation T 19230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-06 | 2025-08-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 262 | Civil | RFI-ELE-CVL-F-C300-PSC-0262 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal for TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-07 | 2025-08-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 263 | Civil | RFI-ELE-CVL-F-C300-PSC-0263 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation T 19230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-08 | 2025-08-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 264 | Civil | RFI-ELE-CVL-F-C300-PSC-0264 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pedestal T 19230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-11 | 2025-08-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 265 | Civil | RFI-ELE-CVL-F-C300-PSC-0265 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation melt tank pump P19221A/B at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-12 | 2025-08-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 266 | Civil | RFI-ELE-CVL-F-C300-PSC-0266 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of 2nd Floor pump foundation and kerb GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-15 | 2025-08-17 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 267 | Civil | RFI-ELE-CVL-F-C300-PSC-0267 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of 1st Mezzanine Floor GL A-B/3-7 pump foundation and kerb at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-16 | 2025-08-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 268 | Civil | RFI-ELE-CVL-F-C300-PSC-0268 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean concrete for new pump P19231 A/B and P19232 A/B at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-16 | 2025-08-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 269 | Civil | RFI-ELE-CVL-F-C300-PSC-0269 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean concrete for D16227 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-16 | 2025-08-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 270 | Civil | RFI-ELE-CVL-F-C300-PSC-0270 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of foundation for new pump P19231 A/B and P19232 A/B at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-19 | 2025-08-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 271 | Civil | RFI-ELE-CVL-F-C300-PSC-0271 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of foundation for D16227 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-19 | 2025-08-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 272 | Civil | RFI-ELE-CVL-F-C300-PSC-0272 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean con for compound slab TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 273 | Civil | RFI-ELE-CVL-F-C300-PSC-0273 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal for D16227 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-21 | 2025-08-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 274 | Civil | RFI-ELE-CVL-F-C300-PSC-0274 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of foundation for new pump P19231 B at Scubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-28 | 2025-08-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 275 | Civil | RFI-ELE-CVL-F-C300-PSC-0275 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of compound slab TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-30 | 2025-09-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 276 | Civil | RFI-ELE-CVL-F-C300-PSC-0276 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of cable tray support foundation near Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-30 | 2025-09-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 277 | Civil | RFI-ELE-CVL-F-C300-PSC-0277 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pump foundation for P-18204A/B at Demineralise Water Pump Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-06 | 2025-09-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 278 | Civil | RFI-ELE-CVL-F-C300-PSC-0278 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of cable tray support foundation near Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-06 | 2025-09-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 279 | Civil | RFI-ELE-CVL-F-C300-PSC-0279 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of foundation for P-16232 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-06 | 2025-09-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 280 | Civil | RFI-ELE-CVL-F-C300-PSC-0280 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of 1st Mezzanine Floor GL A-B/3-7 pump foundation and kerb at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-10 | 2025-09-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 281 | Civil | RFI-ELE-CVL-F-C300-PSC-0281 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon for MC10 Manhole | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-12 | 2025-09-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 282 | Civil | RFI-ELE-CVL-F-C300-PSC-0282 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for leancon at F5 and F6 at SP 10 Platform | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-12 | 2025-09-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 283 | Civil | RFI-ELE-CVL-F-C300-PSC-0283 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for stair foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-12 | 2025-09-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 284 | Civil | RFI-ELE-CVL-F-C300-PSC-0284 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation at F5 and F6 at SP 10 Platform | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-17 | 2025-09-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 285 | Civil | RFI-ELE-CVL-F-C300-PSC-0285 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for stair foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-17 | 2025-09-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 286 | Civil | RFI-ELE-CVL-F-C300-PSC-0286 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of 1st Mezzanine Floor GL A-B/3-7 pump foundation and kerb at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-19 | 2025-09-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 287 | Civil | RFI-ELE-CVL-F-C300-PSC-0287 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of 1st Floor Z-19206 A/B/C Fines Sifter at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-19 | 2025-09-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 288 | Civil | RFI-ELE-CVL-F-C300-PSC-0288 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of 2nd Floor slab GL A-B/6-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-19 | 2025-09-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 289 | Civil | RFI-ELE-CVL-F-C300-PSC-0289 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon for 2 nos F2, 1 nos F3 and 4 nos F5 foundation at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-19 | 2025-09-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 290 | Civil | RFI-ELE-CVL-F-C300-PSC-0290 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of Pileplug for 2 nos F2, 1 nos F3 and 4 nos F5 foundation at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-19 | 2025-09-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 291 | Civil | RFI-ELE-CVL-F-C300-PSC-0291 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of foundation chimney S-19232 at Roof Slab Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-19 | 2025-09-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 292 | Civil | RFI-ELE-CVL-F-C300-PSC-0292 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pilecap for 2 nos F2, 1 nos F3, 1 nos F7 and 4 nos F5 foundation at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-20 | 2025-09-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 293 | Civil | RFI-ELE-CVL-F-C300-PSC-0293 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pedestal at F5 and F6 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-22 | 2025-09-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 294 | Civil | RFI-ELE-CVL-F-C300-PSC-0294 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of 2nd Floor kerb GL A-B/6-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-22 | 2025-09-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 295 | Civil | RFI-ELE-CVL-F-C300-PSC-0295 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-22 | 2025-09-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 296 | Civil | RFI-ELE-CVL-F-C300-PSC-0296 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon for MA5, MA6 and MA7 Manholes around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-22 | 2025-09-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 297 | Civil | RFI-ELE-CVL-F-C300-PSC-0297 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pedestal 2 nos F5, 2 nos F1 and 2 nos F2 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-23 | 2025-09-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 298 | Civil | RFI-ELE-CVL-F-C300-PSC-0298 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for leancon 1 nos F7 and 1 nos F3 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-23 | 2025-09-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 299 | Civil | RFI-ELE-CVL-F-C300-PSC-0299 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for leancon apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-23 | 2025-09-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 300 | Civil | RFI-ELE-CVL-F-C300-PSC-0300 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-23 | 2025-09-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 301 | Civil | RFI-ELE-CVL-F-C300-PSC-0301 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-24 | 2025-09-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 302 | Civil | RFI-ELE-CVL-F-C300-PSC-0302 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap 1 nos F7 and 1 nos F3 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-24 | 2025-09-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 303 | Civil | RFI-ELE-CVL-F-C300-PSC-0303 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap 1 nos F1 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-24 | 2025-09-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 304 | Civil | RFI-ELE-CVL-F-C300-PSC-0304 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 305 | Civil | RFI-ELE-CVL-F-C300-PSC-0305 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pedestal 1 nos F7 and 1 nos F3 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 306 | Civil | RFI-ELE-CVL-F-C300-PSC-0306 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean con for D 18220 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-26 | 2025-09-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 307 | Civil | RFI-ELE-CVL-F-C300-PSC-0307 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pileplug for D 18220 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-26 | 2025-09-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 308 | Civil | RFI-ELE-CVL-F-C300-PSC-0308 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-26 | 2025-09-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 309 | Civil | RFI-ELE-CVL-F-C300-PSC-0309 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for precast manholes MA5, MA6, MA7 and MA8 for C300 at M-One Precast Yard | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-26 | 2025-09-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 310 | Civil | RFI-ELE-CVL-F-C300-PSC-0310 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pilecap for D 18220 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-27 | 2025-09-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 311 | Civil | RFI-ELE-CVL-F-C300-PSC-0311 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-27 | 2025-09-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 312 | Civil | RFI-ELE-CVL-F-C300-PSC-0312 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pedestal for D 18220 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-29 | 2025-10-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 313 | Civil | RFI-ELE-CVL-F-C300-PSC-0313 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for leancon for YM 18250 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-29 | 2025-10-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 314 | Civil | RFI-ELE-CVL-F-C300-PSC-0314 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of foundation for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-29 | 2025-10-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 315 | Civil | RFI-ELE-CVL-F-C300-PSC-0315 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of base MA5, MA6, MA7 and MC10 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-30 | 2025-10-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 316 | Civil | RFI-ELE-CVL-F-C300-PSC-0316 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation for YM 18250 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-30 | 2025-10-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 317 | Civil | RFI-ELE-CVL-F-C300-PSC-0317 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of wall MA5, MA6, MA7 and MC10 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-01 | 2025-01-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 318 | Civil | RFI-ELE-CVL-F-C300-PSC-0318 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of foundation for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-02 | 2025-10-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 319 | Civil | RFI-ELE-CVL-F-C300-PSC-0319 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-02 | 2025-10-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 320 | Civil | RFI-ELE-CVL-F-C300-PSC-0320 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean con for MC1 and MC6 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-06 | 2025-10-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 321 | Civil | RFI-ELE-CVL-F-C300-PSC-0321 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for leancon apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-07 | 2025-10-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 322 | Civil | RFI-ELE-CVL-F-C300-PSC-0322 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of top MA5, MA6, MA7 and MC10 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-07 | 2025-10-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 323 | Civil | RFI-ELE-CVL-F-C300-PSC-0323 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-08 | 2025-10-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 324 | Civil | RFI-ELE-CVL-F-C300-PSC-0324 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean con foundation for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-08 | 2025-10-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 325 | Civil | RFI-ELE-CVL-F-C300-PSC-0325 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for apron slab and ramp around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-09 | 2025-10-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 326 | Civil | RFI-ELE-CVL-F-C300-PSC-0326 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for apron slab around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-10 | 2025-10-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 327 | Civil | RFI-ELE-CVL-F-C300-PSC-0327 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of foundation for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-10 | 2025-10-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 328 | Civil | RFI-ELE-CVL-F-C300-PSC-0328 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for apron slab around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-11 | 2025-10-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 329 | Civil | RFI-ELE-CVL-F-C300-PSC-0329 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of foundation for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-11 | 2025-10-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 330 | Civil | RFI-ELE-CVL-F-C300-PSC-0330 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for apron slab around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-13 | 2025-10-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 331 | Civil | RFI-ELE-CVL-F-C300-PSC-0331 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon for slab at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-13 | 2025-10-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 332 | Civil | RFI-ELE-CVL-F-C300-PSC-0332 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon for cable C360 support foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-13 | 2025-10-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 333 | Civil | RFI-ELE-CVL-F-C300-PSC-0333 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of concrete for F1 Service Platform foundation at Demin Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-13 | 2025-10-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 334 | Civil | RFI-ELE-CVL-F-C300-PSC-0334 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon for MC7 Manholes | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-13 | 2025-10-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 335 | Civil | RFI-ELE-CVL-F-C300-PSC-0335 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of pedestal for F1 Service Platform foundation at Demin Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-14 | 2025-10-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 336 | Civil | RFI-ELE-CVL-F-C300-PSC-0336 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of foundation for cable C360 support foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-14 | 2025-10-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 337 | Civil | RFI-ELE-CVL-F-C300-PSC-0337 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of bund wall for TK16230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-17 | 2025-10-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 338 | Civil | RFI-ELE-CVL-F-C300-PSC-0338 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for apron slab and ramp around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-17 | 2025-10-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 339 | Civil | RFI-ELE-CVL-F-C300-PSC-0339 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for stair landing foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-17 | 2025-10-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 340 | Civil | RFI-ELE-CVL-F-C300-PSC-0340 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of base MC2, MC7 and wall MC1 and MC6 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-18 | 2025-10-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 341 | Civil | RFI-ELE-CVL-F-C300-PSC-0341 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of gully trap GT-1 at Substation C2015 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-18 | 2025-10-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 342 | Civil | RFI-ELE-CVL-F-C300-PSC-0342 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean con for Manholes MC4 and MC8 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-20 | 2025-10-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 343 | Civil | RFI-ELE-CVL-F-C300-PSC-0343 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for apron slab and ramp around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-20 | 2025-10-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 344 | Civil | RFI-ELE-CVL-F-C300-PSC-0344 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for precast manholes MA5, MA6, MA7 and MA8 for C300 at M-One Precast Yard | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-21 | 2025-10-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 345 | Civil | RFI-ELE-CVL-F-C300-PSC-0345 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of slab at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-24 | 2025-10-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 346 | Civil | RFI-ELE-CVL-F-C300-PSC-0346 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of kerb at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-03 | 2025-11-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 347 | Civil | RFI-ELE-CVL-F-C300-PSC-0347 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for apron slab and ramp around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-03 | 2025-11-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 348 | Civil | RFI-ELE-CVL-F-C300-PSC-0348 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pipe support foundation and D-18214 at Demin Water Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-10 | 2025-11-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 349 | Civil | RFI-ELE-CVL-F-C300-PSC-0349 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for RC step Type 3 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-10 | 2025-11-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 350 | Civil | RFI-ELE-CVL-F-C300-PSC-0350 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for leancon MC5 at Manholes C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-13 | 2025-11-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 351 | Civil | RFI-ELE-CVL-F-C300-PSC-0351 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for leancon rigid paving at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-14 | 2025-11-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 352 | Civil | RFI-ELE-CVL-F-C300-PSC-0352 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pipe support foundation at Demin Water Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-14 | 2025-11-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 353 | Civil | RFI-ELE-CVL-F-C300-PSC-0353 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for base for MC4 and MC5, wall for MC2 and MC7 at Manholes C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-14 | 2025-11-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 354 | Civil | RFI-ELE-CVL-F-C300-PSC-0354 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for rigid paving at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-19 | 2025-11-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 355 | Civil | RFI-ELE-CVL-F-C300-PSC-0355 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Wall for MC4 and MC5 Manholes C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-20 | 2025-11-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 356 | Civil | RFI-ELE-CVL-F-C300-PSC-0356 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for kerb paving at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-21 | 2025-11-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 357 | Civil | RFI-ELE-CVL-F-C300-PSC-0357 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection Service Platform SP-07 Foundation at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-26 | 2025-11-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 358 | Civil | RFI-ELE-CVL-F-C300-PSC-0358 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of lean concrete for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-29 | 2025-11-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 359 | Civil | RFI-ELE-CVL-F-C300-PSC-0359 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-29 | 2025-12-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 360 | Civil | RFI-ELE-CVL-F-C300-PSC-0360 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for slab opening at 1st Floor Briquetting Building (SI-085) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-01 | 2025-12-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 361 | Civil | RFI-ELE-CVL-F-C300-PSC-0361 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-03 | 2025-12-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 362 | Civil | RFI-ELE-CVL-F-C300-PSC-0362 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Manhole MC8 base at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-05 | 2025-12-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 363 | Civil | RFI-ELE-CVL-F-C300-PSC-0363 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean con pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-08 | 2025-12-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 364 | Civil | RFI-ELE-CVL-F-C300-PSC-0364 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-09 | 2025-12-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 365 | Civil | RFI-ELE-CVL-F-C300-PSC-0365 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Manhole MC8 wall at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-09 | 2025-12-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 366 | Civil | RFI-ELE-CVL-F-C300-PSC-0366 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean con pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-11 | 2025-12-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 367 | Civil | RFI-ELE-CVL-F-C300-PSC-0367 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-16 | 2025-12-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 368 | Civil | RFI-ELE-CVL-F-C300-PSC-0368 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean con pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-19 | 2025-12-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 368 | Civil | RFI-ELE-CVL-F-C300-PSC-0369 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-23 | 2025-12-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 370 | Civil | RFI-ELE-CVL-F-C300-PSC-0370 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-27 | 2025-12-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 371 | Civil | RFI-ELE-CVL-F-C300-PSC-0371 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean con for TK16230 stairs foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-27 | 2025-12-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 372 | Civil | RFI-ELE-CVL-F-C300-PSC-0372 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for foundation for TK16230 stairs foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-27 | 2025-12-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 373 | Civil | RFI-ELE-CVL-F-C300-PSC-0373 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon for apron slab GL A/ 5-10 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-27 | 2025-12-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 374 | Civil | RFI-ELE-CVL-F-C300-PSC-0374 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for apron slab GL A/ 5-10 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-30 | 2026-01-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 375 | Civil | RFI-ELE-CVL-F-C300-PSC-0375 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pavement kerb at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-30 | 2026-01-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 376 | Civil | RFI-ELE-CVL-F-C300-PSC-0376 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean concrete for manholes MA8 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-03 | 2026-01-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 377 | Civil | RFI-ELE-CVL-F-C300-PSC-0377 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon for apron slab at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-06 | 2026-01-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 378 | Civil | RFI-ELE-CVL-F-C300-PSC-0378 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for apron slab at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-09 | 2026-01-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 379 | Civil | RFI-ELE-CVL-F-C300-PSC-0379 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for stairs TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-12 | 2026-01-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 380 | Civil | RFI-ELE-CVL-F-C300-PSC-0380 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection of leancon for apron slab at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-12 | 2026-01-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 381 | Civil | RFI-ELE-CVL-F-C300-PSC-0381 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for base concrete for manholes MA8 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-12 | 2026-01-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 382 | Civil | RFI-ELE-CVL-F-C300-PSC-0382 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for air vent support for MC4, MC5, MC6, MC7, MA6 and MA7 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-12 | 2026-01-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 383 | Civil | RFI-ELE-CVL-F-C300-PSC-0383 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Wall and Top concrete for manholes MA8 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-19 | 1900-01-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 384 | Civil | RFI-ELE-CVL-F-C300-PSC-0384 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Stairs foundation for Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-19 | 1900-01-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 385 | Civil | RFI-ELE-CVL-F-C300-PSC-0385 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for manhole cover MC1, MC4, MC5, MC6 and MC7 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-19 | 1900-01-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 386 | Civil | RFI-ELE-CVL-F-C300-PSC-0386 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean concrete for ramp at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-19 | 1900-01-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 387 | Civil | RFI-ELE-CVL-F-C300-PSC-0387 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for concrete for apron at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-19 | 2026-01-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 388 | Civil | RFI-ELE-CVL-F-C300-PSC-0388 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for concrete heavy duty paving near Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-19 | 2026-01-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 389 | Civil | RFI-ELE-CVL-F-C300-PSC-0389 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Stairs foundation for Demin Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-22 | 2026-01-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 390 | Civil | RFI-ELE-CVL-F-C300-PSC-0390 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-22 | 2026-01-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 391 | Civil | RFI-ELE-CVL-F-C300-PSC-0391 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for ramp at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-24 | 2026-01-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 392 | Civil | RFI-ELE-CVL-F-C300-PSC-0392 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for airvent pipe support for MC2, MC10 and MC8 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-24 | 2026-01-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 393 | Civil | RFI-ELE-CVL-F-C300-PSC-0393 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for leancon ramp at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-26 | 2026-01-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 394 | Civil | RFI-ELE-CVL-F-C300-PSC-0394 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for leancon pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-26 | 2026-01-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 395 | Civil | RFI-ELE-CVL-F-C300-PSC-0395 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for Heavy Duty Pavement at Man Refiner (South) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-27 | 2026-01-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 396 | Civil | RFI-ELE-CVL-F-C300-PSC-0396 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for manhole cover MC1, MC2, MC4, MC5, MC8 and MA8 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-28 | 2026-01-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 397 | Civil | RFI-ELE-CVL-F-C300-PSC-0397 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for airvent pipe support MA5. MA6 and MA7 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-30 | 2026-02-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 398 | Civil | RFI-ELE-CVL-F-C300-PSC-0398 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for rigid pavement and PL07 pipe support at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-30 | 2026-02-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 399 | Civil | RFI-ELE-CVL-F-C300-PSC-0399 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for slab around MC10 at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-30 | 2026-02-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 400 | Civil | RFI-ELE-CVL-F-C300-PSC-0400 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for lean con for ramp at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-30 | 2026-02-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 401 | Civil | RFI-ELE-CVL-F-C300-PSC-0401 | External | Eleco | Civil Work | N/A | RC Work | Post-pour concrete | Inspection for ramp at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-30 | 2026-02-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing

## 09.RFI_ASB
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-30
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-CVL-F-C300-ASB-0001 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for as built survey for pilecap Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-27 | 2024-09-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 2 | Civil | RFI-ELE-CVL-F-C300-ASB-0002 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for as built survey for stump Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-27 | 2024-09-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 3 | Civil | RFI-ELE-CVL-F-C300-ASB-0003 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for as built survey for groundbeam leancon Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-04 | 2024-10-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 4 | Civil | RFI-ELE-CVL-F-C300-ASB-0004 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for as built survey for groundbeam Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-19 | 2024-10-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 5 | Civil | RFI-ELE-CVL-F-C300-ASB-0005 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for as built survey for groundbeam Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-22 | 2024-10-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 6 | Civil | RFI-ELE-CVL-F-C300-ASB-0006 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for as built survey for groundslab leancon Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-15 | 2024-11-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 7 | Civil | RFI-ELE-CVL-F-C300-ASB-0007 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for as built survey for foundation leancon MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-15 | 2024-11-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 8 | Civil | RFI-ELE-CVL-F-C300-ASB-0008 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for as built survey foundation PC16 MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-16 | 2024-11-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 9 | Civil | RFI-ELE-CVL-F-C300-ASB-0009 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for as built survey for foundation leancon MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-18 | 2024-11-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 10 | Civil | RFI-ELE-CVL-F-C300-ASB-0010 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for as built survey foundation MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-23 | 2024-11-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 11 | Civil | RFI-ELE-CVL-F-C300-ASB-0011 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for as built survey for foundation leancon MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-23 | 2024-11-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 12 | Civil | RFI-ELE-CVL-F-C300-ASB-0012 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for as built survey for foundation leancon for Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-23 | 2024-11-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 13 | Civil | RFI-ELE-CVL-F-C300-ASB-0013 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for as built survey foundation PC16 top MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-29 | 2024-11-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 14 | Civil | RFI-ELE-CVL-F-C300-ASB-0014 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for as built survey pilecap MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-29 | 2024-12-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 15 | Civil | RFI-ELE-CVL-F-C300-ASB-0015 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for as built survey for groundslab Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-29 | 2024-12-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 16 | Civil | RFI-ELE-CVL-F-C300-ASB-0016 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for as built survey for groundbeam Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-05 | 2024-12-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 17 | Civil | RFI-ELE-CVL-F-C300-ASB-0017 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for asbuilt lean concrete at AHU-01A and B and HVAC control panel Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-07 | 2024-12-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 18 | Civil | RFI-ELE-CVL-F-C300-ASB-0018 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for asbuilt lean concrete at PC4c and PC4 foundation at Man refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-07 | 2024-12-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 19 | Civil | RFI-ELE-CVL-F-C300-ASB-0019 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for as built survey for column G/level to 1st level GL A-D/2-3 Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-09 | 2024-12-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 20 | Civil | RFI-ELE-CVL-F-C300-ASB-0020 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for Pilecap Man Refiner Foundation PC4c and PC4d | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-10 | 2024-12-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 21 | Civil | RFI-ELE-CVL-F-C300-ASB-0021 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for as built survey pilecap PC4c topside, PC4d topside, PC8 MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-12 | 2024-12-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 22 | Civil | RFI-ELE-CVL-F-C300-ASB-0022 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for EDG Foundation at Substation C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-13 | 2024-12-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 23 | Civil | RFI-ELE-CVL-F-C300-ASB-0023 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for column G/level to 1st level GL A-D/4-5a Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-13 | 2024-12-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 24 | Civil | RFI-ELE-CVL-F-C300-ASB-0024 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for column G/level to 1st level GL A-D/1x, GL C-D/1, GL A/5-7, GL B/7 and GL B1/5 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-17 | 2024-12-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 25 | Civil | RFI-ELE-CVL-F-C300-ASB-0025 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for lean concrete at PC6a, PC2b, 3 nos of PC2 and PC8a | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-17 | 2024-12-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 26 | Civil | RFI-ELE-CVL-F-C300-ASB-0026 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for column G/level to 1st level GL B1-D / 6-8, GL C1/5A and GL D/5 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-19 | 2024-12-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 27 | Civil | RFI-ELE-CVL-F-C300-ASB-0027 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for lean concrete at PC2b, PC2 and PC9 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-19 | 2024-12-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 28 | Civil | RFI-ELE-CVL-F-C300-ASB-0028 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for Pilecap Man Refiner Foundation PC6a, PC8a, PC2 (2 unit) and PC2b | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-20 | 2024-12-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 29 | Civil | RFI-ELE-CVL-F-C300-ASB-0029 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for Leancon Man Refiner Foundation PC6b, PC2 and PC2a | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-20 | 2024-12-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 30 | Civil | RFI-ELE-CVL-F-C300-ASB-0030 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for Pilecap Transformer MCC-A and MCC-B foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-20 | 2024-12-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 31 | Civil | RFI-ELE-CVL-F-C300-ASB-0031 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for Pilecap PC9, PC2b and PC2 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-21 | 2024-12-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 32 | Civil | RFI-ELE-CVL-F-C300-ASB-0032 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for 2nd Cast PC8a at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-23 | 2024-12-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 33 | Civil | RFI-ELE-CVL-F-C300-ASB-0033 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for leancon Man Refiner Foundation PC4 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-23 | 2024-12-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 34 | Civil | RFI-ELE-CVL-F-C300-ASB-0034 | External | Eleco | Civil work | N/A | Survey work | As Built | Inspection for pedestal C1 PC 11, GL A/3, for Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-23 | 2024-12-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 35 | Civil | RFI-ELE-CVL-F-C300-ASB-0035 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pilecap PC4 and PC6b at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 36 | Civil | RFI-ELE-CVL-F-C300-ASB-0036 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for leancon PC2, PC2a, PC2b/C1 and PC24 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 37 | Civil | RFI-ELE-CVL-F-C300-ASB-0037 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for Pedestal C1 for PC11, PC8, PC6a and PC2b | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 38 | Civil | RFI-ELE-CVL-F-C300-ASB-0038 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for leancon for TK-18203 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-25 | 2024-12-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 39 | Civil | RFI-ELE-CVL-F-C300-ASB-0039 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pedestal for pilecap PC6c, PC6, PC5, PC12, PC8a, PC9, PC2 and PC2a | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-26 | 2024-12-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 40 | Civil | RFI-ELE-CVL-F-C300-ASB-0040 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pedestal for pilecap PC11, PC2 (2 nos), PC1 and PC6b | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-27 | 2024-12-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 41 | Civil | RFI-ELE-CVL-F-C300-ASB-0041 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pilecap PC2,PC2a, PC2b at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-27 | 2024-12-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 42 | Civil | RFI-ELE-CVL-F-C300-ASB-0042 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for leancon pilecap PC2a at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-27 | 2024-12-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 43 | Civil | RFI-ELE-CVL-F-C300-ASB-0043 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pilecap PC5/C1 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-28 | 2024-12-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 44 | Civil | RFI-ELE-CVL-F-C300-ASB-0044 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pedestal for pilecap PC2/PS, PC2a/PS, PC2b/PS at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-28 | 2024-12-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 45 | Civil | RFI-ELE-CVL-F-C300-ASB-0045 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for lean con for pilecap PC 8b and PC4/C1 (2 nos) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-28 | 2024-12-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 46 | Civil | RFI-ELE-CVL-F-C300-ASB-0046 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pedestal for pilecap PC5 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-30 | 2025-01-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 47 | Civil | RFI-ELE-CVL-F-C300-ASB-0047 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for leancon for pilecap PC6d/C1 , PC12/C1 and PC8b | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-31 | 2025-01-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 48 | Civil | RFI-ELE-CVL-F-C300-ASB-0048 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pilecap PC4/C1 2 nos at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-31 | 2025-01-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 49 | Civil | RFI-ELE-CVL-F-C300-ASB-0049 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection pedestal PC2a/C1 GL d/7 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-01 | 2025-01-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 50 | Civil | RFI-ELE-CVL-F-C300-ASB-0050 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection pilecap PC24 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-02 | 2025-01-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 51 | Civil | RFI-ELE-CVL-F-C300-ASB-0051 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection pedestal PC2b/C1 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-02 | 2025-01-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 52 | Civil | RFI-ELE-CVL-F-C300-ASB-0052 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection leancon for PC6d/C1 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-02 | 2025-01-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 53 | Civil | RFI-ELE-CVL-F-C300-ASB-0053 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection pilecap for PC5, PC12/C1 GL E/5, and PC8b at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-03 | 2025-01-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 54 | Civil | RFI-ELE-CVL-F-C300-ASB-0054 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection pilecap for AHU-01 A and 01B, HVAC Control Panel Foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-03 | 2025-01-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 55 | Civil | RFI-ELE-CVL-F-C300-ASB-0055 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pilecap PC8b,PC12/C1,PC6d/C1 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-05 | 2025-01-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 56 | Civil | RFI-ELE-CVL-F-C300-ASB-0056 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pedestal PC4/C1 (2nos) Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-05 | 2025-01-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 57 | Civil | RFI-ELE-CVL-F-C300-ASB-0057 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection leancon for pilecap GL A-A2 - 27' -29' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-06 | 2025-01-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 58 | Civil | RFI-ELE-CVL-F-C300-ASB-0058 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pedestal PC12, PC 6d, PC8b and PC24 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-07 | 2025-01-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 59 | Civil | RFI-ELE-CVL-F-C300-ASB-0059 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of foundation TK 18203 Demin Water Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-08 | 2025-01-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 60 | Civil | RFI-ELE-CVL-F-C300-ASB-0060 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pedestal PC24 (saddle) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-09 | 2025-01-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 61 | Civil | RFI-ELE-CVL-F-C300-ASB-0061 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for foundation leancon Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-10 | 2025-01-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 62 | Civil | RFI-ELE-CVL-F-C300-ASB-0062 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for foundation leancon Briquetting Building-PC22,PC6 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-15 | 2025-01-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 63 | Civil | RFI-ELE-CVL-F-C300-ASB-0063 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for slab and beam 1st floor for Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-16 | 2025-01-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 64 | Civil | RFI-ELE-CVL-F-C300-ASB-0064 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pilecap GL A-A2 - 27' -29' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-16 | 2025-01-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 65 | Civil | RFI-ELE-CVL-F-C300-ASB-0065 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pedestal PC24 (free saddle) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-17 | 2025-01-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 66 | Civil | RFI-ELE-CVL-F-C300-ASB-0066 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of column GL A-D/1X at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-22 | 2025-01-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 67 | Civil | RFI-ELE-CVL-F-C300-ASB-0067 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pilecap GL A1' -A2'/ 28' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-22 | 2025-01-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 68 | Civil | RFI-ELE-CVL-F-C300-ASB-0068 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pedestal GL A1' -A2'/ 29' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-22 | 2025-01-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 69 | Civil | RFI-ELE-CVL-F-C300-ASB-0069 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pilecap PC6 and PC5a at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-23 | 2025-01-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 70 | Civil | RFI-ELE-CVL-F-C300-ASB-0070 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon for pilecap D-2806 at Esstar Vision Compound | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-25 | 2025-01-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 71 | Civil | RFI-ELE-CVL-F-C300-ASB-0071 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pilecap D-2806 at Esstar Vision Compound | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-25 | 2025-01-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 72 | Civil | RFI-ELE-CVL-F-C300-ASB-0072 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pilecap GL A-C/1-4 for Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-27 | 2025-01-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 73 | Civil | RFI-ELE-CVL-F-C300-ASB-0073 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of column GL A-D/4-8 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-31 | 2025-02-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 74 | Civil | RFI-ELE-CVL-F-C300-ASB-0074 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon for pilecap PC6/C1 and PC8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-31 | 2025-02-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 75 | Civil | RFI-ELE-CVL-F-C300-ASB-0075 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pilecap PC6/C1, PC6c/C1 and PC6a/C1 GL A-B/3-4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-01 | 2025-02-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 76 | Civil | RFI-ELE-CVL-F-C300-ASB-0076 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of stump column at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-04 | 2025-02-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 77 | Civil | RFI-ELE-CVL-F-C300-ASB-0077 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pilecap GL A1' -A2'/ 27-29 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 78 | Civil | RFI-ELE-CVL-F-C300-ASB-0078 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pedestal GL A1' -A2'/27- 29' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 79 | Civil | RFI-ELE-CVL-F-C300-ASB-0079 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of column 1st-RL GL B-D/2-3 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 80 | Civil | RFI-ELE-CVL-F-C300-ASB-0080 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of stump column at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-05 | 2025-02-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Cancelled
| 81 | Civil | RFI-ELE-CVL-F-C300-ASB-0081 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of stump column at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-06 | 2024-02-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 82 | Civil | RFI-ELE-CVL-F-C300-ASB-0082 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pilecap at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-06 | 2024-02-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 83 | Civil | RFI-ELE-CVL-F-C300-ASB-0083 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pilecap at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-07 | 2025-02-09 | 9:00 | H | W | N/A | R | Hanis | C300 | Accepted
| 84 | Civil | RFI-ELE-CVL-F-C300-ASB-0084 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon for pilecap at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-07 | 2025-02-09 | 9:00 | H | W | N/A | R | Hanis | C300 | Accepted
| 85 | Civil | RFI-ELE-CVL-F-C300-ASB-0085 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of raft foundation Battery Room at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-07 | 2025-02-09 | 9:00 | H | W | N/A | R | Hanis | C300 | Accepted
| 86 | Civil | RFI-ELE-CVL-F-C300-ASB-0086 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of column 1st-RL at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0004 | B | 2024-02-08 | 2024-02-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 87 | Civil | RFI-ELE-CVL-F-C300-ASB-0087 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon for pilecap at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-11 | 2024-02-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 88 | Civil | RFI-ELE-CVL-F-C300-ASB-0088 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pilecap at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-11 | 2024-02-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 89 | Civil | RFI-ELE-CVL-F-C300-ASB-0089 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of stump column at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-11 | 2024-02-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 90 | Civil | RFI-ELE-CVL-F-C300-ASB-0090 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pilecap GL A1' -A2'/ 27-29 at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-11 | 2024-02-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 91 | Civil | RFI-ELE-CVL-F-C300-ASB-0091 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pedestal GL A1' -A2'/27- 29' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-13 | 2024-02-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 92 | Civil | RFI-ELE-CVL-F-C300-ASB-0092 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of column 1st-RL at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-11 | 2024-02-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 93 | Civil | RFI-ELE-CVL-F-C300-ASB-0093 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pilecap PC3/C2 GL C/9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 94 | Civil | RFI-ELE-CVL-F-C300-ASB-0094 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon PC7a/C1 and PC6b/C1 GL B/5-6 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 95 | Civil | RFI-ELE-CVL-F-C300-ASB-0095 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon Groundbeam GL A/1-2, A-C/1 and C/1-4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 96 | Civil | RFI-ELE-CVL-F-C300-ASB-0096 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pedestal PC4/C2 GL C/8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 97 | Civil | RFI-ELE-CVL-F-C300-ASB-0097 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pilecap Z-19208A Weighing Machines and Silo Foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-19 | 2025-02-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 98 | Civil | RFI-ELE-CVL-F-C300-ASB-0098 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pilecap PC6b and PC6d GL B/6-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-19 | 2025-02-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 99 | Civil | RFI-ELE-CVL-F-C300-ASB-0099 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pilecap PC7a/C1 GL B/5 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-20 | 2025-02-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 100 | Civil | RFI-ELE-CVL-F-C300-ASB-0100 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon PC3/C2 GL C/10 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-20 | 2025-02-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 101 | Civil | RFI-ELE-CVL-F-C300-ASB-0101 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pedestal PC3/C2 GL C/9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-20 | 2025-02-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 102 | Civil | RFI-ELE-CVL-F-C300-ASB-0102 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of roof slab and beam at GL A-D/4-8 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-22 | 2025-02-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 103 | Civil | RFI-ELE-CVL-F-C300-ASB-0103 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of roof beam at GL A-D/1x-1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-22 | 2025-02-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 104 | Civil | RFI-ELE-CVL-F-C300-ASB-0104 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of ground beam Gl A-C/ 1-5 for Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-25 | 2025-02-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 105 | Civil | RFI-ELE-CVL-F-C300-ASB-0105 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pilecap PC3/C2 GL C/10 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-25 | 2025-02-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 106 | Civil | RFI-ELE-CVL-F-C300-ASB-0106 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean con for PC4/C2 (2 nos) GL C/11-12, Z-19208B, Z-19240 Equipment foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-25 | 2025-02-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 107 | Civil | RFI-ELE-CVL-F-C300-ASB-0107 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of foundation pilecap Z-19208B & D-19220 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-27 | 2025-02-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 108 | Civil | RFI-ELE-CVL-F-C300-ASB-0108 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pilecap for PC4/C2 (2 nos) GL C/11-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-27 | 2025-03-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 109 | Civil | RFI-ELE-CVL-F-C300-ASB-0109 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pilecap for PC4/C2 GL A/12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-28 | 2025-03-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 110 | Civil | RFI-ELE-CVL-F-C300-ASB-0110 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean con for PC6/C1 and PC7/C1 GL A/5-6, and Z-19208C at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-28 | 2025-03-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 111 | Civil | RFI-ELE-CVL-F-C300-ASB-0111 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of roof slab GL A-D/1-4 for Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-03 | 2025-03-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 112 | Civil | RFI-ELE-CVL-F-C300-ASB-0112 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pile cap PC6/C1 GL A/4-5 and Z-19208C at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-04 | 2025-03-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 113 | Civil | RFI-ELE-CVL-F-C300-ASB-0113 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of groundbeam GL C/4-9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-04 | 2025-03-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 114 | Civil | RFI-ELE-CVL-F-C300-ASB-0114 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean con PC3/C2 (2nos) GL A/9-10 and PC4/C2 (2nos) GL A/11 and B/12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-04 | 2025-03-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 115 | Civil | RFI-ELE-CVL-F-C300-ASB-0115 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pedestal PC5a, PC6a, PC6, PC7a, PC6b, and PC6d GL B/2-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-04 | 2025-03-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 116 | Civil | RFI-ELE-CVL-F-C300-ASB-0116 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean con P-18201A and P-18201B Pump Foundation at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-05 | 2025-03-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 117 | Civil | RFI-ELE-CVL-F-C300-ASB-0117 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pilecap PC4/C2 (2 nos), PC3/C2 (2 nos) GL A/8-11 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 118 | Civil | RFI-ELE-CVL-F-C300-ASB-0118 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of Pedestal 2nd cast PC5/C1 GL B/1, PC6/C1 (3 nos), PC6a/C1 (2 nos), PC7/C1 (2 nos) and PC4/C2 GL A/1-8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 119 | Civil | RFI-ELE-CVL-F-C300-ASB-0119 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of groundbeam GL A/1-4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 120 | Civil | RFI-ELE-CVL-F-C300-ASB-0120 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pedestal PC3/C2 and PC4/C2 (2nos) GL C/10-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 121 | Civil | RFI-ELE-CVL-F-C300-ASB-0121 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pilecap PC4/C2 GL B/12, PC7/C1 GL A/6 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 122 | Civil | RFI-ELE-CVL-F-C300-ASB-0122 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon PC4/C2 GL A/8, PC3/C2 GL A/9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-06 | 2025-03-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 123 | Civil | RFI-ELE-CVL-F-C300-ASB-0123 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for Pump Foundation P-18201A and P-18201B at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-07 | 2025-03-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 124 | Civil | RFI-ELE-CVL-F-C300-ASB-0124 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for lean concrete and pile plug Stretch Hood Device and ground beam GL A 4-6 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 125 | Civil | RFI-ELE-CVL-F-C300-ASB-0125 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pilecap foundation Stretch Hood Device at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 126 | Civil | RFI-ELE-CVL-F-C300-ASB-0126 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pilecap foundation D-19220 Foundation Melt Tank at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 127 | Civil | RFI-ELE-CVL-F-C300-ASB-0127 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of groundbeam GL A/4-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 128 | Civil | RFI-ELE-CVL-F-C300-ASB-0128 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of 2nd cast pedestal PC6/C1 (2nos) and PC6a/C1 GL A/1-4 Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 129 | Civil | RFI-ELE-CVL-F-C300-ASB-0129 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pedestal PC4/C2 (4nos) and PC3/C2 (3nos) GL A-B/8-12 Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 130 | Civil | RFI-ELE-CVL-F-C300-ASB-0130 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of cast fascia GL A-D/ 4-8 at roof floor Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-08 | 2025-03-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 131 | Civil | RFI-ELE-CVL-F-C300-ASB-0131 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of Lean concrete for ground beam GL A-C/8-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 132 | Civil | RFI-ELE-CVL-F-C300-ASB-0132 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of Lean concrete for PC7/C1 GL A/7 and foundation Stretch Hood Device GL A/8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 133 | Civil | RFI-ELE-CVL-F-C300-ASB-0133 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pedestal for PC6a/C1 and PC6/C1 GL A/4-5 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-10 | 2025-03-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 134 | Civil | RFI-ELE-CVL-F-C300-ASB-0134 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of groundbeam for GL A-C/8 -12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-13 | 2025-03-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 135 | Civil | RFI-ELE-CVL-F-C300-ASB-0135 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pilecap for foundation Stretch Hood Device GL A/8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-13 | 2025-03-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 136 | Civil | RFI-ELE-CVL-F-C300-ASB-0136 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pedestal for PC3/C2 (2 nos) and PC4/C2 (3 nos) GL B-C/9-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-14 | 2025-03-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 137 | Civil | RFI-ELE-CVL-F-C300-ASB-0137 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pedestal foundation D-19220 Foundation Melt Tank at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-14 | 2025-03-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 138 | Civil | RFI-ELE-CVL-F-C300-ASB-0138 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of Lean concrete for PC7/C1 GL A/7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-14 | 2025-03-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 139 | Civil | RFI-ELE-CVL-F-C300-ASB-0139 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of cast fascia GL A-D/ 4at roof floor Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-15 | 2025-03-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 140 | Civil | RFI-ELE-CVL-F-C300-ASB-0140 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pedestal for PC3/C2 (2 nos) and PC4/C2 (3 nos) GL A-B/9-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-15 | 2025-03-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 141 | Civil | RFI-ELE-CVL-F-C300-ASB-0141 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pilecap for PC7/C1 GL A/7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-17 | 2025-03-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 142 | Civil | RFI-ELE-CVL-F-C300-ASB-0142 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pedestal for PC7/C1 GL A/7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-18 | 2025-03-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 143 | Civil | RFI-ELE-CVL-F-C300-ASB-0143 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon groundbeam for GL A/6-8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-18 | 2025-03-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 144 | Civil | RFI-ELE-CVL-F-C300-ASB-0144 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of groundbeam for GL A/6-8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-20 | 2025-03-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 145 | Civil | RFI-ELE-CVL-F-C300-ASB-0145 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean concrete at P-16214 and P-16247 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-22 | 2025-03-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 146 | Civil | RFI-ELE-CVL-F-C300-ASB-0146 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean concrete at P-18203A (2 nos) and P-16224 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-24 | 2025-03-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 147 | Civil | RFI-ELE-CVL-F-C300-ASB-0147 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of foundation afor P-18203A (2 nos), P-16214, P-16247 and P-16224 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-26 | 2025-03-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 148 | Civil | RFI-ELE-CVL-F-C300-ASB-0148 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean concrete for groundslab GL A-C/10-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-10 | 2025-04-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 149 | Civil | RFI-ELE-CVL-F-C300-ASB-0149 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean concrete for Pump foundation at Esstar Vission Compound | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-10 | 2025-04-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 150 | Civil | RFI-ELE-CVL-F-C300-ASB-0150 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of foudation for Pump foundation at Esstar Vission Compound | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-16 | 2025-04-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 151 | Civil | RFI-ELE-CVL-F-C300-ASB-0151 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean concrete GL B-C/1-7 for groundslab Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-16 | 2025-04-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 152 | Civil | RFI-ELE-CVL-F-C300-ASB-0152 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean concrete ACCU Foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-16 | 2025-04-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 153 | Civil | RFI-ELE-CVL-F-C300-ASB-0153 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of groundslab GL A-C/10-12 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-17 | 2025-04-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 154 | Civil | RFI-ELE-CVL-F-C300-ASB-0154 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of ACCU Foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-18 | 2025-04-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 155 | Civil | RFI-ELE-CVL-F-C300-ASB-0155 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of F9 Foundation at Man Refiner GL A-B/9 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-22 | 2025-04-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 156 | Civil | RFI-ELE-CVL-F-C300-ASB-0156 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of for non suspended slab HVAC Room Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-29 | 2025-05-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 157 | Civil | RFI-ELE-CVL-F-C300-ASB-0157 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon groundslab GL A-C/7-9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-03 | 2025-05-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 158 | Civil | RFI-ELE-CVL-F-C300-ASB-0158 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of ground slab GL A-C/7-9 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-12 | 2025-05-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 159 | Civil | RFI-ELE-CVL-F-C300-ASB-0159 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean con ground slab and manholes at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-26 | 2025-05-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 160 | Civil | RFI-ELE-CVL-F-C300-ASB-0160 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean con CCW sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-26 | 2025-05-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 161 | Civil | RFI-ELE-CVL-F-C300-ASB-0161 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean con substation staircase landing | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-26 | 2025-05-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 162 | Civil | RFI-ELE-CVL-F-C300-ASB-0162 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of base sump pit CB4 and CB5 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-28 | 2025-05-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 163 | Civil | RFI-ELE-CVL-F-C300-ASB-0163 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of base foundation for North Staircase at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-28 | 2025-05-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 164 | Civil | RFI-ELE-CVL-F-C300-ASB-0164 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of base CCW S-18244 sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-29 | 2025-05-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 165 | Civil | RFI-ELE-CVL-F-C300-ASB-0165 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean con South side staircase bottom foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-30 | 2025-06-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 166 | Civil | RFI-ELE-CVL-F-C300-ASB-0166 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean con for base manholes MA3 and MA4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-30 | 2025-06-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 167 | Civil | RFI-ELE-CVL-F-C300-ASB-0167 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for North Staircase bottom plinth at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-03 | 2025-06-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 168 | Civil | RFI-ELE-CVL-F-C300-ASB-0168 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of sump pit CB4 and CB5 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-04 | 2025-06-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 169 | Civil | RFI-ELE-CVL-F-C300-ASB-0169 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of South side staircase bottom foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-04 | 2025-06-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 170 | Civil | RFI-ELE-CVL-F-C300-ASB-0170 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon groundslab GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-04 | 2025-06-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 171 | Civil | RFI-ELE-CVL-F-C300-ASB-0171 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of CCW S-18244 sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-05 | 2025-06-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 172 | Civil | RFI-ELE-CVL-F-C300-ASB-0172 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for South Staircase bottom plinth at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-05 | 2025-06-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 173 | Civil | RFI-ELE-CVL-F-C300-ASB-0173 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for North Staircase Fligth at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-06 | 2025-06-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 174 | Civil | RFI-ELE-CVL-F-C300-ASB-0174 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean con for base manholes MA3 and MA4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-06 | 2025-06-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 175 | Civil | RFI-ELE-CVL-F-C300-ASB-0175 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean con for trench for Transfomer at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-10 | 2025-06-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 176 | Civil | RFI-ELE-CVL-F-C300-ASB-0176 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for South Staircase Fligth at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-10 | 2025-06-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 177 | Civil | RFI-ELE-CVL-F-C300-ASB-0177 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean con for P-16211 A and B at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-10 | 2025-06-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 178 | Civil | RFI-ELE-CVL-F-C300-ASB-0178 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of GRE Pipe portion for Battery Room Slab at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-10 | 2025-06-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 179 | Civil | RFI-ELE-CVL-F-C300-ASB-0179 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of trench for Transfomer at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-11 | 2025-06-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 180 | Civil | RFI-ELE-CVL-F-C300-ASB-0180 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pump foundation P-16211 A and B at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-11 | 2025-06-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 181 | Civil | RFI-ELE-CVL-F-C300-ASB-0181 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon groundslab GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-11 | 2025-06-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 182 | Civil | RFI-ELE-CVL-F-C300-ASB-0182 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon for East IER Room RC Step Type 1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-16 | 2025-06-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 183 | Civil | RFI-ELE-CVL-F-C300-ASB-0183 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of trench for Transfomer A and B at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-16 | 2025-06-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 184 | Civil | RFI-ELE-CVL-F-C300-ASB-0184 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of foundation for East IER Room RC Step Type 1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-17 | 2025-06-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 185 | Civil | RFI-ELE-CVL-F-C300-ASB-0185 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pedestal for F9 Foundation (2 nos) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-17 | 2025-06-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 186 | Civil | RFI-ELE-CVL-F-C300-ASB-0186 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of wall CCW S-18244 sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-20 | 2025-06-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 187 | Civil | RFI-ELE-CVL-F-C300-ASB-0187 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of East IER Room RC Step Type 1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-24 | 2025-06-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 188 | Civil | RFI-ELE-CVL-F-C300-ASB-0188 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon for North IER Room RC Step Type 2 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-24 | 2025-06-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 189 | Civil | RFI-ELE-CVL-F-C300-ASB-0189 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean con for trench for EDG at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-24 | 2025-06-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 190 | Civil | RFI-ELE-CVL-F-C300-ASB-0190 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon groundslab GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-24 | 2025-06-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 191 | Civil | RFI-ELE-CVL-F-C300-ASB-0191 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of wall and top CCW S-18244 sump pit at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-25 | 2025-06-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 192 | Civil | RFI-ELE-CVL-F-C300-ASB-0192 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of precast cable support block at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-25 | 2025-06-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Cancelled
| 193 | Civil | RFI-ELE-CVL-F-C300-ASB-0193 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of Foundation for North IER Room RC Step Type 2 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-26 | 2025-06-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 194 | Civil | RFI-ELE-CVL-F-C300-ASB-0194 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of base for trench for EDG at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-26 | 2025-06-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 195 | Civil | RFI-ELE-CVL-F-C300-ASB-0195 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of wall for trench for EDG at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 196 | Civil | RFI-ELE-CVL-F-C300-ASB-0196 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of flight for North IER Room RC Step Type 2 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-06-30 | 2025-07-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 197 | Civil | RFI-ELE-CVL-F-C300-ASB-0197 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon groundslab GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-01 | 2025-07-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 239 | Civil | RFI-ELE-CVL-F-C300-ASB-0198 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of groundslab GL A-C/1-4 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-04 | 2025-07-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 240 | Civil | RFI-ELE-CVL-F-C300-ASB-0199 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon for cable tray support foundation at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-08 | 2025-07-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 241 | Civil | RFI-ELE-CVL-F-C300-ASB-0200 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for cable tray support foundation F1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-10 | 2025-07-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 242 | Civil | RFI-ELE-CVL-F-C300-ASB-0201 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for lean con for Z-18213A foundation for Chilled Water Package | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-10 | 2025-07-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 239 | Civil | RFI-ELE-CVL-F-C300-ASB-0202 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of groundslab GL A-C/4-8 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-11 | 2025-07-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 245 | Civil | RFI-ELE-CVL-F-C300-ASB-0203 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for lean con for Z-18213A foundation for Chilled Water Package | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-14 | 2025-07-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 246 | Civil | RFI-ELE-CVL-F-C300-ASB-0204 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for cable tray support foundation pedestal F1 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-14 | 2025-07-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 247 | Civil | RFI-ELE-CVL-F-C300-ASB-0205 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for lean con PC 3 (E-18206) Foundation at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-14 | 2025-07-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 249 | Civil | RFI-ELE-CVL-F-C300-ASB-0206 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for Z-18213A foundation for Chilled Water Package | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-16 | 2025-07-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 250 | Civil | RFI-ELE-CVL-F-C300-ASB-0207 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for PC 3 (E-18206) Foundation at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-17 | 2025-07-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 251 | Civil | RFI-ELE-CVL-F-C300-ASB-0208 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of roofslab GL A-C/1-3 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-18 | 2025-07-20 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 252 | Civil | RFI-ELE-CVL-F-C300-ASB-0209 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of 1st Floor GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-28 | 2025-07-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 253 | Civil | RFI-ELE-CVL-F-C300-ASB-0210 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of 2nd Floor GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-29 | 2025-07-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 254 | Civil | RFI-ELE-CVL-F-C300-ASB-0211 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of roofslab kerb GL A-C/1-3 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-29 | 2025-07-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 255 | Civil | RFI-ELE-CVL-F-C300-ASB-0212 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean concrete for TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-07-29 | 2025-07-31 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 257 | Civil | RFI-ELE-CVL-F-C300-ASB-0213 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pilecap for TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-02 | 2025-08-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 258 | Civil | RFI-ELE-CVL-F-C300-ASB-0214 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon for P-16232 (P7) at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-02 | 2025-08-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 259 | Civil | RFI-ELE-CVL-F-C300-ASB-0215 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of 1st Mezzanine Floor GL A-B/3-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-04 | 2025-08-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 260 | Civil | RFI-ELE-CVL-F-C300-ASB-0216 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean con for foundation T 19230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-06 | 2025-08-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 262 | Civil | RFI-ELE-CVL-F-C300-ASB-0217 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pedestal for TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-07 | 2025-08-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 260 | Civil | RFI-ELE-CVL-F-C300-ASB-0218 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for foundation T 19230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-08 | 2025-08-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 264 | Civil | RFI-ELE-CVL-F-C300-ASB-0219 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pedestal T 19230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-11 | 2025-08-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 265 | Civil | RFI-ELE-CVL-F-C300-ASB-0220 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for foundation melt tank pump P19221A/B at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-12 | 2025-08-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 266 | Civil | RFI-ELE-CVL-F-C300-ASB-0221 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of 2nd Floor pump foundation and kerb GL A-C/1-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-15 | 2025-08-17 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 266 | Civil | RFI-ELE-CVL-F-C300-ASB-0222 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of 1st Mezzanine Floor GL A-B/3-7 pump foundation and kerb at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-16 | 2025-08-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 268 | Civil | RFI-ELE-CVL-F-C300-ASB-0223 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean concrete for new pump P19231 A/B and P19232 A/B at Scubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-16 | 2025-08-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 269 | Civil | RFI-ELE-CVL-F-C300-ASB-0224 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean concrete for D16227 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-16 | 2025-08-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 270 | Civil | RFI-ELE-CVL-F-C300-ASB-0225 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of foundation for new pump P19231 A/B and P19232 A/B at Scubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-19 | 2025-08-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 271 | Civil | RFI-ELE-CVL-F-C300-ASB-0226 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of foundation for D16227 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-19 | 2025-08-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 272 | Civil | RFI-ELE-CVL-F-C300-ASB-0227 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean con for compound slab TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-20 | 2025-08-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 273 | Civil | RFI-ELE-CVL-F-C300-ASB-0228 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pedestal for D16227 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-21 | 2025-08-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 274 | Civil | RFI-ELE-CVL-F-C300-ASB-0229 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of foundation for new pump P19231 B at Scubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-28 | 2025-08-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 275 | Civil | RFI-ELE-CVL-F-C300-ASB-0230 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of compound slab TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-30 | 2025-09-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 276 | Civil | RFI-ELE-CVL-F-C300-ASB-0231 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of cable tray support foundation near Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-08-30 | 2025-09-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 277 | Civil | RFI-ELE-CVL-F-C300-ASB-0232 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pump foundation for P-18204A/B at Demineralise Water Pump Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-06 | 2025-09-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 278 | Civil | RFI-ELE-CVL-F-C300-ASB-0233 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of cable tray support foundation near Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-06 | 2025-09-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 279 | Civil | RFI-ELE-CVL-F-C300-ASB-0234 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of foundation for P-16232 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-06 | 2025-09-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 280 | Civil | RFI-ELE-CVL-F-C300-ASB-0235 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of 1st Mezzanine Floor GL A-B/3-7 pump foundation and kerb at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-10 | 2025-09-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 281 | Civil | RFI-ELE-CVL-F-C300-ASB-0236 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon for MC10 Manhole | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-12 | 2025-09-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 282 | Civil | RFI-ELE-CVL-F-C300-ASB-0237 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for leancon at F5 and F6 at SP 10 Platform | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-12 | 2025-09-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 283 | Civil | RFI-ELE-CVL-F-C300-ASB-0238 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for stair foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-12 | 2025-09-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 284 | Civil | RFI-ELE-CVL-F-C300-ASB-0239 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for foundation at F5 and F6 at SP 10 Platform | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-17 | 2025-09-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 285 | Civil | RFI-ELE-CVL-F-C300-ASB-0240 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for stair foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-17 | 2025-09-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 286 | Civil | RFI-ELE-CVL-F-C300-ASB-0241 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of 1st Mezzanine Floor GL A-B/3-7 pump foundation and kerb at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-19 | 2025-09-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 287 | Civil | RFI-ELE-CVL-F-C300-ASB-0242 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of 1st Floor Z-19206 A/B/C Fines Sifter at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-19 | 2025-09-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 288 | Civil | RFI-ELE-CVL-F-C300-ASB-0243 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of 2nd Floor slab GL A-B/6-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-19 | 2025-09-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 289 | Civil | RFI-ELE-CVL-F-C300-ASB-0244 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon for 2 nos F2, 1 nos F3 and 4 nos F5 foundation at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-19 | 2025-09-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 291 | Civil | RFI-ELE-CVL-F-C300-ASB-0245 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of foundation chimney S-19232 at Roof Slab Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-19 | 2025-09-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 292 | Civil | RFI-ELE-CVL-F-C300-ASB-0246 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pilecap for 2 nos F2, 1 nos F3, 1 nos F7 and 4 nos F5 foundation at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-20 | 2025-09-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 293 | Civil | RFI-ELE-CVL-F-C300-ASB-0247 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pedestal at F5 and F6 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-22 | 2025-09-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 294 | Civil | RFI-ELE-CVL-F-C300-ASB-0248 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of 2nd Floor kerb GL A-B/6-7 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-22 | 2025-09-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 295 | Civil | RFI-ELE-CVL-F-C300-ASB-0249 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-22 | 2025-09-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 296 | Civil | RFI-ELE-CVL-F-C300-ASB-0250 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon for MA5, MA6 and MA7 Manholes around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-22 | 2025-09-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 297 | Civil | RFI-ELE-CVL-F-C300-ASB-0251 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pedestal 2 nos F5, 2 nos F1 and 2 nos F2 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-23 | 2025-09-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 298 | Civil | RFI-ELE-CVL-F-C300-ASB-0252 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for leancon 1 nos F7 and 1 nos F3 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-23 | 2025-09-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 299 | Civil | RFI-ELE-CVL-F-C300-ASB-0253 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for leancon apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-23 | 2025-09-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 300 | Civil | RFI-ELE-CVL-F-C300-ASB-0254 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-23 | 2025-09-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 301 | Civil | RFI-ELE-CVL-F-C300-ASB-0255 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-24 | 2025-09-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 302 | Civil | RFI-ELE-CVL-F-C300-ASB-0256 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pilecap 1 nos F7 and 1 nos F3 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-24 | 2025-09-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 303 | Civil | RFI-ELE-CVL-F-C300-ASB-0257 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pilecap 1 nos F1 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-24 | 2025-09-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 304 | Civil | RFI-ELE-CVL-F-C300-ASB-0258 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 305 | Civil | RFI-ELE-CVL-F-C300-ASB-0259 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pedestal 1 nos F7 and 1 nos F3 foundation at SP 10 Platform Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-25 | 2025-09-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 306 | Civil | RFI-ELE-CVL-F-C300-ASB-0260 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for lean con for D 18220 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-26 | 2025-09-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 308 | Civil | RFI-ELE-CVL-F-C300-ASB-0261 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-26 | 2025-09-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 310 | Civil | RFI-ELE-CVL-F-C300-ASB-0262 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pilecap for D 18220 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-27 | 2025-09-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 311 | Civil | RFI-ELE-CVL-F-C300-ASB-0263 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-27 | 2025-09-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 312 | Civil | RFI-ELE-CVL-F-C300-ASB-0264 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pedestal for D 18220 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-29 | 2025-10-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 313 | Civil | RFI-ELE-CVL-F-C300-ASB-0265 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for leancon for YM 18250 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-29 | 2025-10-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 314 | Civil | RFI-ELE-CVL-F-C300-ASB-0266 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of foundation for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-29 | 2025-10-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 315 | Civil | RFI-ELE-CVL-F-C300-ASB-0267 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of base MA5, MA6, MA7 and MC10 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-30 | 2025-10-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 316 | Civil | RFI-ELE-CVL-F-C300-ASB-0268 | RFI-ELE-CVL-F-C300-ASB-0269 | RFI-ELE-CVL-F-C300-ASB-0270 | RFI-ELE-CVL-F-C300-ASB-0271 | RFI-ELE-CVL-F-C300-ASB-0272 | RC Work | As Built | Inspection for foundation for YM 18250 Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-30 | 2025-10-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 317 | Civil | RFI-ELE-CVL-F-C300-ASB-0269 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of wall MA5, MA6, MA7 and MC10 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-01 | 2025-01-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 318 | Civil | RFI-ELE-CVL-F-C300-ASB-0270 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of foundation for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-02 | 2025-10-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 319 | Civil | RFI-ELE-CVL-F-C300-ASB-0271 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-02 | 2025-10-04 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 320 | Civil | RFI-ELE-CVL-F-C300-ASB-0272 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for lean con for MC1 and MC6 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-06 | 2025-10-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 321 | Civil | RFI-ELE-CVL-F-C300-ASB-0273 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for leancon apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-07 | 2025-10-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 322 | Civil | RFI-ELE-CVL-F-C300-ASB-0274 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of top MA5, MA6, MA7 and MC10 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-07 | 2025-10-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 323 | Civil | RFI-ELE-CVL-F-C300-ASB-0275 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for apron slab for Inergen Cylinder Base around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-08 | 2025-10-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 324 | Civil | RFI-ELE-CVL-F-C300-ASB-0276 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean con foundation for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-08 | 2025-10-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 325 | Civil | RFI-ELE-CVL-F-C300-ASB-0277 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for apron slab and ramp around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-09 | 2025-10-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 326 | Civil | RFI-ELE-CVL-F-C300-ASB-0278 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for apron slab around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-10 | 2025-10-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 327 | Civil | RFI-ELE-CVL-F-C300-ASB-0279 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of foundation for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-10 | 2025-10-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 328 | Civil | RFI-ELE-CVL-F-C300-ASB-0280 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for apron slab around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-11 | 2025-10-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 329 | Civil | RFI-ELE-CVL-F-C300-ASB-0281 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of foundation for vertical cable ladder support around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-11 | 2025-10-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 330 | Civil | RFI-ELE-CVL-F-C300-ASB-0282 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for apron slab around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-13 | 2025-10-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 331 | Civil | RFI-ELE-CVL-F-C300-ASB-0283 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon for slab at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-13 | 2025-10-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 332 | Civil | RFI-ELE-CVL-F-C300-ASB-0284 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon for cable C360 support foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-13 | 2025-10-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 333 | Civil | RFI-ELE-CVL-F-C300-ASB-0285 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of concrete for F1 Service Platform foundation at Demin Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-13 | 2025-10-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 334 | Civil | RFI-ELE-CVL-F-C300-ASB-0286 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon for MC7 Manholes | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-13 | 2025-10-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 335 | Civil | RFI-ELE-CVL-F-C300-ASB-0287 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of pedestal for F1 Service Platform foundation at Demin Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-14 | 2025-10-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 336 | Civil | RFI-ELE-CVL-F-C300-ASB-0288 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of foundation for cable C360 support foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-14 | 2025-10-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 337 | Civil | RFI-ELE-CVL-F-C300-ASB-0289 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of bund wall for TK16230 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-17 | 2025-10-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 338 | Civil | RFI-ELE-CVL-F-C300-ASB-0290 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for apron slab and ramp around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-17 | 2025-10-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 339 | Civil | RFI-ELE-CVL-F-C300-ASB-0291 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for stair landing foundation at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-17 | 2025-10-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 340 | Civil | RFI-ELE-CVL-F-C300-ASB-0292 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of base MC2, MC7 and wall MC1 and MC6 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-18 | 2025-10-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 341 | Civil | RFI-ELE-CVL-F-C300-ASB-0293 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of gully trap GT-1 at Substation C2015 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-18 | 2025-10-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 342 | Civil | RFI-ELE-CVL-F-C300-ASB-0294 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean con for Manholes MC4 and MC8 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-20 | 2025-10-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 343 | Civil | RFI-ELE-CVL-F-C300-ASB-0295 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for apron slab and ramp around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-20 | 2025-10-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 345 | Civil | RFI-ELE-CVL-F-C300-ASB-0296 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of slab at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-24 | 2025-10-26 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 346 | Civil | RFI-ELE-CVL-F-C300-ASB-0297 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of kerb at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-03 | 2025-11-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 347 | Civil | RFI-ELE-CVL-F-C300-ASB-0298 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for apron slab and ramp around Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-03 | 2025-11-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 348 | Civil | RFI-ELE-CVL-F-C300-ASB-0299 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pipe support foundation and D-18214 at Demin Water Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-10 | 2025-11-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 349 | Civil | RFI-ELE-CVL-F-C300-ASB-0300 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for RC step Type 3 at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-10 | 2025-11-12 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 350 | Civil | RFI-ELE-CVL-F-C300-ASB-0301 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for leancon MC5 at Manholes C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-13 | 2025-11-15 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 351 | Civil | RFI-ELE-CVL-F-C300-ASB-0302 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for leancon rigid paving at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-14 | 2025-11-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 352 | Civil | RFI-ELE-CVL-F-C300-ASB-0303 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pipe support foundation at Demin Water Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-14 | 2025-11-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 353 | Civil | RFI-ELE-CVL-F-C300-ASB-0304 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for base for MC4 and MC5, wall for MC2 and MC7 at Manholes C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-14 | 2025-11-16 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 354 | Civil | RFI-ELE-CVL-F-C300-ASB-0305 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for rigid paving at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-19 | 2025-11-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 355 | Civil | RFI-ELE-CVL-F-C300-ASB-0306 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for Wall for MC4 and MC5 Manholes C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-20 | 2025-11-22 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 354 | Civil | RFI-ELE-CVL-F-C300-ASB-0307 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for kerb paving at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-21 | 2025-11-23 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 357 | Civil | RFI-ELE-CVL-F-C300-ASB-0308 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection Service Platform SP-07 Foundation at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-26 | 2025-11-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 358 | Civil | RFI-ELE-CVL-F-C300-ASB-0309 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of lean concrete for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-29 | 2025-11-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 359 | Civil | RFI-ELE-CVL-F-C300-ASB-0310 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-11-29 | 2025-12-02 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 360 | Civil | RFI-ELE-CVL-F-C300-ASB-0311 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for slab opening at 1st Floor Briquetting Building (SI-085) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-01 | 2025-12-03 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 361 | Civil | RFI-ELE-CVL-F-C300-ASB-0312 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-03 | 2025-12-05 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 362 | Civil | RFI-ELE-CVL-F-C300-ASB-0313 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for Manhole MC8 base at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-05 | 2025-12-07 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 363 | Civil | RFI-ELE-CVL-F-C300-ASB-0314 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for lean con pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-08 | 2025-12-10 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 364 | Civil | RFI-ELE-CVL-F-C300-ASB-0315 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-09 | 2025-12-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 365 | Civil | RFI-ELE-CVL-F-C300-ASB-0316 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for Manhole MC8 wall at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-09 | 2025-12-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 366 | Civil | RFI-ELE-CVL-F-C300-ASB-0317 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for lean con pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-11 | 2025-12-13 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 367 | Civil | RFI-ELE-CVL-F-C300-ASB-0318 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-16 | 2025-12-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 368 | Civil | RFI-ELE-CVL-F-C300-ASB-0319 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for lean con pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-19 | 2025-12-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 368 | Civil | RFI-ELE-CVL-F-C300-ASB-0320 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-23 | 2025-12-25 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 370 | Civil | RFI-ELE-CVL-F-C300-ASB-0321 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-27 | 2025-12-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 371 | Civil | RFI-ELE-CVL-F-C300-ASB-0322 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for lean con for TK16230 stairs foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-27 | 2025-12-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 372 | Civil | RFI-ELE-CVL-F-C300-ASB-0323 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for foundation for TK16230 stairs foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-27 | 2025-12-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 373 | Civil | RFI-ELE-CVL-F-C300-ASB-0324 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon for apron slab GL A/ 5-10 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-27 | 2025-12-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 374 | Civil | RFI-ELE-CVL-F-C300-ASB-0325 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for apron slab GL A/ 5-10 at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-30 | 2026-01-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 375 | Civil | RFI-ELE-CVL-F-C300-ASB-0326 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pavement kerb at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-12-30 | 2026-01-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted
| 376 | Civil | RFI-ELE-CVL-F-C300-ASB-0327 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for lean concrete for manholes MA8 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-03 | 2026-01-06 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 377 | Civil | RFI-ELE-CVL-F-C300-ASB-0328 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon for apron slab at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-06 | 2026-01-08 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 378 | Civil | RFI-ELE-CVL-F-C300-ASB-0329 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for apron slab at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-09 | 2026-01-11 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 379 | Civil | RFI-ELE-CVL-F-C300-ASB-0330 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for stairs TK16230 at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-12 | 2026-01-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 380 | Civil | RFI-ELE-CVL-F-C300-ASB-0331 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection of leancon for apron slab at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-12 | 2026-01-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 381 | Civil | RFI-ELE-CVL-F-C300-ASB-0332 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for base concrete for manholes MA8 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-12 | 2026-01-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 382 | Civil | RFI-ELE-CVL-F-C300-ASB-0333 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for air vent support for MC4, MC5, MC6, MC7, MA6 and MA7 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-12 | 2026-01-14 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 383 | Civil | RFI-ELE-CVL-F-C300-ASB-0334 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for Wall and Top concrete for manholes MA8 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-19 | 1900-01-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 384 | Civil | RFI-ELE-CVL-F-C300-ASB-0335 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for Stairs foundation for Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-19 | 1900-01-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 385 | Civil | RFI-ELE-CVL-F-C300-ASB-0336 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for manhole cover MC1, MC4, MC5, MC6 and MC7 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-19 | 1900-01-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 386 | Civil | RFI-ELE-CVL-F-C300-ASB-0337 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for lean concrete for ramp at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-19 | 1900-01-19 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 387 | Civil | RFI-ELE-CVL-F-C300-ASB-0338 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for concrete for apron at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-19 | 2026-01-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 389 | Civil | RFI-ELE-CVL-F-C300-ASB-0339 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for concrete heavy duty paving near Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-19 | 2026-01-21 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 389 | Civil | RFI-ELE-CVL-F-C300-ASB-0340 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for Stairs foundation for Demin Tank | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-22 | 2026-01-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 390 | Civil | RFI-ELE-CVL-F-C300-ASB-0341 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-22 | 2026-01-24 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 391 | Civil | RFI-ELE-CVL-F-C300-ASB-0342 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for ramp at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-24 | 2026-01-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 392 | Civil | RFI-ELE-CVL-F-C300-ASB-0343 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for airvent pipe support for MC2, MC10 and MC8 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-24 | 2026-01-27 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 393 | Civil | RFI-ELE-CVL-F-C300-ASB-0344 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for leancon ramp at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-26 | 2026-01-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 394 | Civil | RFI-ELE-CVL-F-C300-ASB-0345 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for leancon pavement at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-26 | 2026-01-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 395 | Civil | RFI-ELE-CVL-F-C300-ASB-0346 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for Heavy Duty Pavement at Man Refiner (South) | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-27 | 2026-01-29 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 396 | Civil | RFI-ELE-CVL-F-C300-ASB-0347 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for manhole cover MC1, MC2, MC4, MC5, MC8 and MA8 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-28 | 2026-01-30 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 397 | Civil | RFI-ELE-CVL-F-C300-ASB-0348 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for airvent pipe support MA5. MA6 and MA7 at C300 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-30 | 2026-02-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 398 | Civil | RFI-ELE-CVL-F-C300-ASB-0349 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for rigid pavement and PL07 pipe support at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-30 | 2026-02-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 399 | Civil | RFI-ELE-CVL-F-C300-ASB-0350 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for slab around MC10 at Scrubber Unit | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-30 | 2026-02-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 400 | Civil | RFI-ELE-CVL-F-C300-ASB-0351 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for lean con for ramp at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-30 | 2026-02-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing
| 401 | Civil | RFI-ELE-CVL-F-C300-ASB-0352 | External | Eleco | Civil Work | N/A | RC Work | As Built | Inspection for ramp at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2026-01-30 | 2026-02-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Ongoing

## 10.RFI_CUB
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-30
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
-
-
-
-
-
-
-
-
-
-
-
-
-
-

## 11.RFI_BFL
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-30
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-CVL-F-C300-BFL-0001 | External | Eleco | Civil Work | N/A | RC Work | Backfilling | Inspection for foundation backfilling for Sub-station C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-07 | 2024-09-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 2 | Civil | RFI-ELE-CVL-F-C300-BFL-0002 | External | Eleco | Civil Work | N/A | RC Work | Backfilling | Inspection for foundation backfilling for Sub-station C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-28 | 2024-09-28 | 4.00 PM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 3 | Civil | RFI-ELE-CVL-F-C300-BFL-0003 | External | Eleco | Civil Work | N/A | RC Work | Backfilling | Inspection for backfilling work at Sub-station C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-01 | 2024-11-01 | 11.30 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 4 | Civil | RFI-ELE-CVL-F-C300-BFL-0004 | External | Eleco | Civil Work | N/A | RC Work | Backfilling | Inspection for backfilling work at Sub-station C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-07 | 2024-11-08 | 11.30 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 5 | Civil | RFI-ELE-CVL-F-C300-BFL-0005 | External | Eleco | Civil Work | N/A | RC Work | Backfilling | Inspection for backfilling work PC16 Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-20 | 2024-11-21 | 11.30 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 6 | Civil | RFI-ELE-CVL-F-C300-BFL-0006 | External | Eleco | Civil Work | N/A | RC Work | Backfilling | Inspection for backfilling work for foundation Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-11-27 | 2024-11-28 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 7 | Civil | RFI-ELE-CVL-F-C300-BFL-0007 | External | Eleco | Civil Work | N/A | RC Work | Backfilling | Inspection for backfilling work for foundation GL A-D/1-4 Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-01-31 | 2025-02-01 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 8 | Civil | RFI-ELE-CVL-F-C300-BFL-0008 | External | Eleco | Civil Work | N/A | RC Work | Backfilling | Inspection for backfilling work for foundation GL A2' - A / 27' - 29' at New Piperack | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-18 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 9 | Civil | RFI-ELE-CVL-F-C300-BFL-0009 | External | Eleco | Civil Work | N/A | RC Work | Backfilling | Inspection for hardcore backfilling work for Ground Slab at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-08 | 2025-04-09 | 9.00 AM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 10 | Civil | RFI-ELE-CVL-F-C300-BFL-0010 | External | Eleco | Civil Work | N/A | RC Work | Backfilling | Inspection for 40 mm gravel backfilling work for cable cellar room at Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-10 | 2025-04-10 | 4.00 PM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 11 | Civil | RFI-ELE-CVL-F-C300-BFL-0011 | External | Eleco | Civil Work | N/A | RC Work | Backfilling | Inspection for backfilling work at Man Refiner Pump Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-23 | 2025-04-24 | 4.00 PM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 12 | Civil | RFI-ELE-CVL-F-C300-BFL-0012 | External | Eleco | Civil Work | N/A | RC Work | Backfilling | Inspection for backfilling work at Scubber Unit Area | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-08 | 2025-10-09 | 4.00 PM | H | W | N/A | R | Hanis | C300 | Accepted | -
| 13 | Civil | RFI-ELE-CVL-F-C300-BFL-0013 | External | Eleco | Civil Work | N/A | RC Work | Backfilling | Inspection for backfilling work at Briquetting Building Area | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-10-08 | 2025-10-09 | 4.00 PM | H | W | N/A | R | Hanis | C300 | Accepted | -
-

## 12.RFI_FDT
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-30
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-CVL-F-C300-FDT-0001 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Field Density Test for 1st,2nd and 3rd layer of foundation backfilling at Substation C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-09 | 2024-09-10 | 9.00 AM | H | W | I | W/R | Hanis | C300 | Accepted | -
| 2 | Civil | RFI-ELE-CVL-F-C300-FDT-0002 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test for foundation backfilling at stump level at Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-17 | 2024-09-19 | 9.00 AM | H | W | I | W/R | Hanis | C300 | Accepted | -
| 3 | Civil | RFI-ELE-CVL-F-C300-FDT-0003 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Field Density Test for 1st,2nd and 3rd layer of foundation backfilling at Substation C-2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-09-28 | 2024-10-01 | 9.00 AM | H | W | I | W/R | Hanis | C300 | Accepted | -
| 4 | Civil | RFI-ELE-CVL-F-C300-FDT-0004 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test for backfilling at groundfloor level at Substation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-10-31 | 2024-11-01 | 9.00 AM | H | W | I | W/R | Hanis | C300 | Accepted | -
| 5 | Civil | RFI-ELE-CVL-F-C300-FDT-0005 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test for compacted hardcore backfilling at AHU-01A and B and HVAC Control Panel Foundation | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-07 | 2024-12-09 | 9.00 AM | H | W | I | W/R | Hanis | C300 | Cancelled | -
| 6 | Civil | RFI-ELE-CVL-F-C300-FDT-0006 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test for at MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-12-14 | 2024-12-16 | 9.00 AM | H | W | I | W/R | Hanis | C300 | Cancelled | -
| 7 | Civil | RFI-ELE-CVL-F-C300-FDT-0007 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test at MAN Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-06 | 2024-02-07 | 9.00 AM | H | W | I | W/R | Hanis | C300 | Accepted | -
| 8 | Civil | RFI-ELE-CVL-F-C300-FDT-0008 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2024-02-06 | 2024-02-07 | 9.00 AM | H | W | I | W/R | Hanis | C300 | Accepted | -
| 9 | Civil | RFI-ELE-CVL-F-C300-FDT-0009 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-02-17 | 2025-02-18 | 9.00 AM | H | W | I | W/R | Hanis | C300 | Accepted | -
| 10 | Civil | RFI-ELE-CVL-F-C300-FDT-0010 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-03-15 | 2025-03-17 | 9.00 AM | H | W | I | W/R | Hanis | C300 | Accepted | -
| 11 | Civil | RFI-ELE-CVL-F-C300-FDT-0011 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for hardcore Field Density Test at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-10 | 2025-04-11 | 9.00 AM | H | W | I | W/R | Hanis | C300 | Accepted | -
| 12 | Civil | RFI-ELE-CVL-F-C300-FDT-0012 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for hardcore Field Density Test at Man Refiner | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-14 | 2025-04-15 | 9.00 AM | H | W | I | W/R | Hanis | C300 | Accepted | -
| 13 | Civil | RFI-ELE-CVL-F-C300-FDT-0013 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test at Pump Foundation Esstar Vission Compund | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-04-14 | 2025-04-15 | 9.00 AM | H | W | I | W/R | Hanis | C300 | Accepted | -
| 14 | Civil | RFI-ELE-CVL-F-C300-FDT-0014 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for hardcore Field Density Test at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-03 | 2025-05-05 | 9.00 AM | H | W | I | W/R | Hanis | C300 | Accepted | -
| 15 | Civil | RFI-ELE-CVL-F-C300-FDT-0015 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for hardcore Field Density Test at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-05-16 | 2025-05-17 | 9.00 AM | H | W | I | W/R | Hanis | C300 | Accepted | -
| 16 | Civil | RFI-ELE-CVL-F-C300-FDT-0016 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for hardcore Field Density Test at Briquetting Building | BASIL-01-EXE-HQC-000-QAC-ITP-0004 | B | 2025-05-24 | 2025-05-26 | 9.00 AM | H | W | I | W/R | Hanis | C300 | Accepted
| 17 | Civil | RFI-ELE-CVL-F-C300-FDT-0017 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for hardcore Field Density Test at apron Substation C2105 | BASIL-01-EXE-HQC-000-QAC-ITP-0004 | B | 2025-10-06 | 2025-10-07 | 9.00 AM | H | W | I | W/R | Hanis | C300 | Accepted
| 18 | Civil | RFI-ELE-CVL-F-C300-FDT-0018 | External | Eleco | Civil Work | N/A | Earthwork | Field Density Test | Inspection for Field Density Test at apron Scubber Unit Area | BASIL-01-EXE-HQC-000-QAC-ITP-0004 | B | 2025-10-08 | 2025-10-09 | 9.00 AM | H | W | I | W/R | Hanis | C300 | Accepted

## 13.RFI_FNL
|  |  |  | BASIL PROJECT Request for Inspection (RFI)-Summary | [16 empty] | Job No : 000000047080
[21 empty] | Request On : |  | 2026-01-30
System No | No. | Discipline | RFI No. | Type of RFI | Subcon Name | Main Scope | System No | Type Of Inspection | Work Item | Detail Item | ITP Reference No | ITP | Date of RFI | Date Of Insp. | Time Of Insp. | Inspection Points |  |  |  | PIC | Location | Inspection Status | Reason | Status | Trasmittal Out | Date Issue | Trasmittal In | Date Received (PCMTBE) | RFI Scan Status | Date Scan | Volume No. | File Name
[16 empty] | Sub-Con. | Contractor | 3rd Party | COMPANY
| 1 | Civil | RFI-ELE-CVL-F-C300-FNL-0001 | External | Eleco | Civil Work | N/A | Final Inspection | Final Inspection | Final Inspection for Substation C2105 civil structure with punchlists | BASIL-01-EXE-HQC-000-QAC-ITP-0003 | B | 2025-09-05 | 2025-09-06 | 9.00 AM | H | W | I | W/R | Hanis | C300 | Accepted | -